## Export Worksheet
PROJECT_ID | PROJECT_NAME | RISK_ID | TRANSACTION_ID | PERFORMANCEIMPACT_RISK_RANKING | COST_RISK_RANKING | SCHEDULE_RISK_RANKING | USER_ID | ID | FIRST_NAME | LAST_NAME | DATE_TIME | REASON | RISK_LOG_NOTE | EDITDATE | TREATMENTS_IMPLEMENTED
2126 | Amite River and Tributaries - East of the MS River Analysis | 2 | 1 | 3 | 1 | 1 | 4751 | 4751 | Barth | Benjamin | 2023-06-02 19:19 | New Project Risk | New Risk Added | 2023-06-02 19:19
2307 | Miami-Dade Back Bay Coastal Storm Risk Management Feasibility Study, Miami-Dade County, Florida | 1 | 1 | 4 | 1 | 1 | 488 | 488 | Elizabeth | Behrens | 2023-03-17 14:10 | New Project Risk | New Risk Added | 2023-03-17 14:10
2307 | Miami-Dade Back Bay Coastal Storm Risk Management Feasibility Study, Miami-Dade County, Florida | 2 | 1 | 1 | 1 | 1 | 5170 | 5170 | Alex | Colter | 2023-05-01 18:44 | New Project Risk | New Risk Added | 2023-05-01 18:44
3069 | Tampa Harbor Navigation Improvement Study | 2 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-17 19:27 | New Project Risk | New Risk Added | 2023-05-17 19:27
3069 | Tampa Harbor Navigation Improvement Study | 16 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 18:47 | New Project Risk | New Risk Added | 2023-05-18 18:47
3069 | Tampa Harbor Navigation Improvement Study | 18 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 19:10 | New Project Risk | New Risk Added | 2023-05-18 19:10
3069 | Tampa Harbor Navigation Improvement Study | 19 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 19:14 | New Project Risk | New Risk Added | 2023-05-18 19:14
3069 | Tampa Harbor Navigation Improvement Study | 14 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 18:11 | New Project Risk | New Risk Added | 2023-05-18 18:11
3069 | Tampa Harbor Navigation Improvement Study | 13 | 2 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 18:44 | Corrected Error | Corrected Risk Identity | 2023-05-18 18:44
3069 | Tampa Harbor Navigation Improvement Study | 4 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-17 19:56 | New Project Risk | New Risk Added | 2023-05-17 19:56
3069 | Tampa Harbor Navigation Improvement Study | 2 | 2 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 15:01 | Corrected Error | Changed milestone risk & response. | 2023-05-18 15:01
3069 | Tampa Harbor Navigation Improvement Study | 11 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 15:08 | New Project Risk | New Risk Added | 2023-05-18 15:08
3069 | Tampa Harbor Navigation Improvement Study | 13 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 15:21 | New Project Risk | New Risk Added | 2023-05-18 15:21
3069 | Tampa Harbor Navigation Improvement Study | 15 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 18:33 | New Project Risk | New Risk Added | 2023-05-18 18:33
3069 | Tampa Harbor Navigation Improvement Study | 17 | 1 | 2 | 1 | 1 | 4951 | 4951 | Laurel | Reichold | 2023-05-18 19:04 | New Project Risk | New Risk Added | 2023-05-18 19:04
3069 | Tampa Harbor Navigation Improvement Study | 6 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-05-18 14:07 | New Project Risk | New Risk Added | 2023-05-18 14:07
3069 | Tampa Harbor Navigation Improvement Study | 9 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-05-18 14:53 | New Project Risk | New Risk Added | 2023-05-18 14:53 | PLE-9-1
3069 | Tampa Harbor Navigation Improvement Study | 7 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-05-18 14:36 | New Project Risk | New Risk Added | 2023-05-18 14:36 | PRM-7-1, PRM-7-2, PRM-7-3
3069 | Tampa Harbor Navigation Improvement Study | 8 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-05-18 14:48 | New Project Risk | New Risk Added | 2023-05-18 14:48 | PLC-8-1
3069 | Tampa Harbor Navigation Improvement Study | 10 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-05-18 15:05 | New Project Risk | New Risk Added | 2023-05-18 15:05 | PLP-10-1
3069 | Tampa Harbor Navigation Improvement Study | 12 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-05-18 15:08 | New Project Risk | New Risk Added | 2023-05-18 15:08 | PLE-12-1
3069 | Tampa Harbor Navigation Improvement Study | 5 | 1 | 3 | 1 | 3 | -99 |  |  |  | 2023-05-18 13:53 | New Project Risk | New Risk Added | 2023-05-18 13:53 | PLP-5-1
3130 | Akutan Harbor Navigational Improvements, AK | 1 | 1 | 0 | 0 | 0 | 7887 |  |  |  | 2023-03-14 15:40 | New Project Risk | New Risk Added | 2023-03-14 15:40
3130 | Akutan Harbor Navigational Improvements, AK | 2 | 1 | 3 | 0 | 1 | 7887 |  |  |  | 2023-03-14 15:44 | New Project Risk | New Risk Added | 2023-03-14 15:44
3130 | Akutan Harbor Navigational Improvements, AK | 6 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 17:56 | New Project Risk | New Risk Added | 2023-03-14 17:56
3130 | Akutan Harbor Navigational Improvements, AK | 7 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 17:59 | New Project Risk | New Risk Added | 2023-03-14 17:59
3130 | Akutan Harbor Navigational Improvements, AK | 9 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 18:02 | New Project Risk | New Risk Added | 2023-03-14 18:02
3130 | Akutan Harbor Navigational Improvements, AK | 15 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 19:21 | New Project Risk | New Risk Added | 2023-03-14 19:21
3130 | Akutan Harbor Navigational Improvements, AK | 16 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 19:23 | New Project Risk | New Risk Added | 2023-03-14 19:23
3130 | Akutan Harbor Navigational Improvements, AK | 18 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 19:26 | New Project Risk | New Risk Added | 2023-03-14 19:26
3130 | Akutan Harbor Navigational Improvements, AK | 5 | 2 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 19:35 | Corrected Error |  | 2023-03-14 19:35
3130 | Akutan Harbor Navigational Improvements, AK | 19 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 15:46 | New Project Risk | New Risk Added | 2023-03-16 15:46
3130 | Akutan Harbor Navigational Improvements, AK | 21 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 15:49 | New Project Risk | New Risk Added | 2023-03-16 15:49
3130 | Akutan Harbor Navigational Improvements, AK | 22 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 17:13 | New Project Risk | New Risk Added | 2023-03-16 17:13
3130 | Akutan Harbor Navigational Improvements, AK | 23 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 17:15 | New Project Risk | New Risk Added | 2023-03-16 17:15
3130 | Akutan Harbor Navigational Improvements, AK | 24 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 17:16 | New Project Risk | New Risk Added | 2023-03-16 17:16
3130 | Akutan Harbor Navigational Improvements, AK | 25 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 17:18 | New Project Risk | New Risk Added | 2023-03-16 17:18
3130 | Akutan Harbor Navigational Improvements, AK | 27 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 17:24 | New Project Risk | New Risk Added | 2023-03-16 17:24
3130 | Akutan Harbor Navigational Improvements, AK | 3 | 1 | 2 | 0 | 0 | 7887 |  |  |  | 2023-03-14 16:10 | New Project Risk | New Risk Added | 2023-03-14 16:10
3130 | Akutan Harbor Navigational Improvements, AK | 4 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 16:12 | New Project Risk | New Risk Added | 2023-03-14 16:12
3130 | Akutan Harbor Navigational Improvements, AK | 5 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 16:20 | New Project Risk | New Risk Added | 2023-03-14 16:20
3130 | Akutan Harbor Navigational Improvements, AK | 12 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 18:16 | New Project Risk | New Risk Added | 2023-03-14 18:16
3130 | Akutan Harbor Navigational Improvements, AK | 26 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 17:23 | New Project Risk | New Risk Added | 2023-03-16 17:23
3130 | Akutan Harbor Navigational Improvements, AK | 11 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 18:07 | New Project Risk | New Risk Added | 2023-03-14 18:07
3130 | Akutan Harbor Navigational Improvements, AK | 14 | 1 | 2 | 0 | 1 | 7887 |  |  |  | 2023-03-14 19:19 | New Project Risk | New Risk Added | 2023-03-14 19:19
3130 | Akutan Harbor Navigational Improvements, AK | 8 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 18:01 | New Project Risk | New Risk Added | 2023-03-14 18:01
3130 | Akutan Harbor Navigational Improvements, AK | 20 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-16 15:47 | New Project Risk | New Risk Added | 2023-03-16 15:47
3130 | Akutan Harbor Navigational Improvements, AK | 10 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 18:05 | New Project Risk | New Risk Added | 2023-03-14 18:05 | PLE-10-1
3130 | Akutan Harbor Navigational Improvements, AK | 13 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 19:17 | New Project Risk | New Risk Added | 2023-03-14 19:17
3130 | Akutan Harbor Navigational Improvements, AK | 17 | 1 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 19:24 | New Project Risk | New Risk Added | 2023-03-14 19:24
3130 | Akutan Harbor Navigational Improvements, AK | 1 | 2 | 0 | 0 | 0 | 7887 |  |  |  | 2023-03-14 19:29 | New Information |  | 2023-03-14 19:29
3130 | Akutan Harbor Navigational Improvements, AK | 2 | 2 | 3 | 0 | 1 | 7887 |  |  |  | 2023-03-14 19:31 | Conditions Changed |  | 2023-03-14 19:31
3130 | Akutan Harbor Navigational Improvements, AK | 3 | 2 | 2 | 0 | 0 | 7887 |  |  |  | 2023-03-14 19:32 | Corrected Error |  | 2023-03-14 19:32
3130 | Akutan Harbor Navigational Improvements, AK | 4 | 2 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 19:34 | Corrected Error |  | 2023-03-14 19:34
3130 | Akutan Harbor Navigational Improvements, AK | 6 | 2 | 2 | 1 | 1 | 7887 |  |  |  | 2023-03-14 19:36 | Corrected Error |  | 2023-03-14 19:36
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 1 | 1 | 3 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-02-24 18:10 | New Project Risk | New Risk Added | 2023-02-24 18:10
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 2 | 1 | 3 | 4 | 3 | 6246 | 6246 | Fay | Lachney | 2023-06-30 14:00 | New Project Risk | New Risk Added | 2023-06-30 14:00 | PRM-2-1
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 1 | 2 | 3 | 4 | 3 | 6246 | 6246 | Fay | Lachney | 2023-06-30 14:04 | New Information | Potential schedule impact adjusted based on team discussions | 2023-06-30 14:04
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 3 | 1 | 3 | 4 | 4 | 6246 | 6246 | Fay | Lachney | 2023-06-30 14:36 | New Project Risk | New Risk Added | 2023-06-30 14:36
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 2 | 2 | 3 | 4 | 3 | 6246 | 6246 | Fay | Lachney | 2023-06-30 14:37 | Corrected Error |  | 2023-06-30 14:37
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 5 | 1 | 2 | 4 | 3 | 6246 | 6246 | Fay | Lachney | 2023-07-07 19:56 | New Project Risk | New Risk Added | 2023-07-07 19:56
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 7 | 1 | 4 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-07 20:23 | New Project Risk | New Risk Added | 2023-07-07 20:23
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 9 | 1 | 3 | 4 | 3 | 6246 | 6246 | Fay | Lachney | 2023-07-07 21:29 | New Project Risk | New Risk Added | 2023-07-07 21:29
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 14 | 1 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-07 23:29 | New Project Risk | New Risk Added | 2023-07-07 23:29
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 16 | 1 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-10 04:42 | New Project Risk | New Risk Added | 2023-07-10 04:42
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 17 | 1 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-10 04:58 | New Project Risk | New Risk Added | 2023-07-10 04:58
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 19 | 1 | 2 | 0 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-12 10:31 | New Project Risk | New Risk Added | 2023-07-12 10:31
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 20 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-14 13:04 | New Project Risk | New Risk Added | 2023-07-14 13:04
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 21 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-14 13:17 | New Project Risk | New Risk Added | 2023-07-14 13:17 | EHH-21-1
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 5 | 2 | 3 | 4 | 3 | 6246 | 6246 | Fay | Lachney | 2023-07-07 19:59 | Corrected Error |  | 2023-07-07 19:59
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 6 | 1 | 3 | 4 | 3 | 6246 | 6246 | Fay | Lachney | 2023-07-07 20:08 | New Project Risk | New Risk Added | 2023-07-07 20:08
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 8 | 1 | 4 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-07 20:54 | New Project Risk | New Risk Added | 2023-07-07 20:54
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 11 | 1 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-07 22:13 | New Project Risk | New Risk Added | 2023-07-07 22:13
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 22 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-17 02:15 | New Project Risk | New Risk Added | 2023-07-17 02:15
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 23 | 1 | 1 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-17 02:30 | New Project Risk | New Risk Added | 2023-07-17 02:30
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 25 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 09:44 | New Project Risk | New Risk Added | 2023-07-18 09:44
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 26 | 1 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 09:48 | New Project Risk | New Risk Added | 2023-07-18 09:48
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 26 | 2 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 09:52 | Corrected Error |  | 2023-07-18 09:52
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 27 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 09:56 | New Project Risk | New Risk Added | 2023-07-18 09:56
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 28 | 1 | 2 | 2 | 3 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:04 | New Project Risk | New Risk Added | 2023-07-18 10:04
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 29 | 1 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:10 | New Project Risk | New Risk Added | 2023-07-18 10:10
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 30 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:16 | New Project Risk | New Risk Added | 2023-07-18 10:16
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 31 | 1 | 2 | 4 | 4 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:21 | New Project Risk | New Risk Added | 2023-07-18 10:21
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 32 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:27 | New Project Risk | New Risk Added | 2023-07-18 10:27
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 33 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:39 | New Project Risk | New Risk Added | 2023-07-18 10:39
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 35 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:49 | New Project Risk | New Risk Added | 2023-07-18 10:49
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 36 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:56 | New Project Risk | New Risk Added | 2023-07-18 10:56
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 37 | 1 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 11:00 | New Project Risk | New Risk Added | 2023-07-18 11:00
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 38 | 1 | 2 | 4 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 11:04 | New Project Risk | New Risk Added | 2023-07-18 11:04
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 39 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 11:11 | New Project Risk | New Risk Added | 2023-07-18 11:11
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 40 | 1 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 11:13 | New Project Risk | New Risk Added | 2023-07-18 11:13
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 41 | 1 | 3 | 0 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 11:17 | New Project Risk | New Risk Added | 2023-07-18 11:17
3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 30 | 2 | 2 | 2 | 2 | 6246 | 6246 | Fay | Lachney | 2023-07-18 10:29 | New Information | Better category for Performance was selected. | 2023-07-18 10:29
3531 | Lower Missouri Brunswick L-246 | 4 | 1 | 2 | 2 | 2 | 4830 | 4830 | Ricki | Mitchell | 2023-02-03 15:36 | New Project Risk | New Risk Added | 2023-02-03 15:36
3531 | Lower Missouri Brunswick L-246 | 5 | 1 | 0 | 2 | 0 | 8774 | 8774 | Naomi | Fraenkel | 2023-02-03 16:17 | New Project Risk | New Risk Added | 2023-02-03 16:17
3531 | Lower Missouri Brunswick L-246 | 4 | 2 | 2 | 2 | 2 | 8774 | 8774 | Naomi | Fraenkel | 2023-03-03 17:36 | New Information |  | 2023-03-03 17:36
3531 | Lower Missouri Brunswick L-246 | 4 | 5 | 2 | 2 | 2 | 8774 | 8774 | Naomi | Fraenkel | 2023-03-03 17:48 | Corrected Error |  | 2023-03-03 17:48
3531 | Lower Missouri Brunswick L-246 | 4 | 6 | 2 | 2 | 2 | 8774 | 8774 | Naomi | Fraenkel | 2023-03-03 17:55 | Corrected Error |  | 2023-03-03 17:55
3531 | Lower Missouri Brunswick L-246 | 4 | 3 | 2 | 2 | 2 | 8774 | 8774 | Naomi | Fraenkel | 2023-03-03 17:37 | Corrected Error |  | 2023-03-03 17:37
3531 | Lower Missouri Brunswick L-246 | 4 | 4 | 2 | 2 | 2 | 8774 | 8774 | Naomi | Fraenkel | 2023-03-03 17:37 | Corrected Error |  | 2023-03-03 17:37
3430 | LSJ Lathrop Manteca Feasibility Study | 3 | 1 | 2 | 1 | 1 | 7687 | 7687 | Sara | Schultz | 2023-04-06 15:19 | New Project Risk | New Risk Added | 2023-04-06 15:19
3430 | LSJ Lathrop Manteca Feasibility Study | 4 | 1 | 0 | 1 | 2 | 7687 | 7687 | Sara | Schultz | 2023-04-06 15:48 | New Project Risk | New Risk Added | 2023-04-06 15:48
3430 | LSJ Lathrop Manteca Feasibility Study | 4 | 2 | 2 | 1 | 2 | 7687 | 7687 | Sara | Schultz | 2023-04-06 15:59 | Corrected Error |  | 2023-04-06 15:59
3430 | LSJ Lathrop Manteca Feasibility Study | 4 | 3 | 3 | 1 | 2 | 7687 | 7687 | Sara | Schultz | 2023-04-06 16:01 | Corrected Error |  | 2023-04-06 16:01
3430 | LSJ Lathrop Manteca Feasibility Study | 11 | 1 | 2 | 1 | 2 | 7687 | 7687 | Sara | Schultz | 2023-04-27 15:39 | New Project Risk | New Risk Added | 2023-04-27 15:39
3430 | LSJ Lathrop Manteca Feasibility Study | 7 | 1 | 3 | 1 | 1 | 7687 | 7687 | Sara | Schultz | 2023-04-06 18:06 | New Project Risk | New Risk Added | 2023-04-06 18:06
3430 | LSJ Lathrop Manteca Feasibility Study | 9 | 1 | 0 | 0 | 0 | 7687 | 7687 | Sara | Schultz | 2023-04-06 18:18 | New Project Risk | New Risk Added | 2023-04-06 18:18
3430 | LSJ Lathrop Manteca Feasibility Study | 10 | 1 | 0 | 0 | 0 | 7687 | 7687 | Sara | Schultz | 2023-04-06 18:26 | New Project Risk | New Risk Added | 2023-04-06 18:26
3430 | LSJ Lathrop Manteca Feasibility Study | 5 | 1 | 2 | 1 | 2 | 7687 | 7687 | Sara | Schultz | 2023-04-06 17:25 | New Project Risk | New Risk Added | 2023-04-06 17:25
3430 | LSJ Lathrop Manteca Feasibility Study | 6 | 1 | 3 | 1 | 3 | 7687 | 7687 | Sara | Schultz | 2023-04-06 17:42 | New Project Risk | New Risk Added | 2023-04-06 17:42
3430 | LSJ Lathrop Manteca Feasibility Study | 8 | 1 | 1 | 1 | 1 | 7687 | 7687 | Sara | Schultz | 2023-04-06 18:12 | New Project Risk | New Risk Added | 2023-04-06 18:12
3430 | LSJ Lathrop Manteca Feasibility Study | 6 | 2 | 3 | 3 | 3 | 7687 | 7687 | Sara | Schultz | 2023-04-06 20:19 | New Information |  | 2023-04-06 20:19
3430 | LSJ Lathrop Manteca Feasibility Study | 4 | 4 | 3 | 1 | 2 | 7687 | 7687 | Sara | Schultz | 2023-04-06 20:39 | New Information |  | 2023-04-06 20:39
3430 | LSJ Lathrop Manteca Feasibility Study | 4 | 5 | 3 | 2 | 2 | 7687 | 7687 | Sara | Schultz | 2023-04-06 20:42 | Corrected Error |  | 2023-04-06 20:42
3430 | LSJ Lathrop Manteca Feasibility Study | 5 | 2 | 2 | 2 | 2 | 7687 | 7687 | Sara | Schultz | 2023-04-06 20:53 | New Information |  | 2023-04-06 20:53
3430 | LSJ Lathrop Manteca Feasibility Study | 12 | 1 | 2 | 4 | 4 | 8752 |  |  |  | 2023-05-05 21:36 | New Project Risk | New Risk Added | 2023-05-05 21:36
3430 | LSJ Lathrop Manteca Feasibility Study | 12 | 2 | 2 | 4 | 4 | 8752 |  |  |  | 2023-05-05 21:40 | Corrected Error |  | 2023-05-05 21:40
3430 | LSJ Lathrop Manteca Feasibility Study | 1 | 2 | 3 | 2 | 1 | 298 |  |  |  | 2023-06-08 14:05 | Corrected Error | Risk mitigation of including FPMP and additional costs for EO 11988 coordination, totaling $300,000 k, is included in the scope of the study. | 2023-06-08 14:05 | PLP-1-1
3430 | LSJ Lathrop Manteca Feasibility Study | 1 | 1 | 3 | 2 | 1 | 298 |  |  |  | 2023-03-31 14:02 | New Project Risk | New Risk Added | 2023-03-31 14:02
3430 | LSJ Lathrop Manteca Feasibility Study | 12 | 3 | 2 | 2 | 3 | 298 |  |  |  | 2023-06-08 14:01 | Corrected Error | The PDT has already included the sensitivity analysis in the scope of the study to partially mitigate this risk. The remaining risk is the need for full inland climate change quantitative analysis. | 2023-06-08 14:01 | EHH-12-2
3430 | LSJ Lathrop Manteca Feasibility Study | 3 | 2 | 2 | 1 | 1 | 298 |  |  |  | 2023-06-08 14:08 | Corrected Error | Risk mitigation has been implemented to eliminate this risk. | 2023-06-08 14:08 | PLE-3-1
3430 | LSJ Lathrop Manteca Feasibility Study | 4 | 6 | 3 | 1 | 1 | 298 |  |  |  | 2023-06-08 14:20 | Corrected Error | This risk has been mitigated with the inclusion of additional coordination funds in the study budget and early/ongoing coordination with the agencies. | 2023-06-08 14:20 | PLE-4-1
3430 | LSJ Lathrop Manteca Feasibility Study | 3 | 3 | 2 | 1 | 1 | 298 |  |  |  | 2023-06-08 14:21 | Corrected Error | Est. for mitigation action was updated. | 2023-06-08 14:21
3430 | LSJ Lathrop Manteca Feasibility Study | 5 | 3 | 2 | 1 | 1 | 298 |  |  |  | 2023-06-08 14:23 | Corrected Error | This risk is resolved since LifeSIM is included in the study risk. | 2023-06-08 14:23 | PLP-5-1
2969 | Ponte Vedra Beach CSRM | 3 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-11 13:46 | New Project Risk | New Risk Added | 2023-07-11 13:46
2969 | Ponte Vedra Beach CSRM | 4 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-11 14:13 | New Project Risk | New Risk Added | 2023-07-11 14:13
2969 | Ponte Vedra Beach CSRM | 5 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-11 14:22 | New Project Risk | New Risk Added | 2023-07-11 14:22
2969 | Ponte Vedra Beach CSRM | 4 | 2 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-11 14:25 | Corrected Error |  | 2023-07-11 14:25
2969 | Ponte Vedra Beach CSRM | 3 | 2 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:05 | Corrected Error |  | 2023-07-17 14:05
2969 | Ponte Vedra Beach CSRM | 6 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:11 | New Project Risk | New Risk Added | 2023-07-17 14:11
2969 | Ponte Vedra Beach CSRM | 7 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:15 | New Project Risk | New Risk Added | 2023-07-17 14:15
2969 | Ponte Vedra Beach CSRM | 6 | 2 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:17 | Corrected Error |  | 2023-07-17 14:17
2969 | Ponte Vedra Beach CSRM | 7 | 2 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:22 | Corrected Error |  | 2023-07-17 14:22
2969 | Ponte Vedra Beach CSRM | 8 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:27 | New Project Risk | New Risk Added | 2023-07-17 14:27
2969 | Ponte Vedra Beach CSRM | 9 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:31 | New Project Risk | New Risk Added | 2023-07-17 14:31
2969 | Ponte Vedra Beach CSRM | 10 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:34 | New Project Risk | New Risk Added | 2023-07-17 14:34
2969 | Ponte Vedra Beach CSRM | 12 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:37 | New Project Risk | New Risk Added | 2023-07-17 14:37
2969 | Ponte Vedra Beach CSRM | 10 | 2 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:41 | Corrected Error |  | 2023-07-17 14:41
2969 | Ponte Vedra Beach CSRM | 5 | 2 | 3 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:16 | Corrected Error |  | 2023-07-17 14:16
2969 | Ponte Vedra Beach CSRM | 6 | 3 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:38 | Corrected Error |  | 2023-07-17 14:38
2969 | Ponte Vedra Beach CSRM | 7 | 3 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:38 | Corrected Error |  | 2023-07-17 14:38
2969 | Ponte Vedra Beach CSRM | 8 | 2 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:40 | Corrected Error |  | 2023-07-17 14:40
2969 | Ponte Vedra Beach CSRM | 9 | 2 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:40 | Corrected Error |  | 2023-07-17 14:40
2969 | Ponte Vedra Beach CSRM | 13 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:43 | New Project Risk | New Risk Added | 2023-07-17 14:43
2969 | Ponte Vedra Beach CSRM | 14 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:54 | New Project Risk | New Risk Added | 2023-07-17 14:54
2969 | Ponte Vedra Beach CSRM | 15 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:58 | New Project Risk | New Risk Added | 2023-07-17 14:58
2969 | Ponte Vedra Beach CSRM | 14 | 2 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 14:59 | Corrected Error |  | 2023-07-17 14:59
2969 | Ponte Vedra Beach CSRM | 9 | 3 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:02 | Corrected Error |  | 2023-07-17 15:02
2969 | Ponte Vedra Beach CSRM | 14 | 3 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:03 | Corrected Error |  | 2023-07-17 15:03
2969 | Ponte Vedra Beach CSRM | 16 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:05 | New Project Risk | New Risk Added | 2023-07-17 15:05
2969 | Ponte Vedra Beach CSRM | 17 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:13 | New Project Risk | New Risk Added | 2023-07-17 15:13
2969 | Ponte Vedra Beach CSRM | 18 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:16 | New Project Risk | New Risk Added | 2023-07-17 15:16
2969 | Ponte Vedra Beach CSRM | 19 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:19 | New Project Risk | New Risk Added | 2023-07-17 15:19
2969 | Ponte Vedra Beach CSRM | 20 | 1 | 3 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:22 | New Project Risk | New Risk Added | 2023-07-17 15:22
2969 | Ponte Vedra Beach CSRM | 21 | 1 | 2 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:25 | New Project Risk | New Risk Added | 2023-07-17 15:25
2969 | Ponte Vedra Beach CSRM | 22 | 1 | 3 | 1 | 1 | 9374 | 9374 | Joseph | Collum | 2023-07-17 15:27 | New Project Risk | New Risk Added | 2023-07-17 15:27
3555 | St. Augustine Back Bay CSRM | 13 | 1 | 3 | 4 | 3 | 390 | 390 | Edwin | Rossman | 2023-04-20 12:38 | New Project Risk | New Risk Added | 2023-04-20 12:38
3555 | St. Augustine Back Bay CSRM | 14 | 1 | 2 | 4 | 4 | 390 | 390 | Edwin | Rossman | 2023-04-20 12:42 | New Project Risk | New Risk Added | 2023-04-20 12:42
3555 | St. Augustine Back Bay CSRM | 15 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-04-26 15:20 | New Project Risk | New Risk Added | 2023-04-26 15:20
3555 | St. Augustine Back Bay CSRM | 7 | 3 | 1 | 4 | 4 | 4614 |  |  |  | 2023-04-26 15:50 | New Information |  | 2023-04-26 15:50
3555 | St. Augustine Back Bay CSRM | 6 | 3 | 3 | 4 | 3 | 4614 |  |  |  | 2023-04-26 16:05 | New Information |  | 2023-04-26 16:05
3555 | St. Augustine Back Bay CSRM | 1 | 2 | 4 | 4 | 4 | 4614 |  |  |  | 2023-04-26 16:07 | New Information |  | 2023-04-26 16:07
3555 | St. Augustine Back Bay CSRM | 2 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-03-14 15:32 | New Project Risk | New Risk Added | 2023-03-14 15:32 | PLE-28-1
3555 | St. Augustine Back Bay CSRM | 3 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-03-14 15:40 | New Project Risk | New Risk Added | 2023-03-14 15:40 | PLE-28-1
3555 | St. Augustine Back Bay CSRM | 4 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-03-14 15:42 | New Project Risk | New Risk Added | 2023-03-14 15:42
3555 | St. Augustine Back Bay CSRM | 5 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-03-14 15:43 | New Project Risk | New Risk Added | 2023-03-14 15:43
3555 | St. Augustine Back Bay CSRM | 6 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-03-14 15:45 | New Project Risk | New Risk Added | 2023-03-14 15:45
3555 | St. Augustine Back Bay CSRM | 8 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-03-20 19:44 | New Project Risk | New Risk Added | 2023-03-20 19:44
3555 | St. Augustine Back Bay CSRM | 1 | 1 | 3 | 1 | 4 | 4614 |  |  |  | 2023-03-13 14:00 | New Project Risk | New Risk Added | 2023-03-13 14:00
3555 | St. Augustine Back Bay CSRM | 7 | 1 | 2 | 1 | 1 | 4614 |  |  |  | 2023-03-15 18:53 | New Project Risk | New Risk Added | 2023-03-15 18:53
3555 | St. Augustine Back Bay CSRM | 7 | 2 | 1 | 4 | 3 | 4614 |  |  |  | 2023-03-20 19:34 | New Information |  | 2023-03-20 19:34 | OTH-7-1
3555 | St. Augustine Back Bay CSRM | 11 | 2 | 3 | 4 | 3 | 4614 |  |  |  | 2023-04-26 16:08 | New Information |  | 2023-04-26 16:08
3555 | St. Augustine Back Bay CSRM | 16 | 1 | 2 | 0 | 0 | 162 |  |  |  | 2023-04-26 19:45 | New Project Risk | New Risk Added | 2023-04-26 19:45 | PLE-16-1
3555 | St. Augustine Back Bay CSRM | 17 | 1 | 2 | 1 | 1 | 162 |  |  |  | 2023-04-26 19:57 | New Project Risk | New Risk Added | 2023-04-26 19:57
3555 | St. Augustine Back Bay CSRM | 11 | 1 | 0 | 4 | 3 | 8814 |  |  |  | 2023-03-23 13:04 | New Project Risk | New Risk Added | 2023-03-23 13:04
3555 | St. Augustine Back Bay CSRM | 9 | 1 | 2 | 1 | 1 | 8814 |  |  |  | 2023-03-23 12:26 | New Project Risk | New Risk Added | 2023-03-23 12:26
3555 | St. Augustine Back Bay CSRM | 12 | 1 | 1 | 0 | 0 | 8814 |  |  |  | 2023-03-23 13:11 | New Project Risk | New Risk Added | 2023-03-23 13:11
3555 | St. Augustine Back Bay CSRM | 6 | 2 | 2 | 1 | 4 | 8817 |  |  |  | 2023-04-05 13:03 | New Information |  | 2023-04-05 13:03
3555 | St. Augustine Back Bay CSRM | 3 | 2 | 2 | 0 | 0 | 7848 |  |  |  | 2023-04-04 19:49 | New Information | Updated details by PDEC | 2023-04-04 19:49
3571 | Boston Metropolitan Area, MA | 1 | 1 | 0 | 3 | 3 | 249 |  |  |  | 2023-06-20 22:13 | New Project Risk | New Risk Added | 2023-06-20 22:13
3571 | Boston Metropolitan Area, MA | 2 | 1 | 2 | 0 | 0 | 249 |  |  |  | 2023-06-20 22:23 | New Project Risk | New Risk Added | 2023-06-20 22:23 | EHH-2-1
3571 | Boston Metropolitan Area, MA | 3 | 1 | 2 | 2 | 0 | 249 |  |  |  | 2023-06-20 22:31 | New Project Risk | New Risk Added | 2023-06-20 22:31
3571 | Boston Metropolitan Area, MA | 4 | 1 | 2 | 0 | 2 | 249 |  |  |  | 2023-06-20 22:38 | New Project Risk | New Risk Added | 2023-06-20 22:38
3571 | Boston Metropolitan Area, MA | 5 | 1 | 2 | 1 | 0 | 249 |  |  |  | 2023-06-20 22:49 | New Project Risk | New Risk Added | 2023-06-20 22:49
3571 | Boston Metropolitan Area, MA | 6 | 1 | 2 | 0 | 0 | 249 |  |  |  | 2023-06-20 22:56 | New Project Risk | New Risk Added | 2023-06-20 22:56
3571 | Boston Metropolitan Area, MA | 4 | 2 | 2 | 0 | 2 | 249 |  |  |  | 2023-06-20 22:59 | Corrected Error |  | 2023-06-20 22:59
3572 | City of Boston Coastal Storm Risk | 4 | 1 | 2 | 1 | 1 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:03 | New Project Risk | New Risk Added | 2023-01-30 16:03 | EHH-3-1
3572 | City of Boston Coastal Storm Risk | 4 | 2 | 3 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:05 | New Information | If I don't keep saving updates, the program times out on me. | 2023-01-30 16:05 | EHH-3-1
3572 | City of Boston Coastal Storm Risk | 4 | 3 | 3 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:08 | New Information | Updating Risk | 2023-01-30 16:08 | EHH-3-1
3572 | City of Boston Coastal Storm Risk | 4 | 4 | 3 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:10 | New Information | Updating Risk | 2023-01-30 16:10 | EHH-4-1, EHH-3-1
3572 | City of Boston Coastal Storm Risk | 6 | 1 | 2 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:33 | New Project Risk | New Risk Added | 2023-01-30 16:33 | PLE-5-1, EHH-3-1
3572 | City of Boston Coastal Storm Risk | 7 | 2 | 3 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:59 | New Information | Update to risk. | 2023-01-30 16:59 | PLE-5-1, EHH-3-1
3572 | City of Boston Coastal Storm Risk | 8 | 4 | 2 | 4 | 4 | 4490 | 4490 | Brent J. | Andrews | 2023-01-31 16:46 | New Information | Updated information | 2023-01-31 16:46
3572 | City of Boston Coastal Storm Risk | 4 | 5 | 3 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-02-14 19:48 | New Information |  | 2023-02-14 19:48 | EHH-4-2
3572 | City of Boston Coastal Storm Risk | 15 | 1 | 3 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 19:35 | New Project Risk | New Risk Added | 2023-03-01 19:35 | OTH-15-1
3572 | City of Boston Coastal Storm Risk | 16 | 1 | 4 | 2 | 3 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 19:52 | New Project Risk | New Risk Added | 2023-03-01 19:52 | OTH-16-1
3572 | City of Boston Coastal Storm Risk | 17 | 1 | 4 | 0 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 20:05 | New Project Risk | New Risk Added | 2023-03-01 20:05 | PLP-17-1
3572 | City of Boston Coastal Storm Risk | 18 | 1 | 3 | 4 | 4 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 20:18 | New Project Risk | New Risk Added | 2023-03-01 20:18 | OTH-18-1
3572 | City of Boston Coastal Storm Risk | 17 | 2 | 4 | 0 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 22:36 | Corrected Error |  | 2023-03-01 22:36
3572 | City of Boston Coastal Storm Risk | 4 | 6 | 3 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-03-23 19:42 | Risk Response implemented | 15 March an IPR was held with HH&C CoP, L&PC Team, MSC, and PCX to discuss modeling strategy. 17 March, the Chief of Planning at NAD approved the modeling strategy. | 2023-03-23 19:42
3572 | City of Boston Coastal Storm Risk | 4 | 7 | 3 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-03-24 14:18 | Corrected Error |  | 2023-03-24 14:18
3572 | City of Boston Coastal Storm Risk | 28 | 1 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-29 14:51 | New Project Risk | New Risk Added | 2023-03-29 14:51 | PLE-28-1, PLE-28-2
3572 | City of Boston Coastal Storm Risk | 27 | 2 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-29 15:03 | Corrected Error |  | 2023-03-29 15:03
3572 | City of Boston Coastal Storm Risk | 5 | 2 | 2 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-02-14 19:44 | New Information | update | 2023-02-14 19:44 | PLE-5-2
3572 | City of Boston Coastal Storm Risk | 10 | 2 | 2 | 0 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-02-14 19:52 | New Information |  | 2023-02-14 19:52 | PLP-10-1
3572 | City of Boston Coastal Storm Risk | 12 | 1 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-02-14 20:10 | New Project Risk | New Risk Added | 2023-02-14 20:10 | EHH-12-1
3572 | City of Boston Coastal Storm Risk | 25 | 3 | 1 | 2 | 1 | 4490 | 4490 | Brent J. | Andrews | 2023-03-23 20:00 | Corrected Error | Corrected the name of the Opportunity. | 2023-03-23 20:00
3572 | City of Boston Coastal Storm Risk | 17 | 3 | 2 | 0 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-27 18:02 | New Information | Discussions with MSC Real Estate and the District Real Estate Team reduced the Performance Risk. | 2023-03-27 18:02
3572 | City of Boston Coastal Storm Risk | 13 | 1 | 2 | 0 | 3 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 18:15 | New Project Risk | New Risk Added | 2023-03-01 18:15
3572 | City of Boston Coastal Storm Risk | 13 | 2 | 2 | 0 | 3 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 18:16 | Conditions Changed |  | 2023-03-01 18:16
3572 | City of Boston Coastal Storm Risk | 6 | 4 | 3 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 18:26 | Corrected Error |  | 2023-03-01 18:26
3572 | City of Boston Coastal Storm Risk | 6 | 5 | 4 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 18:52 | Corrected Error |  | 2023-03-01 18:52
3572 | City of Boston Coastal Storm Risk | 19 | 1 | 0 | 4 | 4 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 20:33 | New Project Risk | New Risk Added | 2023-03-01 20:33 | EGT-19-1
3572 | City of Boston Coastal Storm Risk | 20 | 1 | 0 | 0 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 20:42 | New Project Risk | New Risk Added | 2023-03-01 20:42 | EGT-20-1
3572 | City of Boston Coastal Storm Risk | 28 | 2 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-29 14:53 | Corrected Error |  | 2023-03-29 14:53
3572 | City of Boston Coastal Storm Risk | 5 | 4 | 2 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-03-29 15:03 | Corrected Error |  | 2023-03-29 15:03
3572 | City of Boston Coastal Storm Risk | 10 | 3 | 3 | 0 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 19:07 | Conditions Changed |  | 2023-03-01 19:07 | PLP-10-2
3572 | City of Boston Coastal Storm Risk | 12 | 2 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 19:11 | Corrected Error |  | 2023-03-01 19:11
3572 | City of Boston Coastal Storm Risk | 14 | 1 | 3 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 19:21 | New Project Risk | New Risk Added | 2023-03-01 19:21 | PLE-14-1, PLE-14-2
3572 | City of Boston Coastal Storm Risk | 21 | 1 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 21:38 | New Project Risk | New Risk Added | 2023-03-01 21:38 | PLE-21-1, PLE-21-2
3572 | City of Boston Coastal Storm Risk | 22 | 1 | 3 | 0 | 4 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 21:48 | New Project Risk | New Risk Added | 2023-03-01 21:48 | PLE-22-1, PLE-22-2
3572 | City of Boston Coastal Storm Risk | 23 | 1 | 4 | 0 | 4 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 21:56 | New Project Risk | New Risk Added | 2023-03-01 21:56 | OTH-23-1
3572 | City of Boston Coastal Storm Risk | 25 | 1 | 1 | 2 | 1 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 22:14 | New Project Risk | New Risk Added | 2023-03-01 22:14
3572 | City of Boston Coastal Storm Risk | 26 | 1 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 22:26 | New Project Risk | New Risk Added | 2023-03-01 22:26 | PLE-26-1
3572 | City of Boston Coastal Storm Risk | 5 | 1 | 2 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:14 | New Project Risk | New Risk Added | 2023-01-30 16:14 | EHH-3-1
3572 | City of Boston Coastal Storm Risk | 6 | 2 | 2 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:39 | New Information | Risk updated. | 2023-01-30 16:39 | EHH-3-1, EHH-6-1, PLE-5-1, EHH-6-2
3572 | City of Boston Coastal Storm Risk | 7 | 1 | 3 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 16:55 | New Project Risk | New Risk Added | 2023-01-30 16:55 | EHH-3-1, PLE-7-1, PLE-5-1
3572 | City of Boston Coastal Storm Risk | 8 | 1 | 2 | 3 | 3 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 17:06 | New Project Risk | New Risk Added | 2023-01-30 17:06 | EHH-3-1, RLE-8-1, PLE-5-1
3572 | City of Boston Coastal Storm Risk | 10 | 1 | 2 | 0 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 17:19 | New Project Risk | New Risk Added | 2023-01-30 17:19 | PLE-5-1, EHH-3-1
3572 | City of Boston Coastal Storm Risk | 8 | 2 | 2 | 3 | 3 | 4490 | 4490 | Brent J. | Andrews | 2023-01-30 17:19 | New Information |  | 2023-01-30 17:19 | PLE-5-1, EHH-3-1
3572 | City of Boston Coastal Storm Risk | 8 | 3 | 2 | 3 | 3 | 4490 | 4490 | Brent J. | Andrews | 2023-01-31 14:43 | New Information | update POC | 2023-01-31 14:43
3572 | City of Boston Coastal Storm Risk | 24 | 1 | 1 | 1 | 1 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 22:02 | New Project Risk | New Risk Added | 2023-03-01 22:02
3572 | City of Boston Coastal Storm Risk | 6 | 3 | 2 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 18:20 | Risk Response implemented |  | 2023-03-01 18:20
3572 | City of Boston Coastal Storm Risk | 21 | 2 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-01 21:50 | Corrected Error |  | 2023-03-01 21:50
3572 | City of Boston Coastal Storm Risk | 5 | 3 | 2 | 0 | 0 | 4490 | 4490 | Brent J. | Andrews | 2023-03-23 19:54 | Conditions Changed | On March 17th, 2023 an IPR was held with the VT, HH&C CoP, CPR CoP, PCX and PDT. A decision was made to refine CHS and use G2 as the economic model. However, to ensure accuracy in the FWOP floodplain, a Targeted ATR will be performed. This decision was approved by the NAD Chief of Planning on 17 March 2023. | 2023-03-23 19:54
3572 | City of Boston Coastal Storm Risk | 12 | 3 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-23 19:55 | Corrected Error | changed the word validation to refinement for the CHS Coastal Model. | 2023-03-23 19:55
3572 | City of Boston Coastal Storm Risk | 25 | 2 | 1 | 2 | 1 | 4490 | 4490 | Brent J. | Andrews | 2023-03-23 19:59 | Corrected Error | changed the term Validation to refinement for the CHS Coastal Model. | 2023-03-23 19:59
3572 | City of Boston Coastal Storm Risk | 27 | 1 | 2 | 2 | 2 | 4490 | 4490 | Brent J. | Andrews | 2023-03-23 20:15 | New Project Risk | New Risk Added | 2023-03-23 20:15 | EHH-27-1
3576 | Owyhee | 1 | 1 | 2 | 0 | 0 | 2919 | 2919 | Courtney | Jackson | 2023-02-02 17:33 | New Project Risk | New Risk Added | 2023-02-02 17:33
3574 | Lower Missouri River Jefferson City L-142 | 1 | 1 | 2 | 4 | 3 | 4051 |  |  |  | 2023-04-11 03:09 | New Project Risk | New Risk Added | 2023-04-11 03:09
3574 | Lower Missouri River Jefferson City L-142 | 6 | 1 | 2 | 4 | 4 | 4051 |  |  |  | 2023-04-14 18:40 | New Project Risk | New Risk Added | 2023-04-14 18:40
3574 | Lower Missouri River Jefferson City L-142 | 13 | 1 | 2 | 2 | 3 | 4051 |  |  |  | 2023-04-28 23:16 | New Project Risk | New Risk Added | 2023-04-28 23:16
3574 | Lower Missouri River Jefferson City L-142 | 14 | 1 | 3 | 4 | 4 | 4051 |  |  |  | 2023-04-28 23:18 | New Project Risk | New Risk Added | 2023-04-28 23:18
3574 | Lower Missouri River Jefferson City L-142 | 15 | 1 | 3 | 2 | 2 | 4051 |  |  |  | 2023-04-28 23:23 | New Project Risk | New Risk Added | 2023-04-28 23:23
3574 | Lower Missouri River Jefferson City L-142 | 15 | 2 | 3 | 2 | 2 | 4051 |  |  |  | 2023-04-28 23:25 | Corrected Error |  | 2023-04-28 23:25
3574 | Lower Missouri River Jefferson City L-142 | 17 | 1 | 2 | 0 | 3 | 4051 |  |  |  | 2023-04-28 23:38 | New Project Risk | New Risk Added | 2023-04-28 23:38
3574 | Lower Missouri River Jefferson City L-142 | 2 | 1 | 2 | 4 | 3 | 4051 |  |  |  | 2023-04-14 18:23 | New Project Risk | New Risk Added | 2023-04-14 18:23
3574 | Lower Missouri River Jefferson City L-142 | 3 | 1 | 2 | 4 | 4 | 4051 |  |  |  | 2023-04-14 18:28 | New Project Risk | New Risk Added | 2023-04-14 18:28
3574 | Lower Missouri River Jefferson City L-142 | 4 | 1 | 2 | 2 | 3 | 4051 |  |  |  | 2023-04-14 18:32 | New Project Risk | New Risk Added | 2023-04-14 18:32
3574 | Lower Missouri River Jefferson City L-142 | 5 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-04-14 18:37 | New Project Risk | New Risk Added | 2023-04-14 18:37
3574 | Lower Missouri River Jefferson City L-142 | 7 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-04-14 18:42 | New Project Risk | New Risk Added | 2023-04-14 18:42
3574 | Lower Missouri River Jefferson City L-142 | 8 | 1 | 2 | 4 | 2 | 4051 |  |  |  | 2023-04-14 18:45 | New Project Risk | New Risk Added | 2023-04-14 18:45
3574 | Lower Missouri River Jefferson City L-142 | 9 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-04-14 18:47 | New Project Risk | New Risk Added | 2023-04-14 18:47
3574 | Lower Missouri River Jefferson City L-142 | 10 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-04-14 18:58 | New Project Risk | New Risk Added | 2023-04-14 18:58
3574 | Lower Missouri River Jefferson City L-142 | 11 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-04-14 19:00 | New Project Risk | New Risk Added | 2023-04-14 19:00
3574 | Lower Missouri River Jefferson City L-142 | 12 | 1 | 3 | 2 | 2 | 4051 |  |  |  | 2023-04-14 19:01 | New Project Risk | New Risk Added | 2023-04-14 19:01
3574 | Lower Missouri River Jefferson City L-142 | 27 | 1 | 2 | 4 | 2 | 4051 |  |  |  | 2023-05-01 19:48 | New Project Risk | New Risk Added | 2023-05-01 19:48
3574 | Lower Missouri River Jefferson City L-142 | 16 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-04-28 23:28 | New Project Risk | New Risk Added | 2023-04-28 23:28
3574 | Lower Missouri River Jefferson City L-142 | 18 | 1 | 1 | 2 | 2 | 4051 |  |  |  | 2023-05-01 18:52 | New Project Risk | New Risk Added | 2023-05-01 18:52
3574 | Lower Missouri River Jefferson City L-142 | 19 | 1 | 3 | 2 | 0 | 4051 |  |  |  | 2023-05-01 18:58 | New Project Risk | New Risk Added | 2023-05-01 18:58
3574 | Lower Missouri River Jefferson City L-142 | 20 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-05-01 19:05 | New Project Risk | New Risk Added | 2023-05-01 19:05
3574 | Lower Missouri River Jefferson City L-142 | 21 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-05-01 19:14 | New Project Risk | New Risk Added | 2023-05-01 19:14 | PLE-21-1
3574 | Lower Missouri River Jefferson City L-142 | 22 | 1 | 2 | 2 | 0 | 4051 |  |  |  | 2023-05-01 19:19 | New Project Risk | New Risk Added | 2023-05-01 19:19
3574 | Lower Missouri River Jefferson City L-142 | 23 | 1 | 2 | 2 | 2 | 4051 |  |  |  | 2023-05-01 19:24 | New Project Risk | New Risk Added | 2023-05-01 19:24
3574 | Lower Missouri River Jefferson City L-142 | 24 | 1 | 3 | 2 | 0 | 4051 |  |  |  | 2023-05-01 19:30 | New Project Risk | New Risk Added | 2023-05-01 19:30
3574 | Lower Missouri River Jefferson City L-142 | 24 | 2 | 3 | 2 | 0 | 4051 |  |  |  | 2023-05-01 19:37 | Corrected Error |  | 2023-05-01 19:37
3574 | Lower Missouri River Jefferson City L-142 | 25 | 1 | 2 | 2 | 3 | 4051 |  |  |  | 2023-05-01 19:42 | New Project Risk | New Risk Added | 2023-05-01 19:42
3574 | Lower Missouri River Jefferson City L-142 | 26 | 1 | 3 | 4 | 4 | 4051 |  |  |  | 2023-05-01 19:45 | New Project Risk | New Risk Added | 2023-05-01 19:45
3631 | RumaylanDetention Facility | 2 | 1 | 4 | 4 | 0 | 8912 |  |  |  | 2023-02-26 22:55 | New Project Risk | New Risk Added | 2023-02-26 22:55 | CNT-2-1
3653 | 2024 Dredging Project, Military Ocean Terminal Concord (MOTCO), CA. | 1 | 1 | 2 | 1 | 1 | 4571 |  |  |  | 2023-03-14 20:11 | New Project Risk | New Risk Added | 2023-03-14 20:11
3654 | Keystone Dam – Wedge (495646) | 1 | 1 | 0 | 4 | 4 | 28 |  |  |  | 2023-03-13 19:51 | New Project Risk | New Risk Added | 2023-03-13 19:51 | PLP-1-1
3654 | Keystone Dam – Wedge (495646) | 2 | 1 | 2 | 4 | 2 | 28 |  |  |  | 2023-03-13 19:58 | New Project Risk | New Risk Added | 2023-03-13 19:58 | PLE-2-1
3654 | Keystone Dam – Wedge (495646) | 3 | 1 | 0 | 0 | 4 | 28 |  |  |  | 2023-03-13 20:07 | New Project Risk | New Risk Added | 2023-03-13 20:07 | PRM-3-1
3654 | Keystone Dam – Wedge (495646) | 4 | 1 | 0 | 4 | 2 | 28 |  |  |  | 2023-03-13 20:12 | New Project Risk | New Risk Added | 2023-03-13 20:12 | PRM-4-1
3654 | Keystone Dam – Wedge (495646) | 5 | 1 | 0 | 1 | 1 | 28 |  |  |  | 2023-03-13 20:18 | New Project Risk | New Risk Added | 2023-03-13 20:18 | PLP-5-1
3654 | Keystone Dam – Wedge (495646) | 6 | 1 | 0 | 4 | 2 | 28 |  |  |  | 2023-03-13 20:27 | New Project Risk | New Risk Added | 2023-03-13 20:27 | EHH-6-1
3654 | Keystone Dam – Wedge (495646) | 5 | 2 | 0 | 1 | 1 | 28 |  |  |  | 2023-03-13 20:31 | Corrected Error |  | 2023-03-13 20:31
3654 | Keystone Dam – Wedge (495646) | 4 | 2 | 0 | 4 | 2 | -99 |  |  |  | 2023-03-13 20:31 | Corrected Error |  | 2023-03-13 20:31
3677 | Capstone | 14 | 1 | 0 | 2 | 2 | 5627 | 5627 | Angela | Lane | 2023-03-14 14:23 | New Project Risk | New Risk Added | 2023-03-14 14:23 | PLE-28-1
3677 | Capstone | 20 | 1 | 0 | 2 | 0 | 5210 | 5210 | Thomas | Hodson | 2023-03-14 14:18 | New Project Risk | New Risk Added | 2023-03-14 14:18 | PLE-28-1
3677 | Capstone | 9 | 1 | 4 | 4 | 4 | 8952 | 8952 | Justine | Woodward | 2023-03-14 14:21 | New Project Risk | New Risk Added | 2023-03-14 14:21 | PLE-28-1
3677 | Capstone | 16 | 1 | 2 | 4 | 4 | 7308 |  |  |  | 2023-03-14 14:26 | New Project Risk | New Risk Added | 2023-03-14 14:26 | PLE-28-1
3677 | Capstone | 15 | 1 | 4 | 4 | 0 | 7650 |  |  |  | 2023-03-14 14:24 | New Project Risk | New Risk Added | 2023-03-14 14:24 | PLE-28-1
3677 | Capstone | 29 | 1 | 3 | 4 | 4 | 6587 |  |  |  | 2023-06-06 13:07 | New Project Risk | New Risk Added | 2023-06-06 13:07
3677 | Capstone | 40 | 2 | 3 | 2 | 4 | 6587 |  |  |  | 2023-07-18 16:52 | Corrected Error |  | 2023-07-18 16:52
3677 | Capstone | 39 | 1 | 0 | 2 | 2 | 6587 |  |  |  | 2023-07-18 16:36 | New Project Risk | New Risk Added | 2023-07-18 16:36
3677 | Capstone | 39 | 2 | 0 | 2 | 2 | 6587 |  |  |  | 2023-07-18 16:44 | New Information |  | 2023-07-18 16:44
3677 | Capstone | 40 | 1 | 3 | 2 | 4 | 6587 |  |  |  | 2023-07-18 16:49 | New Project Risk | New Risk Added | 2023-07-18 16:49
3677 | Capstone | 35 | 1 | 3 | 4 | 4 | 3573 |  |  |  | 2023-06-06 13:05 | New Project Risk | New Risk Added | 2023-06-06 13:05 | EHH-35-1, EHH-35-2
3677 | Capstone | 35 | 2 | 3 | 4 | 4 | 3573 |  |  |  | 2023-06-06 13:10 | Corrected Error |  | 2023-06-06 13:10
3677 | Capstone | 35 | 3 | 3 | 4 | 4 | 3573 |  |  |  | 2023-06-06 13:10 | Risk Response implemented |  | 2023-06-06 13:10
3677 | Capstone | 26 | 2 | 2 | 2 | 4 | 7949 |  |  |  | 2023-06-06 13:04 | Conditions Changed | Recommend HTRW avoidance based on Phase I results | 2023-06-06 13:04
3677 | Capstone | 26 | 1 | 2 | 2 | 4 | 7949 |  |  |  | 2023-06-06 13:00 | New Project Risk | New Risk Added | 2023-06-06 13:00 | PLE-26-1
3677 | Capstone | 13 | 1 | 4 | 3 | 4 | 8934 |  |  |  | 2023-03-14 14:27 | New Project Risk | New Risk Added | 2023-03-14 14:27 | PLE-28-1
3677 | Capstone | 25 | 1 | 1 | 2 | 2 | 8007 |  |  |  | 2023-03-14 14:28 | New Project Risk | New Risk Added | 2023-03-14 14:28 | PLE-28-1
3677 | Capstone | 38 | 1 | 0 | 4 | 0 | 4826 |  |  |  | 2023-06-06 13:10 | New Project Risk | New Risk Added | 2023-06-06 13:10
3677 | Capstone | 33 | 1 | 2 | 2 | 2 | 8070 |  |  |  | 2023-06-06 13:15 | New Project Risk | New Risk Added | 2023-06-06 13:15
3677 | Capstone | 30 | 1 | 3 | 4 | 4 | 6807 |  |  |  | 2023-06-06 13:07 | New Project Risk | New Risk Added | 2023-06-06 13:07
3677 | Capstone | 19 | 1 | 3 | 4 | 4 | 7707 |  |  |  | 2023-03-14 14:30 | New Project Risk | New Risk Added | 2023-03-14 14:30 | EHH-19-1, PLE-28-1
3677 | Capstone | 6 | 1 | 2 | 2 | 4 | 7329 |  |  |  | 2023-03-14 14:35 | New Project Risk | New Risk Added | 2023-03-14 14:35 | PLE-28-1
3677 | Capstone | 27 | 1 | 2 | 4 | 4 | 9132 |  |  |  | 2023-06-06 13:15 | New Project Risk | New Risk Added | 2023-06-06 13:15
3677 | Capstone | 18 | 1 | 3 | 4 | 4 | 7893 |  |  |  | 2023-03-14 14:30 | New Project Risk | New Risk Added | 2023-03-14 14:30 | PLE-28-1
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 5 | 1 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-17 18:40 | New Project Risk | New Risk Added | 2023-03-17 18:40
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 7 | 2 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-27 21:37 | New Information | Risk is a work in progress, and changes will be made as feedback is received | 2023-03-27 21:37
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 8 | 2 | 4 | 1 | 1 | 8413 |  |  |  | 2023-03-27 22:39 | Corrected Error | Correcting information from prior error's made, document is subject to change to incorporate additional team feedback, | 2023-03-27 22:39
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 9 | 1 | 2 | 1 | 1 | 8413 |  |  |  | 2023-04-03 17:15 | New Project Risk | New Risk Added | 2023-04-03 17:15
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 2 | 2 | 3 | 4 | 1 | 8413 |  |  |  | 2023-03-22 22:24 | New Information | Received additional feedback. | 2023-03-22 22:24
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 7 | 3 | 2 | 1 | 1 | 8413 |  |  |  | 2023-04-03 16:27 | Corrected Error | Risk categorized under the construction phase by accident and registrar does not allow to edit this; will enter new risk separately to correct this. | 2023-04-03 16:27
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 5 | 2 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-23 22:48 | New Information | Risk is a work in progress and will be updated as needed. | 2023-03-23 22:48
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 2 | 1 | 2 | 4 | 1 | 8413 |  |  |  | 2023-03-17 17:57 | New Project Risk | New Risk Added | 2023-03-17 17:57
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 4 | 1 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-17 18:26 | New Project Risk | New Risk Added | 2023-03-17 18:26
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 6 | 1 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-17 18:42 | New Project Risk | New Risk Added | 2023-03-17 18:42
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 7 | 1 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-17 18:51 | New Project Risk | New Risk Added | 2023-03-17 18:51
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 8 | 1 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-22 15:59 | New Project Risk | New Risk Added | 2023-03-22 15:59
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 4 | 2 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-23 22:26 | New Information | Incorporating feedback from PDT members, a work in progress and subject to further changes, | 2023-03-23 22:26
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 5 | 3 | 3 | 1 | 1 | 8413 |  |  |  | 2023-03-24 22:16 | New Information | Risk is a work in progress and will be updated as needed when incorporating feedback. | 2023-03-24 22:16
3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 6 | 2 | 2 | 1 | 1 | 8413 |  |  |  | 2023-03-24 22:49 | New Information | Incorporating additional feedback, risk is a work in progress. | 2023-03-24 22:49
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 7 | 3 | 2 | 2 | 0 | 793 | 793 | Josh | Garcia | 2023-06-13 17:56 | Risk Response implemented | Updated information and added estimated cost for mitigation during PED phase. | 2023-06-13 17:56
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 4 | 1 | 0 | 4 | 1 | 337 |  |  |  | 2023-06-13 13:51 | New Project Risk | New Risk Added | 2023-06-13 13:51
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 5 | 1 | 2 | 0 | 0 | 337 |  |  |  | 2023-06-13 14:01 | New Project Risk | New Risk Added | 2023-06-13 14:01
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 6 | 1 | 2 | 0 | 0 | 337 |  |  |  | 2023-06-13 14:11 | New Project Risk | New Risk Added | 2023-06-13 14:11
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 6 | 2 | 2 | 0 | 0 | 337 |  |  |  | 2023-06-13 14:14 | Corrected Error |  | 2023-06-13 14:14
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 4 | 2 | 0 | 4 | 1 | 337 |  |  |  | 2023-06-13 17:08 | Corrected Error |  | 2023-06-13 17:08
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 7 | 2 | 2 | 0 | 0 | 337 |  |  |  | 2023-06-13 17:09 | New Information | Still figuring out how to use the eRisk Register tool | 2023-06-13 17:09
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 10 | 2 | 2 | 1 | 1 | 337 |  |  |  | 2023-06-13 17:11 | New Information | Learning how to use the risk register tool. | 2023-06-13 17:11
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 11 | 2 | 2 | 0 | 1 | 337 |  |  |  | 2023-06-13 17:14 | New Information | Learning how to use the risk register tool. | 2023-06-13 17:14
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 7 | 1 | 2 | 0 | 0 | 337 |  |  |  | 2023-06-13 14:33 | New Project Risk | New Risk Added | 2023-06-13 14:33
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 8 | 1 | 2 | 0 | 0 | 337 |  |  |  | 2023-06-13 14:40 | New Project Risk | New Risk Added | 2023-06-13 14:40
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 9 | 1 | 2 | 0 | 0 | 337 |  |  |  | 2023-06-13 15:02 | New Project Risk | New Risk Added | 2023-06-13 15:02
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 1 | 1 | 0 | 1 | 1 | 337 |  |  |  | 2023-06-12 19:39 | New Project Risk | New Risk Added | 2023-06-12 19:39
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 2 | 1 | 3 | 0 | 0 | 337 |  |  |  | 2023-06-12 19:46 | New Project Risk | New Risk Added | 2023-06-12 19:46
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 3 | 1 | 2 | 0 | 1 | 337 |  |  |  | 2023-06-12 19:57 | New Project Risk | New Risk Added | 2023-06-12 19:57 | PLP-3-1
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 10 | 1 | 2 | 1 | 1 | 337 |  |  |  | 2023-06-13 15:13 | New Project Risk | New Risk Added | 2023-06-13 15:13
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 11 | 1 | 2 | 0 | 1 | 337 |  |  |  | 2023-06-13 15:17 | New Project Risk | New Risk Added | 2023-06-13 15:17
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 12 | 1 | 2 | 1 | 1 | 337 |  |  |  | 2023-06-13 15:19 | New Project Risk | New Risk Added | 2023-06-13 15:19
3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 8 | 2 | 2 | 0 | 0 | 337 |  |  |  | 2023-06-13 17:10 | New Information | Learning how to use the Risk Register tool | 2023-06-13 17:10
3811 | Hyder Harbor Navigational Improvements | 4 | 1 | 3 | 0 | 0 | 7996 |  |  |  | 2023-04-27 21:36 | New Project Risk | New Risk Added | 2023-04-27 21:36
3811 | Hyder Harbor Navigational Improvements | 1 | 1 | 0 | 0 | 0 | 7996 |  |  |  | 2023-04-27 21:25 | New Project Risk | New Risk Added | 2023-04-27 21:25
3811 | Hyder Harbor Navigational Improvements | 2 | 1 | 0 | 0 | 0 | 7996 |  |  |  | 2023-04-27 21:29 | New Project Risk | New Risk Added | 2023-04-27 21:29
3811 | Hyder Harbor Navigational Improvements | 3 | 1 | 2 | 0 | 0 | 7996 |  |  |  | 2023-04-27 21:33 | New Project Risk | New Risk Added | 2023-04-27 21:33
3811 | Hyder Harbor Navigational Improvements | 5 | 1 | 0 | 0 | 0 | 7996 |  |  |  | 2023-04-27 21:39 | New Project Risk | New Risk Added | 2023-04-27 21:39
3811 | Hyder Harbor Navigational Improvements | 6 | 1 | 0 | 0 | 0 | 7996 |  |  |  | 2023-04-27 21:47 | New Project Risk | New Risk Added | 2023-04-27 21:47
3811 | Hyder Harbor Navigational Improvements | 7 | 1 | 0 | 0 | 0 | 7996 |  |  |  | 2023-04-27 21:54 | New Project Risk | New Risk Added | 2023-04-27 21:54
3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 2 | 1 | 3 | 0 | 0 | 3233 |  |  |  | 2023-05-25 23:53 | New Project Risk | New Risk Added | 2023-05-25 23:53
3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 2 | 2 | 4 | 0 | 0 | 3233 |  |  |  | 2023-05-25 23:58 | Corrected Error | If seeking policy exemption, would likely need to develop exemption package by the TSP. | 2023-05-25 23:58
3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 4 | 1 | 2 | 0 | 0 | 5416 |  |  |  | 2023-06-13 17:46 | New Project Risk | New Risk Added | 2023-06-13 17:46
3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 5 | 1 | 2 | 2 | 3 | 5416 |  |  |  | 2023-06-13 17:59 | New Project Risk | New Risk Added | 2023-06-13 17:59
3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 8 | 1 | 2 | 3 | 4 | 5416 |  |  |  | 2023-06-13 19:48 | New Project Risk | New Risk Added | 2023-06-13 19:48
3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 7 | 2 | 4 | 4 | 4 | 5416 |  |  |  | 2023-06-13 19:48 | Corrected Error | changed schedule impact from 18 days to 550 day (rough equivalent of 18 months). | 2023-06-13 19:48
3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 6 | 1 | 3 | 4 | 4 | 5416 |  |  |  | 2023-06-13 19:06 | New Project Risk | New Risk Added | 2023-06-13 19:06
3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 7 | 1 | 4 | 4 | 2 | 5416 |  |  |  | 2023-06-13 19:26 | New Project Risk | New Risk Added | 2023-06-13 19:26
3911 | Andalusia Island Complex | 4 | 1 | 2 | 0 | 0 | 9281 | 9281 | William | Mahoney | 2023-06-29 20:38 | New Project Risk | New Risk Added | 2023-06-29 20:38
3911 | Andalusia Island Complex | 3 | 1 | 0 | 0 | 4 | 6867 |  |  |  | 2023-06-21 20:36 | New Project Risk | New Risk Added | 2023-06-21 20:36
3911 | Andalusia Island Complex | 1 | 1 | 0 | 0 | 0 | 6867 |  |  |  | 2023-06-05 19:51 | New Project Risk | New Risk Added | 2023-06-05 19:51
3544 | Test A Project | 8 | 1 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-02-13 17:30 | New Project Risk | New Risk Added | 2023-02-13 17:30
3544 | Test A Project | 1 | 4 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-03-03 17:46 | Corrected Error | New Owner/Discipline | 2023-03-03 17:46
3544 | Test A Project | 10 | 1 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-03-06 16:17 | New Project Risk | New Risk Added | 2023-03-06 16:17
3544 | Test A Project | 10 | 3 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-03-06 16:20 | Corrected Error | Changed Discipline | 2023-03-06 16:20
3544 | Test A Project | 10 | 4 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-03-06 16:21 | Corrected Error | Changed Owner | 2023-03-06 16:21
3544 | Test A Project | 1 | 3 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-03-03 17:42 | Corrected Error | New Owner | 2023-03-03 17:42
3544 | Test A Project | 10 | 2 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-03-06 16:18 | Corrected Error |  | 2023-03-06 16:18
3544 | Test A Project | 10 | 5 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-03-07 14:59 | Corrected Error | Changed Owner | 2023-03-07 14:59
3544 | Test A Project | 4 | 1 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-01-24 13:48 | New Project Risk | New Risk Added | 2023-01-24 13:48
3544 | Test A Project | 4 | 2 | 2 | 2 | 2 | 8775 | 8775 | Idris | Dobbs | 2023-01-24 13:49 | Corrected Error | Edit | 2023-01-24 13:49
3544 | Test A Project | 18 | 1 | 2 | 4 | 4 | 9033 | 9033 | Erin | Rooks | 2023-05-31 21:52 | New Project Risk | New Risk Added | 2023-05-31 21:52
3544 | Test A Project | 1 | 1 | 2 | 2 | 2 | 138 |  |  |  | 2023-01-19 22:06 | New Project Risk | New Risk Added | 2023-01-19 22:06
3544 | Test A Project | 5 | 1 | 2 | 4 | 4 | 138 |  |  |  | 2023-01-24 13:56 | New Project Risk | New Risk Added | 2023-01-24 13:56
3544 | Test A Project | 7 | 1 | 2 | 1 | 4 | 138 |  |  |  | 2023-01-31 19:42 | New Project Risk | New Risk Added | 2023-01-31 19:42 | OPS-7-1
3544 | Test A Project | 14 | 1 | 3 | 2 | 0 | 138 |  |  |  | 2023-04-17 13:44 | New Project Risk | New Risk Added | 2023-04-17 13:44
3544 | Test A Project | 15 | 1 | 3 | 4 | 4 | 138 |  |  |  | 2023-04-17 14:38 | New Project Risk | New Risk Added | 2023-04-17 14:38
3544 | Test A Project | 12 | 2 | 2 | 1 | 2 | 138 |  |  |  | 2023-04-17 14:39 | Conditions Changed | implement a risk measure | 2023-04-17 14:39
3544 | Test A Project | 6 | 1 | 2 | 2 | 4 | 138 |  |  |  | 2023-01-24 14:11 | New Project Risk | New Risk Added | 2023-01-24 14:11
3544 | Test A Project | 1 | 5 | 2 | 2 | 2 | 138 |  |  |  | 2023-03-30 15:46 | Conditions Changed |  | 2023-03-30 15:46
3544 | Test A Project | 16 | 1 | 2 | 2 | 0 | 138 |  |  |  | 2023-05-19 14:28 | New Project Risk | New Risk Added | 2023-05-19 14:28
3544 | Test A Project | 17 | 1 | 3 | 2 | 0 | 138 |  |  |  | 2023-05-25 13:27 | New Project Risk | New Risk Added | 2023-05-25 13:27 | EPE-17-1
3544 | Test A Project | 8 | 2 | 2 | 2 | 2 | 138 |  |  |  | 2023-05-25 13:33 | Risk Response implemented |  | 2023-05-25 13:33
3544 | Test A Project | 5 | 2 | 2 | 2 | 2 | 138 |  |  |  | 2023-03-23 19:36 | Risk Response implemented | avoided risk | 2023-03-23 19:36 | PLC-5-2
3544 | Test A Project | 13 | 1 | 2 | 2 | 2 | 138 |  |  |  | 2023-03-30 15:41 | New Project Risk | New Risk Added | 2023-03-30 15:41
3544 | Test A Project | 19 | 1 | 4 | 2 | 0 | 138 |  |  |  | 2023-06-26 16:55 | New Project Risk | New Risk Added | 2023-06-26 16:55
3544 | Test A Project | 9 | 1 | 2 | 2 | 2 | 138 |  |  |  | 2023-02-27 15:41 | New Project Risk | New Risk Added | 2023-02-27 15:41
3544 | Test A Project | 1 | 2 | 2 | 2 | 2 | 138 |  |  |  | 2023-02-02 15:53 | New Information | Add your discussion here | 2023-02-02 15:53
3544 | Test A Project | 11 | 1 | 3 | 2 | 0 | 138 |  |  |  | 2023-03-20 14:26 | New Project Risk | New Risk Added | 2023-03-20 14:26
3544 | Test A Project | 12 | 1 | 2 | 2 | 3 | 138 |  |  |  | 2023-03-23 19:34 | New Project Risk | New Risk Added | 2023-03-23 19:34
3544 | Test A Project | 3 | 3 | 2 | 2 | 2 | 8653 |  |  |  | 2023-01-19 22:25 | Corrected Error | 22 | 2023-01-19 22:25
3544 | Test A Project | 3 | 2 | 0 | 2 | 0 | 8653 |  |  |  | 2023-01-19 22:24 | Corrected Error | 111 | 2023-01-19 22:24
3544 | Test A Project | 2 | 1 | 2 | 2 | 2 | 8653 |  |  |  | 2023-01-19 22:19 | New Project Risk | New Risk Added | 2023-01-19 22:19
3544 | Test A Project | 3 | 1 | 1 | 2 | 0 | 8653 |  |  |  | 2023-01-19 22:24 | New Project Risk | New Risk Added | 2023-01-19 22:24
3593 | Lower Mississippi River Comprehensive Management Study | 1 | 1 | 3 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 19:49 | New Project Risk | New Risk Added | 2023-02-24 19:49
3593 | Lower Mississippi River Comprehensive Management Study | 2 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:22 | New Project Risk | New Risk Added | 2023-02-24 20:22
3593 | Lower Mississippi River Comprehensive Management Study | 2 | 2 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:23 | Corrected Error |  | 2023-02-24 20:23
3593 | Lower Mississippi River Comprehensive Management Study | 3 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:28 | New Project Risk | New Risk Added | 2023-02-24 20:28
3593 | Lower Mississippi River Comprehensive Management Study | 5 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:39 | New Project Risk | New Risk Added | 2023-02-24 20:39
3593 | Lower Mississippi River Comprehensive Management Study | 6 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:43 | New Project Risk | New Risk Added | 2023-02-24 20:43
3593 | Lower Mississippi River Comprehensive Management Study | 7 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:46 | New Project Risk | New Risk Added | 2023-02-24 20:46
3593 | Lower Mississippi River Comprehensive Management Study | 8 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:49 | New Project Risk | New Risk Added | 2023-02-24 20:49
3593 | Lower Mississippi River Comprehensive Management Study | 9 | 1 | 3 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:55 | New Project Risk | New Risk Added | 2023-02-24 20:55
3593 | Lower Mississippi River Comprehensive Management Study | 10 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:06 | New Project Risk | New Risk Added | 2023-02-24 21:06
3593 | Lower Mississippi River Comprehensive Management Study | 11 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:10 | New Project Risk | New Risk Added | 2023-02-24 21:10
3593 | Lower Mississippi River Comprehensive Management Study | 13 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:26 | New Project Risk | New Risk Added | 2023-02-24 21:26
3593 | Lower Mississippi River Comprehensive Management Study | 14 | 1 | 4 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:31 | New Project Risk | New Risk Added | 2023-02-24 21:31
3593 | Lower Mississippi River Comprehensive Management Study | 15 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:33 | New Project Risk | New Risk Added | 2023-02-24 21:33
3593 | Lower Mississippi River Comprehensive Management Study | 16 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:38 | New Project Risk | New Risk Added | 2023-02-24 21:38
3593 | Lower Mississippi River Comprehensive Management Study | 17 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:40 | New Project Risk | New Risk Added | 2023-02-24 21:40
3593 | Lower Mississippi River Comprehensive Management Study | 18 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:47 | New Project Risk | New Risk Added | 2023-02-24 21:47
3593 | Lower Mississippi River Comprehensive Management Study | 19 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:50 | New Project Risk | New Risk Added | 2023-02-24 21:50
3593 | Lower Mississippi River Comprehensive Management Study | 20 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:52 | New Project Risk | New Risk Added | 2023-02-24 21:52
3593 | Lower Mississippi River Comprehensive Management Study | 21 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:55 | New Project Risk | New Risk Added | 2023-02-24 21:55
3593 | Lower Mississippi River Comprehensive Management Study | 23 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-04-17 19:38 | New Project Risk | New Risk Added | 2023-04-17 19:38
3593 | Lower Mississippi River Comprehensive Management Study | 1 | 2 | 3 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 19:50 | Corrected Error |  | 2023-02-24 19:50
3593 | Lower Mississippi River Comprehensive Management Study | 12 | 2 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:12 | Corrected Error |  | 2023-02-24 21:12
3593 | Lower Mississippi River Comprehensive Management Study | 15 | 2 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:35 | Corrected Error |  | 2023-02-24 21:35
3593 | Lower Mississippi River Comprehensive Management Study | 1 | 3 | 3 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-05-23 20:48 | New Information |  | 2023-05-23 20:48
3593 | Lower Mississippi River Comprehensive Management Study | 4 | 1 | 2 | 1 | 2 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 20:31 | New Project Risk | New Risk Added | 2023-02-24 20:31
3593 | Lower Mississippi River Comprehensive Management Study | 1 | 4 | 3 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-05-23 21:10 | New Information |  | 2023-05-23 21:10
3593 | Lower Mississippi River Comprehensive Management Study | 12 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-02-24 21:11 | New Project Risk | New Risk Added | 2023-02-24 21:11
3593 | Lower Mississippi River Comprehensive Management Study | 22 | 1 | 2 | 1 | 1 | 6361 | 6361 | Jim | Hutchison | 2023-04-17 19:37 | New Project Risk | New Risk Added | 2023-04-17 19:37
3652 | DE Inland Bay/Bay Coast | 4 | 1 | 2 | 1 | 4 | 863 | 863 | Heather | Jensen | 2023-04-28 13:50 | New Project Risk | New Risk Added | 2023-04-28 13:50
3652 | DE Inland Bay/Bay Coast | 5 | 1 | 1 | 2 | 4 | 863 | 863 | Heather | Jensen | 2023-04-28 13:55 | New Project Risk | New Risk Added | 2023-04-28 13:55
3652 | DE Inland Bay/Bay Coast | 6 | 1 | 1 | 4 | 4 | 863 | 863 | Heather | Jensen | 2023-04-28 14:10 | New Project Risk | New Risk Added | 2023-04-28 14:10
3652 | DE Inland Bay/Bay Coast | 7 | 1 | 2 | 3 | 4 | 863 | 863 | Heather | Jensen | 2023-04-28 14:20 | New Project Risk | New Risk Added | 2023-04-28 14:20
3652 | DE Inland Bay/Bay Coast | 9 | 1 | 2 | 1 | 1 | 863 | 863 | Heather | Jensen | 2023-04-28 14:34 | New Project Risk | New Risk Added | 2023-04-28 14:34
3652 | DE Inland Bay/Bay Coast | 10 | 1 | 2 | 1 | 1 | 863 | 863 | Heather | Jensen | 2023-04-28 14:39 | New Project Risk | New Risk Added | 2023-04-28 14:39
3652 | DE Inland Bay/Bay Coast | 8 | 1 | 2 | 1 | 1 | 863 | 863 | Heather | Jensen | 2023-04-28 14:30 | New Project Risk | New Risk Added | 2023-04-28 14:30
3652 | DE Inland Bay/Bay Coast | 20 | 1 | 0 | 0 | 0 | 5627 | 5627 | Angela | Lane | 2023-05-02 15:17 | New Project Risk | New Risk Added | 2023-05-02 15:17
3652 | DE Inland Bay/Bay Coast | 20 | 2 | 0 | 2 | 2 | 5627 | 5627 | Angela | Lane | 2023-05-02 15:23 | Corrected Error |  | 2023-05-02 15:23
3652 | DE Inland Bay/Bay Coast | 21 | 1 | 0 | 2 | 4 | 5627 | 5627 | Angela | Lane | 2023-05-02 15:39 | New Project Risk | New Risk Added | 2023-05-02 15:39
3652 | DE Inland Bay/Bay Coast | 1 | 1 | 3 | 4 | 3 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-04-25 12:38 | New Project Risk | New Risk Added | 2023-04-25 12:38
3652 | DE Inland Bay/Bay Coast | 2 | 1 | 2 | 0 | 1 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-04-25 12:50 | New Project Risk | New Risk Added | 2023-04-25 12:50
3652 | DE Inland Bay/Bay Coast | 3 | 1 | 0 | 1 | 1 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-04-25 12:58 | New Project Risk | New Risk Added | 2023-04-25 12:58 | PLE-3-1
3652 | DE Inland Bay/Bay Coast | 11 | 1 | 2 | 0 | 0 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 12:11 | New Project Risk | New Risk Added | 2023-05-01 12:11
3652 | DE Inland Bay/Bay Coast | 12 | 1 | 2 | 4 | 3 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 12:23 | New Project Risk | New Risk Added | 2023-05-01 12:23
3652 | DE Inland Bay/Bay Coast | 13 | 1 | 2 | 4 | 3 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 12:29 | New Project Risk | New Risk Added | 2023-05-01 12:29
3652 | DE Inland Bay/Bay Coast | 11 | 2 | 2 | 0 | 0 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 12:29 | Corrected Error |  | 2023-05-01 12:29
3652 | DE Inland Bay/Bay Coast | 14 | 1 | 2 | 0 | 0 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 12:34 | New Project Risk | New Risk Added | 2023-05-01 12:34
3652 | DE Inland Bay/Bay Coast | 15 | 1 | 2 | 2 | 3 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 17:22 | New Project Risk | New Risk Added | 2023-05-01 17:22
3652 | DE Inland Bay/Bay Coast | 19 | 1 | 2 | 0 | 0 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 20:31 | New Project Risk | New Risk Added | 2023-05-01 20:31
3652 | DE Inland Bay/Bay Coast | 3 | 2 | 2 | 2 | 2 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 14:43 | Conditions Changed |  | 2023-05-12 14:43
3652 | DE Inland Bay/Bay Coast | 4 | 2 | 2 | 4 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 14:48 | Conditions Changed |  | 2023-05-12 14:48
3652 | DE Inland Bay/Bay Coast | 5 | 2 | 2 | 3 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 15:00 | Conditions Changed |  | 2023-05-12 15:00
3652 | DE Inland Bay/Bay Coast | 11 | 3 | 2 | 0 | 0 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 15:19 | Conditions Changed |  | 2023-05-12 15:19
3652 | DE Inland Bay/Bay Coast | 19 | 2 | 2 | 2 | 0 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 15:23 | Conditions Changed |  | 2023-05-12 15:23
3652 | DE Inland Bay/Bay Coast | 6 | 3 | 3 | 4 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-24 17:49 | Conditions Changed |  | 2023-05-24 17:49
3652 | DE Inland Bay/Bay Coast | 17 | 3 | 2 | 4 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 18:11 | Corrected Error |  | 2023-05-01 18:11
3652 | DE Inland Bay/Bay Coast | 8 | 2 | 2 | 4 | 3 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 15:05 | Conditions Changed |  | 2023-05-12 15:05
3652 | DE Inland Bay/Bay Coast | 2 | 2 | 2 | 0 | 1 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-24 17:16 | New Information |  | 2023-05-24 17:16
3652 | DE Inland Bay/Bay Coast | 5 | 3 | 2 | 3 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-24 17:18 | New Information |  | 2023-05-24 17:18
3652 | DE Inland Bay/Bay Coast | 21 | 2 | 3 | 3 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-24 17:21 | Conditions Changed |  | 2023-05-24 17:21
3652 | DE Inland Bay/Bay Coast | 20 | 3 | 0 | 2 | 2 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-24 17:31 | Conditions Changed |  | 2023-05-24 17:31
3652 | DE Inland Bay/Bay Coast | 19 | 3 | 2 | 2 | 2 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-24 17:33 | Conditions Changed |  | 2023-05-24 17:33
3652 | DE Inland Bay/Bay Coast | 11 | 4 | 2 | 0 | 0 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-24 17:51 | Conditions Changed |  | 2023-05-24 17:51
3652 | DE Inland Bay/Bay Coast | 22 | 1 | 2 | 2 | 2 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-06-16 16:22 | New Project Risk | New Risk Added | 2023-06-16 16:22
3652 | DE Inland Bay/Bay Coast | 23 | 1 | 2 | 4 | 3 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-06-16 16:25 | New Project Risk | New Risk Added | 2023-06-16 16:25
3652 | DE Inland Bay/Bay Coast | 17 | 1 | 2 | 4 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 18:08 | New Project Risk | New Risk Added | 2023-05-01 18:08
3652 | DE Inland Bay/Bay Coast | 17 | 2 | 2 | 4 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-01 18:10 | Corrected Error |  | 2023-05-01 18:10
3652 | DE Inland Bay/Bay Coast | 6 | 2 | 3 | 4 | 4 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 15:03 | Conditions Changed |  | 2023-05-12 15:03
3652 | DE Inland Bay/Bay Coast | 15 | 2 | 2 | 2 | 2 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 15:07 | Conditions Changed |  | 2023-05-12 15:07
3652 | DE Inland Bay/Bay Coast | 9 | 2 | 2 | 2 | 2 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-12 15:18 | Conditions Changed |  | 2023-05-12 15:18
3652 | DE Inland Bay/Bay Coast | 14 | 2 | 2 | 2 | 2 | 8780 | 8780 | Ginger | Niemann-Harper | 2023-05-24 17:53 | Conditions Changed |  | 2023-05-24 17:53
3771 | Atka Navigation Improvements | 1 | 1 | 2 | 1 | 0 | 6223 |  |  |  | 2023-04-11 23:45 | New Project Risk | New Risk Added | 2023-04-11 23:45
3772 | Bluestone DSA | 2 | 1 | 2 | 1 | 1 | 8955 | 8955 | Alicia | Barrette | 2023-04-13 12:19 | New Project Risk | New Risk Added | 2023-04-13 12:19
3772 | Bluestone DSA | 3 | 1 | 2 | 0 | 4 | 8955 | 8955 | Alicia | Barrette | 2023-04-13 12:22 | New Project Risk | New Risk Added | 2023-04-13 12:22
3772 | Bluestone DSA | 1 | 1 | 2 | 1 | 1 | 8955 | 8955 | Alicia | Barrette | 2023-04-12 18:58 | New Project Risk | New Risk Added | 2023-04-12 18:58
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 11 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-13 19:42 | New Project Risk | New Risk Added | 2023-06-13 19:42 | PRM-11-1
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 13 | 2 | 2 | 0 | 0 | 584 | 584 | John | Logan | 2023-06-26 13:48 | Risk Response implemented | 3x3x3 waiver request for study budget and schedule approved by ASA (CW) on 6 January 2023 and 16 June 2023. | 2023-06-26 13:48
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 17 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-26 14:08 | New Project Risk | New Risk Added | 2023-06-26 14:08
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 18 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-26 14:49 | New Project Risk | New Risk Added | 2023-06-26 14:49
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 19 | 1 | 3 | 2 | 3 | 584 | 584 | John | Logan | 2023-06-26 15:03 | New Project Risk | New Risk Added | 2023-06-26 15:03
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 20 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-28 19:49 | New Project Risk | New Risk Added | 2023-06-28 19:49
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 20 | 2 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-28 19:50 | Corrected Error |  | 2023-06-28 19:50
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 9 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-12 16:47 | New Project Risk | New Risk Added | 2023-06-12 16:47
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 15 | 2 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-13 20:28 | Corrected Error |  | 2023-06-13 20:28
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 5 | 4 | 3 | 4 | 3 | 584 | 584 | John | Logan | 2023-07-13 17:50 | New Information |  | 2023-07-13 17:50
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 20 | 3 | 3 | 4 | 2 | 584 | 584 | John | Logan | 2023-07-13 18:22 | New Information | Kaltenbach added information. | 2023-07-13 18:22 | EGT-20-1
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 19 | 2 | 3 | 2 | 3 | 584 | 584 | John | Logan | 2023-07-13 18:23 | New Information |  | 2023-07-13 18:23
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 7 | 3 | 2 | 2 | 3 | 584 | 584 | John | Logan | 2023-07-13 18:38 | New Information | Kaltenbach additions | 2023-07-13 18:38
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 8 | 2 | 2 | 4 | 2 | 584 | 584 | John | Logan | 2023-07-13 18:57 | New Information | Kaltenbach additions | 2023-07-13 18:57
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 8 | 3 | 2 | 4 | 2 | 584 | 584 | John | Logan | 2023-07-13 19:00 | New Information |  | 2023-07-13 19:00
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 10 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-13 19:28 | New Project Risk | New Risk Added | 2023-06-13 19:28
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 12 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-13 19:51 | New Project Risk | New Risk Added | 2023-06-13 19:51
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 13 | 1 | 3 | 0 | 0 | 584 | 584 | John | Logan | 2023-06-13 20:06 | New Project Risk | New Risk Added | 2023-06-13 20:06 | PRM-13-1
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 14 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-13 20:17 | New Project Risk | New Risk Added | 2023-06-13 20:17
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 15 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-13 20:27 | New Project Risk | New Risk Added | 2023-06-13 20:27
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 16 | 1 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-13 20:35 | New Project Risk | New Risk Added | 2023-06-13 20:35
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 3 | 1 | 0 | 3 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 17:59 | New Project Risk | New Risk Added | 2023-06-07 17:59
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 4 | 1 | 0 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 18:05 | New Project Risk | New Risk Added | 2023-06-07 18:05
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 6 | 1 | 2 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 18:13 | New Project Risk | New Risk Added | 2023-06-07 18:13
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 7 | 2 | 2 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 21:37 | Corrected Error |  | 2023-06-07 21:37
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 2 | 1 | 0 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 17:58 | New Project Risk | New Risk Added | 2023-06-07 17:58
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 5 | 1 | 2 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 18:07 | New Project Risk | New Risk Added | 2023-06-07 18:07 | EGT-5-1
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 7 | 1 | 2 | 1 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 21:26 | New Project Risk | New Risk Added | 2023-06-07 21:26 | CNT-7-1
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 8 | 1 | 2 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 21:28 | New Project Risk | New Risk Added | 2023-06-07 21:28
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 5 | 2 | 2 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 21:35 | Corrected Error |  | 2023-06-07 21:35
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 5 | 3 | 2 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 21:38 | Corrected Error |  | 2023-06-07 21:38
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 2 | 2 | 0 | 2 | 2 | 138 |  |  |  | 2023-06-26 19:09 | Corrected Error | testing | 2023-06-26 19:09
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 9 | 2 | 2 | 2 | 2 | 138 |  |  |  | 2023-06-26 17:58 | Corrected Error | Modified name for testing purposes | 2023-06-26 17:58
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 2 | 3 | 0 | 2 | 2 | 138 |  |  |  | 2023-06-26 19:10 | Corrected Error | no changes | 2023-06-26 19:10
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 9 | 3 | 2 | 2 | 2 | 138 |  |  |  | 2023-06-26 20:05 | Corrected Error | need to delete | 2023-06-26 20:05
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 9 | 4 | 2 | 2 | 2 | 138 |  |  |  | 2023-07-17 20:32 | New Information | test | 2023-07-17 20:32
3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 9 | 5 | 2 | 2 | 2 | 138 |  |  |  | 2023-07-17 20:33 | New Information | TEST | 2023-07-17 20:33
3914 | Surf City Beach Construction PL 116-20 | 1 | 2 | 2 | 2 | 2 | 584 | 584 | John | Logan | 2023-06-12 15:41 | Corrected Error |  | 2023-06-12 15:41
3914 | Surf City Beach Construction PL 116-20 | 5 | 1 | 2 | 4 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:40 | New Project Risk | New Risk Added | 2023-06-06 20:40
3914 | Surf City Beach Construction PL 116-20 | 7 | 1 | 2 | 0 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:43 | New Project Risk | New Risk Added | 2023-06-06 20:43
3914 | Surf City Beach Construction PL 116-20 | 8 | 1 | 0 | 4 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:45 | New Project Risk | New Risk Added | 2023-06-06 20:45
3914 | Surf City Beach Construction PL 116-20 | 2 | 2 | 2 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 21:53 | Corrected Error |  | 2023-06-07 21:53
3914 | Surf City Beach Construction PL 116-20 | 1 | 1 | 2 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:30 | New Project Risk | New Risk Added | 2023-06-06 20:30
3914 | Surf City Beach Construction PL 116-20 | 2 | 1 | 2 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:32 | New Project Risk | New Risk Added | 2023-06-06 20:32
3914 | Surf City Beach Construction PL 116-20 | 3 | 1 | 2 | 4 | 4 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:34 | New Project Risk | New Risk Added | 2023-06-06 20:34
3914 | Surf City Beach Construction PL 116-20 | 4 | 1 | 3 | 4 | 4 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:38 | New Project Risk | New Risk Added | 2023-06-06 20:38
3914 | Surf City Beach Construction PL 116-20 | 6 | 1 | 0 | 4 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:42 | New Project Risk | New Risk Added | 2023-06-06 20:42
3914 | Surf City Beach Construction PL 116-20 | 4 | 2 | 3 | 4 | 4 | 9033 | 9033 | Erin | Rooks | 2023-06-06 20:51 | Corrected Error |  | 2023-06-06 20:51
3914 | Surf City Beach Construction PL 116-20 | 5 | 2 | 2 | 4 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-06 22:55 | Corrected Error |  | 2023-06-06 22:55
3915 | Seismically Upgrade, Reno B2, Replace B1 | 4 | 2 | 0 | 4 | 0 | 8774 | 8774 | Naomi | Fraenkel | 2023-06-13 12:46 | Corrected Error | test save. no changes actually made | 2023-06-13 12:46
3915 | Seismically Upgrade, Reno B2, Replace B1 | 2 | 1 | 0 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 01:03 | New Project Risk | New Risk Added | 2023-06-07 01:03
3915 | Seismically Upgrade, Reno B2, Replace B1 | 4 | 1 | 0 | 4 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 01:10 | New Project Risk | New Risk Added | 2023-06-07 01:10 | PRM-4-1, PRM-3-1
3915 | Seismically Upgrade, Reno B2, Replace B1 | 6 | 1 | 0 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 01:16 | New Project Risk | New Risk Added | 2023-06-07 01:16 | PRM-3-1
3915 | Seismically Upgrade, Reno B2, Replace B1 | 7 | 1 | 0 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 01:26 | New Project Risk | New Risk Added | 2023-06-07 01:26 | PRM-3-1
3915 | Seismically Upgrade, Reno B2, Replace B1 | 9 | 1 | 0 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 16:26 | New Project Risk | New Risk Added | 2023-06-07 16:26
3915 | Seismically Upgrade, Reno B2, Replace B1 | 10 | 1 | 0 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 16:28 | New Project Risk | New Risk Added | 2023-06-07 16:28
3915 | Seismically Upgrade, Reno B2, Replace B1 | 11 | 1 | 0 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 16:29 | New Project Risk | New Risk Added | 2023-06-07 16:29
3915 | Seismically Upgrade, Reno B2, Replace B1 | 13 | 1 | 0 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 16:32 | New Project Risk | New Risk Added | 2023-06-07 16:32
3915 | Seismically Upgrade, Reno B2, Replace B1 | 1 | 1 | 0 | 2 | 1 | 9033 | 9033 | Erin | Rooks | 2023-06-07 00:45 | New Project Risk | New Risk Added | 2023-06-07 00:45 | PRM-1-1
3915 | Seismically Upgrade, Reno B2, Replace B1 | 1 | 2 | 0 | 2 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 00:46 | Corrected Error |  | 2023-06-07 00:46
3915 | Seismically Upgrade, Reno B2, Replace B1 | 8 | 1 | 0 | 4 | 3 | 9033 | 9033 | Erin | Rooks | 2023-06-07 01:30 | New Project Risk | New Risk Added | 2023-06-07 01:30 | PRM-3-1
3915 | Seismically Upgrade, Reno B2, Replace B1 | 12 | 1 | 0 | 0 | 2 | 9033 | 9033 | Erin | Rooks | 2023-06-07 16:30 | New Project Risk | New Risk Added | 2023-06-07 16:30
3915 | Seismically Upgrade, Reno B2, Replace B1 | 14 | 1 | 0 | 0 | 0 | 9033 | 9033 | Erin | Rooks | 2023-06-07 16:33 | New Project Risk | New Risk Added | 2023-06-07 16:33
3915 | Seismically Upgrade, Reno B2, Replace B1 | 8 | 2 | 0 | 4 | 3 | 9033 | 9033 | Erin | Rooks | 2023-06-07 16:45 | Corrected Error |  | 2023-06-07 16:45
3971 | Homer Navigation Improvements | 2 | 2 | 2 | 4 | 1 | 7996 |  |  |  | 2023-07-12 17:39 | Corrected Error | entered notes from separate risk accidentally. | 2023-07-12 17:39
3971 | Homer Navigation Improvements | 2 | 1 | 2 | 4 | 1 | 7996 |  |  |  | 2023-07-12 17:37 | New Project Risk | New Risk Added | 2023-07-12 17:37
3671 |  | 1 | 7 | 4 | 2 | 4 | 6867 |  |  |  | 2023-05-18 20:26 | Conditions Changed |  | 2023-05-18 20:26
3671 |  | 1 | 2 | 2 | 1 | 4 | 6867 |  |  |  | 2023-03-13 20:00 | New Information | new survey - less sinkholes | 2023-03-13 20:00
3671 |  | 1 | 4 | 4 | 1 | 4 | 6867 |  |  |  | 2023-03-15 17:29 | Conditions Changed |  | 2023-03-15 17:29
3671 |  | 1 | 1 | 4 | 1 | 4 | 6867 |  |  |  | 2023-03-13 19:59 | New Project Risk | New Risk Added | 2023-03-13 19:59
3671 |  | 1 | 3 | 2 | 1 | 4 | 6867 |  |  |  | 2023-03-13 20:03 | Conditions Changed | not enough fill for sinkholes | 2023-03-13 20:03 | EGT-1-2
3671 |  | 1 | 5 | 4 | 1 | 4 | 6867 |  |  |  | 2023-03-15 17:31 | Corrected Error |  | 2023-03-15 17:31
3671 |  | 1 | 6 | 4 | 4 | 4 | 6867 |  |  |  | 2023-03-20 19:46 | Conditions Changed | changed | 2023-03-20 19:46
3671 |  | 2 | 1 | 0 | 2 | 4 | 6867 |  |  |  | 2023-03-20 19:59 | New Project Risk | New Risk Added | 2023-03-20 19:59
3545 |  | 1 | 1 | 2 | 2 | 1 | 2331 | 2331 | Amanda | Ogden | 2023-01-24 14:11 | New Project Risk | New Risk Added | 2023-01-24 14:11
3554 |  | 1 | 1 | 2 | 2 | 4 | 138 |  |  |  | 2023-01-25 20:35 | New Project Risk | New Risk Added | 2023-01-25 20:35
3552 |  | 3 | 1 | 3 | 2 | 4 | 2331 | 2331 | Amanda | Ogden | 2023-01-24 13:56 | New Project Risk | New Risk Added | 2023-01-24 13:56
3552 |  | 1 | 1 | 3 | 2 | 4 | 2331 | 2331 | Amanda | Ogden | 2023-01-24 13:23 | New Project Risk | New Risk Added | 2023-01-24 13:23

## SQL
select t.PROJECT_ID, --p.project_id, p.PROJECT_NAME, t.RISK_ID, t.TRANSACTION_ID, t.PERFORMANCEIMPACT_RISK_RANKING, --DEFNITION? t.COST_RISK_RANKING, --DEFINITION? t.SCHEDULE_RISK_RANKING, -- DEFINITION? --t.RISK_TREATMENTS_IMPLEMENTED, -- is this being used? duplicate of 'RISK_TRANSACTION.TREATMENT_IMPLEMENTED' FIELD t.USER_ID, m.ID, m.FIRST_NAME, m.LAST_NAME, t.DATE_TIME, c.REASON, t.RISK_LOG_NOTE, t.EDITDATE, t.TREATMENTS_IMPLEMENTED from app_err.RISK_TRANSACTION t left outer join app_err.PROJECT_VIEW_NEW p on p.project_id = t.project_id left outer join app_err.REASONCHANGE c on c.id = t.REASONFORCHANGEID left outer join app_err.TEAM_MEMBERS_LOOKUP m on m.ID = t.USER_ID