## Export Worksheet
RISK_ID | RISK_IDENTIFIER | PROJECT_ID | PROJECT_NAME | P2_LOOKUP | RISK_NAME | RISKCATEGORY | RISKCATEGORYID | RISK_STATEMENT | PROB_OCCURRENCE | LIKELIHOOD | LIKELIHOOD_DISC | PROB_OCCURRENCE_EVIDENCE | OCCURRENCECONFIDENCEID | CONFIDENCE | RISKOWNERDISCIPLINEID | DISCIPLINE | DISCIPLINE_ACRONYM | RISKMANAGERID | RISKMANAGER | PERFORMANCEIMPACTTYPEID | PERFORMANCEIMPACTTYPE | PERFORMANCEIMPACT_DESC | PERFORMANCEIMPACT_IMPCT | PERFORMANCEIMPACT_RISK_RANKING | COST_IMPACT_LOWEST | COST_IMPACT_MOSTLIKELY | COST_IMPACT_HIGHEST | COST_IMPACT_EVIDENCE | SCHEDULE_IMPACT_LOWEST | SCHEDULE_IMPACT_MOSTLIKELY | SCHEDULE_IMPACT_HIGHEST | SCHEDULE_IMPACT_EVIDENCE | SCHEDULE_RISK_RANKING | RISKSTATUSID | ID | RISKSTATUS | PROJECTPHASEID | LIFECYCLEPHASENAME | PROJECTMILESTONEID | ID_1 | MILESTONE | EDITDATE | LOCKSTATUS | USER_ID | FIRST_NAME | LAST_NAME | COST_IMPACT_DISTTYPE | SCHEDULE_IMPACT_DISTTYPE | NO_PERFORMANCE_IMPACT | NO_COST_IMPACT | NO_SCHEDULE_IMPACT
2 | PLP-2 | 2126 | Amite River and Tributaries - East of the MS River Analysis | 464542 | Exemption Plan risks: Public Opposition & USACE policies. | Agency Policy and Process | 7 | Public Risk: -Public opposition to NS only alternative in favor of structural alternative. -NS only alternative implementation is voluntary and has historically very low participation rates for the area for similar programs. USACE Risk: -NED analysis limited to cost update only of Dam and 25YR NS, with limited assessment of acceptability and technical criteria-Limited EJ evaluation that may not address all of EPA's request.-Limited sub-aggregation of NS plan. -Limited Comprehensive benefits assessment. -LPP waiver approval-Since the NS plan is voluntary, will the plan demonstrate that the disadvantage communities/population can be accommodated i.e.. a) since they are likely to be unable to accept that burden for temporary relocation b) If structures are valued less than the cost of elevation, how is USACE accommodating? | 3 | Likely | Likely (50% to 70%) | -Support comes from the public that represents the owners of approximately 36,000 structures that would receive benefits from the Darlington Dam structure alternative vs. the approximately 300 structures in the footprint of the dam.-NEPA letter submitted on 2/20/20 requesting EJ outreach and survey. -Historically difficult to document inclusivity in implemented nonstructural plans'-Presently the study does not have technical conclusion that Presently the study does not have technical conclusion that the Darlington dam alternative is not feasible. |  |  | 13 | Planning - Plan Formulation | PLP | 4751 |  | 8 | Agency Strategy | An additional exemption request is currently being prepared to incorporate the time assumption length needed in case of NED waiver. Can not estimate project performance impact if NFS no longer concurs with a NS only plan due to the public opposition. | 10 | 3 | 0 | 0 | 0 | Unknown at this time | 0 | 0 | 0 | Unknown at this time; however, an additional exemption request is currently being prepared that would include the NED waiver time estimate (of 4 months) based on MVD provided assumptions to include. | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-06-02 19:19 | 0 | 4751 | Lesley | Prochaska | 299 | 299 | 0 | 0 | 0
1 | PLP-1 | 2307 | Miami-Dade Back Bay Coastal Storm Risk Management Feasibility Study, Miami-Dade County, Florida | 476677 | Florida Statute - Biscayne Bay Preserve | Legislative or Political | 8 | Florida Statute 258.397 Biscayne Bay Preserve - limits filling and dredging within Biscayne Bay. https://www.flsenate.gov/laws/statutes/2019/258.397 Coordinating agencies include Miami-Dade County Department of Environmental Resources Management and Florida Department of Environmental Protection. | 5 | Extremely Likely | Extremely Likely (90% to 100%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 488 |  | 6 | Compliance | This will impact all measures in the Biscayne Bay including the 2021 Recommended Plan | 10 | 4 | 0 | 0 | 0 |  | 0 | 0 | 0 | Environmental compliance will be impacted without a coordinated path forward. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-17 14:10 | 0 | 488 | Michelle | Hamor | 299 | 299 | 0 | 0 | 0
2 | EHH-2 | 2307 | Miami-Dade Back Bay Coastal Storm Risk Management Feasibility Study, Miami-Dade County, Florida | 476677 | Coastal Barriers - Haulover Inlet | Info and Data Analysis | 1 | Environmental Compliance requires exact footprint of outer barrier location. That will be a challenge without modeling several different scenarios to determine the best location. Bridge Scour analysis is needed, sedimentation analysis is needed, and ADCIRC modeling refinement is needed to understand if out barrier lowers the water levels in the Back Bay. Cost and time may be a factor. | 4 | Very Likely | Very Likely (70% to 90%) | It is very likely that complications or non compliance will occur if the Inlet is not modeled. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 5170 |  | 6 | Compliance | If the ADCIRC ERDC modeling determines that the outer barrier is ineffective, then this may change the focus on where to provide structural measures. | -10 | 1 | 0 | 0 | 0 | cost has not been estimated at this time. The cost of a sector gate at this inlet could be prohibitive. | 0 | 0 | 0 | There will be a schedule impact because the ADCIRC analysis has to occur to decided if out barriers are needed. Timeframe has not been estimated to complete modeling. | 1 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 18:44 | 0 | 5170 | Robin | Williams | 299 | 299 | 0 | 0 | 0
2 | PLP-2 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | BUDM/Placement Analysis | Info and Data Analysis | 1 | There is a wide range of anticipated dredged material volumes early in the study (from 5MCY to well over 20 MCY). The risk is ensuring there is sufficient capacity in identified placement sites to accommodate the volumes both for the initial construction and the 20-year O&M. Current Placement Area opportunities include Egmont (nearshore/beach/island restoration), 2D, 3D, ODMDS, viable dredge holes (4), island creation (for private use, bird habitat creation, and seagrass restoration), permitted Port site, Manatee County boat launch site. Team will conduct least cost analysis. Viable options that are not least cost will be pursued to see if there is a cost sharing partner to pay incremental difference. | 3 | Likely | Likely (50% to 70%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 15:01 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
4 | ESD-4 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Subsurface Utilities | Site Conditions | 6 | EN recalls that TECO possibly has a gas line that intersects the proposed project area. EN mentioned that the subsurface utilities did not interfere with the previous plans to Widen Cut-B. To mitigate risk, it is necessary to obtain a map of all subsurface utilities. | 3 | Likely | Likely (50% to 70%) | EN recalls that TECO possibly has a gas line that intersects the proposed project area. EN mentioned that the subsurface utilities did not interfere with the previous plans to Widen Cut-B. Consequence if subsurface utilities do interfere: delay in study approval and/or increase cost. |  |  | 6 | Engineering - Structural Design | ESD | 2963 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-17 19:56 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
5 | PLP-5 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Study Funding Delays | Agency Policy and Process | 7 | The PDT's available funding as of 1-JUN will likely only last the PDT through June. When SAJ requested additional funding in May, funding was denied and the MSC/HW indicated additional study funds may not be approved until a decision on the exception request is made | 3 | Likely | Likely (50% to 70%) | Likelihood is solely dependent on leadership/vertical team |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other | Funding needs must be met for the study to stay on schedule. | 10 | 3 | 0 | 0 | 0 |  | 0 | 120 | 0 | If funding is delayed, the schedule will be delayed. the TSP milestone will not be met | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 13:53 | 0 | -99 |  |  | 299 | 299 | 0 | 0 | 0
6 | EHH-6 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Widening of Passing Lanes | Site Conditions | 6 | Widening for passing lanes would be conducted from the centerline of the channel rather than to one side only. Deepening of the channel would impact hardbottoms (HB) on both sides of the channel; however the difference of deepening impacts compared to the widening impacts to these HB are unknown. There is a risk of greatly increasing HB impacts from widening both sides of the channel over the impacts resulting from deepening alone. Additional HB surveys (in situ, qualitative, and quantitative) may be required to assess impacts if widening is determined to cause impacts over deepening alone. Additional mitigation may be required if impacts are greater | 3 | Likely | Likely (50% to 70%) | Hardbottom surveys are ongoing (As of MAY-202X). Impacts will be better understood when these surveys are complete in Fall 202X |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 2963 |  | 5 | Other | Mitigation is available through beneficial use of the rock dredged during construction | 5 | 2 | 0 | 0 | 0 | Additional HB surveys to evaluate impacts could be expensive and time-consuming, increasing cost. | 0 | 0 | 0 | Additional HB surveys to evaluate impacts could be expensive and time-consuming, delaying the study. | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-05-18 14:07 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
7 | PRM-7 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Federal Funding | Agency Policy and Process | 7 | There will be a gap in Federal funding streams for the study after the AMM. NFS can accelerate their share of the funding. Three various efforts are in play during the spring (earmark, workplan, infrastructure bill) which could help in getting needed Federal funding. 15-FEB-22: Funding from IIJA was approved in early 2022 to fully fund the Federal portion of the study at $3M. Based on the $4.5M study budget, these federal funds will be sufficient to fund the study through the TSP (Spring 2023) | 1 | Very Unlikely | Very Unlikely (5% to 30%) | There are several avenues in play, subject to change |  |  | 17 | Project Management | PRM | 514 |  | 8 | Agency Strategy | Team would need to stop work if all funds exhausted. 1-APR-2022: There is sufficient time to plan ahead to maintain funding streams consistent with the authorized budget. The rating was downgraded from "major problem" to "minor problem", but is dependent upon receiving a decision to the exception request by 1-JUL to avoid schedule impacts. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | There is a risk that if there is a gap in Federal funding for too long, NFS accelerated funds may be exhausted, causing a study delay and risk to 3-year schedule | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 14:36 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
8 | PLC-8 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Cultural Resources Surveys | Info and Data Analysis | 1 | The team is currently not pursuing a Programmatic Agreement (PA), but to reduce risk will conduct needed surveys for placement areas during feasibility. Channel is generally already surveyed but there could be some additional surveys | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 14 | Planning - Cultural Resources | PLC | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 | A wide array of placement areas is under consideration. All options may need to be analyzed if some are not screened out early, and may require additional funding | 0 | 0 | 0 | A wide array of placement areas is under consideration. All options may need to be analyzed if some are not screened out early, and may require additional time | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 14:48 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
9 | PLE-9 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Environmental Surveys & Effects Analysis for Placement | Info and Data Analysis | 1 | If placement options are not decided upon with enough time, then must include all in NEPA analysis, including potential surveys, which would take more time, funding, and effort | 3 | Likely | Likely (50% to 70%) |  |  |  | 16 | Planning - Environmental | PLE | 8837 |  | 5 | Other | More time and funding needed to include all placement options in NEPA analysis | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 14:53 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
10 | PLP-10 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Policy Exception for Additional Funding | Agency Policy and Process | 7 | Scope necessitates a need for a policy exception for an additional $1.5M to perform the needed analysis through the TSP. Exception request was submitted in early 2022. There is some risk and uncertainty as to whether a policy exception will be granted. | 3 | Likely | Likely (50% to 70%) | If a decision is not made by 1-JUL-2022, there would be significant schedule delays to realign scope of study to enable its completion in 3 years and under $3M. |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other | Port would lose the chance for Corps to do important analysis on reducing congestion (through passing lanes) and maneuverability (turning basins) | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 15:05 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
11 | PLE-11 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Environmental Compliance - Hardbottom & Seagrass Surveys | Info and Data Analysis | 1 | Environmental compliance such as a BO could require more extensive seagrass/channel edge surveys. Multibeam and camera drops could be needed to provide additional information. Study will use side scan sonar to better understand extent of hardbottom along channel, to complete environmental compliance during feasibility for effects analysis. Study will use existing seagrass surveys to begin assumptions for effects analysis and could propose to complete final surveys in PED/prior to construction to refine placement locations to avoid seagrass or refine effects as needed. | 3 | Likely | Likely (50% to 70%) | Env surveys were conducted in ~2008 for Cuts A and B. Agencies likely have seagrass surveys that could be used for planning purposes and effects analysis. |  |  | 16 | Planning - Environmental | PLE | 8837 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 15:08 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
12 | PLE-12 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | UMAM Impact Analysis | Info and Data Analysis | 1 | Team will use UMAM for impacts analysis, NMFS HCD is onboard. There could be risk if support changes | 1 | Very Unlikely | Very Unlikely (5% to 30%) | This was coordinated with NMFS HCD in an email on 10-DEC-2021, where NMFS HCD agreed with the path forward to use this model. |  |  | 16 | Planning - Environmental | PLE | 8837 |  | 5 | Other | Team would need to re-coordinate model for effects analysis | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 15:08 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
13 | PLP-13 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Scope Selection | Agency Policy and Process | 7 | Team has evaluated scopes relative to key problems, for multiple parameters of time and funding, under 9 key risk drivers. This scope still has many challenges but the over risk to completing it in the funding/timeframe is medium. The team will proceed with scope 2 for the study analysis, per Port decision at meeting on 12/8/2021 (analysis of incremental deepening, incremental wideners for transitions, passing lanes and turning basins, as well as beneficial use). | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Very low likelihood. Team has evaluated scope. |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-18 18:44 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
14 | ESD-14 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Ship Simulation | Info and Data Analysis | 1 | Study will include ship simulation during feasibility study for passing lane and turning basin analysis for design and optimization of footprint. Ensure have adequate time and funding to include it. | 2 | Unlikely | Unlikely (30% to 50%) | Unlikely, ROM costs and timeframe has been included in the study scope and budget. |  |  | 6 | Engineering - Structural Design | ESD | 2963 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 18:11 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
15 | PLE-15 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | EQ/OSE/RED Qualification Benefits Analysis | Agency Policy and Process | 7 | Risk that EQ/OSE/RED quantification benefits analysis is new, and many districts may be doing it differently, making it difficult to know what the standard process should be to meet policy requirements. Also, given the post-pandemic world many business and operations are changing and may change during or after the analysis. | 3 | Likely | Likely (50% to 70%) | Somewhat likely given new guidance without implementation guidance |  |  | 15 | Planning - Economics | PLE | 2265 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 18:33 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
16 | PLE-16 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Design Vessel Selection | Info and Data Analysis | 1 | Ensure that the proper design vessel(s) are selected/explored when evaluating the potential scope of the study. Risk of a poor planning decision if study team doesn't holistically look at the vessels utilized at the neighboring ports such as Mobile, New Orleans, and Houston. | 2 | Unlikely | Unlikely (30% to 50%) | 1-MAR-22: Design Vessel was selected and PTB concurred with the appropriateness of its use. |  |  | 15 | Planning - Economics | PLE | 2265 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-18 18:47 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
17 | ESD-17 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Deepening beyond 50 feet | Info and Data Analysis | 1 | Preliminary analysis shows that depths just off the outer entrance channel are ~50 feet. Potential deepening beyond that could cause a need to deepen beyond that, so ensure a gradual transition for vessels. This could have a large cost implication for the cost analysis pertaining to those alternatives. | 3 | Likely | Likely (50% to 70%) | This still needs to be understood and analyzed further by the team. |  |  | 6 | Engineering - Structural Design | ESD | 2963 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 19:04 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
18 | EHH-18 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | H&H Modeling Needs | Info and Data Analysis | 1 | Numerical modeling of disposal site suitability (waves/sediment transport) as well as effects of disposal sites (flushing/circulation) may be needed later, to support env compliance. The need, extent, and type of numerical modeling has not yet been identified. When the need/extent/type of numerical modeling is identified, it could be later in the study process leading to schedule delays and cost increases. | 3 | Likely | Likely (50% to 70%) |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-05-18 19:10 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
19 | PLP-19 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Relocation of ATONS | Site Conditions | 6 | USCG ATONS will likely be affected from a TSP/recommended plan due to potential passing lanes. Relocations of ATONS must be coordinated with USCG and are also paid for Federally out of USCG. These take a lot of coordination and could be expensive. USCG needs time to vet and plan for these changes and costs. USCG may need more time or have funding constraints. | 3 | Likely | Likely (50% to 70%) | It is somewhat likely, but more unlikely if coordination begins early. |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 19:14 | 0 | 4951 | Juliana | Matiz | 299 | 299 | 0 | 0 | 0
1 | PLP-1 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Road not completed from Akutan Harbor to Akutan | Stakeholder, Sponsor or Partners | 9 | Road not completed from Akutan Harbor to Native Village of Akutan May not be able to utilize Akutan Harbor to transport goods/passengers in and out of Akutan Road was not required LSF for the Akutan Harbor Project | 2 | Unlikely | Unlikely (30% to 50%) | original likelihood: none Road was not required LSF for the Akutan Harbor Project Funding has been received to construct road and permit application with USACE updated 2023. Materials will be stockpiled during 2023, construction 2024. |  |  | 13 | Planning - Plan Formulation | PLP | 7887 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-03-14 19:29 | 0 | 7887 | John | Olson | 299 | 299 | 1 | 1 | 1
2 | PLE-2 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Some economic benefit categories may be unknown | Info and Data Analysis | 1 | Some economic benefit categories may be unknown. On-site open discussion allows for other potential benefit categories and project impacts to come to light, without those discussion opportunities our data may be limited. May leave unknow benefits undocumented. | 3 | Likely | Likely (50% to 70%) | original likelihood: low On-site meetings planned in the near future |  |  | 15 | Planning - Economics | PLE | 5479 |  | 7 | Agency Reputational |  | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | andria, update?? | 1 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 19:31 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 1 | 0
3 | PLE-3 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Under/overestimating benefits | Info and Data Analysis | 1 | Only transportation cost savings and reduced delays were considered during FID May not account for all benefits Could lead to inaccurate documentation of benefits and inaccurate BCR | 2 | Unlikely | Unlikely (30% to 50%) | original likelihood: low Other benefits will be examined during feasibility |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 19:32 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 1 | 1
4 | PLE-4 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Use of pre-COVID transportation data | Info and Data Analysis | 1 | Decline in transportation since 2020 assumed to be solely due to COVID-19 pandemic. Pre-pandemic transportation levels are assumed to be more accurate for long-term transportation demand. Most recent data is not used. Fail to capture other causes in transportation decline. Fail to capture post-pandemic tranportation changes if transportation demand is not expected to return to pre-pandemic levels Potential to misidentify a transportation trend that could impact the economic analysis. Could lead to inaccurate analysis of future conditions | 4 | Very Likely | Very Likely (70% to 90%) | original likelihood: High Unknown if decline was due solely to COVID-19 and only way to verify is post-pandemic transportation levels which are not available |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:34 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
5 | PLE-5 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | subsistence benefits | Site Conditions | 6 | Assumed knowledge of fishing/hunting areas and project would improve access to these areas. Fishing/hunting areas may not be completely known or the project may not improve access to the areas. Could lead to inaccurate documentation of OSE benefits Fishing/hunting areas may not be completely known or the project may not improve access to the areas Could lead to inaccurate documentation of OSE benefits | 1 | Very Unlikely | Very Unlikely (5% to 30%) | original likelihood: low Community meeting and reaching out to the Community POC on subsistence are planned for the near future and subsistence will be one of the topics discussed |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 19:35 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
6 | PLE-6 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Negative Impacts | Info and Data Analysis | 1 | May have negative impacts that we are not identifying. Might miss some negative impacts from the projects. Could lead to inaccurate economic analysis | 1 | Very Unlikely | Very Unlikely (5% to 30%) | original likelihood risk: low Community meetings are planned in the near future. Meeting held in November. |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 19:36 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
7 | PLE-7 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Project justification on NED benefits | Info and Data Analysis | 1 | It is assumed that the project would be able to be justified on NED benefits due to the intitial FID analysis, however, some costs and benefits have been identified since the FID which may lead to the need to justify the project based on OSE benefits. If the feasibility study does not identify an NED justified plan, pivoting to OSE justification will be more difficult and likely more time consuming due to data gathering and communication requirements. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | original likelihood: Medium If the project cannot be justified on NED benefits, the team will need to pivot to OSE justification |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 17:59 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
8 | PLE-8 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Underestimating costs | Info and Data Analysis | 1 | Costs for shuttle vessel, O&M for shuttle vessel and LSF were not included in the FID cost estimates. The absence of cost for vessel, OMRR&R and LSF could lead to inaccurate BCR | 2 | Unlikely | Unlikely (30% to 50%) | original likelihood: Low Could impact project cost |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 18:01 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
9 | PLE-9 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Misappropriation of benefits | Info and Data Analysis | 1 | As shuttle transport would be a new activity, the transportation benefits may be treated as recreation benefits, not commercial benefits Could lead to misappropriation of benefits | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | original likelihood: not filled out. |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 18:02 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
10 | PLE-10 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Shuttle vessel operating limitations | Info and Data Analysis | 1 | Based on vessel feasibility report, the shuttle vessel design would allow operation in conditions up to an 8 ft wave and a 20 knot wind, which may preclude operation for a substantial portion of time. If vessel operating limitations are not considered it could lead to overstating benefits Possibly lead to inaccurate economic analysis | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | Original likelihood: low Operational conditions will be examined during feasibility |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 18:05 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
11 | PLE-11 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Aircraft operating limitations | Info and Data Analysis | 1 | Aircraft can only operate in conditions with windspeed of less than 15 knots. This may limit the flights in and out of Akutan airport. If aircraft operating limitations are not considered it could lead to overstating benefits | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | Original likelihood: low Operational conditions will be examined during feasibility |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 18:07 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
12 | PLC-12 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Site selection will likely be a previously impacted area. | Info and Data Analysis | 1 | Historic properties are located all along the coast, the proposed project site has been previously impacted. Historic properties are located all along the coast, the proposed project site has been previously impacted. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | original likelihood: low Cultural Resources coordination and analysis will occur during feasibility and PED |  |  | 14 | Planning - Cultural Resources | PLC | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 18:16 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
13 | PLC-13 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Identify cultural resources at the site through existing doc | Site Conditions | 6 | Cultural resources can include aspects like sites used for traditional dancing, greeting places, worship, etc. May have positive economic benefits/negative impacts to cultural sites that have not been formally documented. Possible increase in project costs and negative impacts to cultural resources | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | original likelihood: low Cultural Resources coordination and analysis will occur during feasibility and PED |  |  | 14 | Planning - Cultural Resources | PLC | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:17 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
14 | PLC-14 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | ESA/MMPA Policy Exception | Legal or Regulatory Actions | 10 | There may be a need to submit a policy exception request due to blasting requirements Project schedule could be delayed if policy waiver is not begun early in the process Possible delayed schedule if policy waiver is not obtained during feasibility, if needed. | 3 | Likely | Likely (50% to 70%) | original likelihood: low Determination of policy waiver is planned for early in the study to initiate a policy waiver, if required |  |  | 14 | Planning - Cultural Resources | PLC | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:19 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 1 | 0
15 | EHH-15 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Unknown nearshore bathymetry | Info and Data Analysis | 1 | Bathymetry cannot be collected in the nearshore zone due to the small tide range and safety concerns for operating a vessel in shallow waters near an apparent rocky shoreline. Bathymetry will be interpolated from deeper waters to the base of the shoreline where data can be collected by terrestrial methods. This lack of data produces uncertainties in breakwater and dredging quantities and produces more uncertainty of the character of bottom materials. If interpolation/assumptions are incorrect, it could lead to increased project cost and non-performace of the project | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | original likelihood: medium There will be some uncertainty regarding the interpolations |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:21 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
16 | EHH-16 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Unknown nature of materials to be dredged | Info and Data Analysis | 1 | Aerial imagery shows a mix of rock outcrops and granular material along the coastline in the study area. It is not known how deep the granular material deposits are which would affect the efficiency of dredging operations. Dredging requirements for these materials are significantly different. Blasting may be required to remove the rocky materials. Mechanical methods would be needed to remove materials loosened by blasting. The assumption can be made that all materials will require blasting for removal. Blasting requirements may lead to increased project cost and need for ESA/MMPA policy exception | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | original likelihood: medium Dredging requirements will be analyzed during feasibility. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:23 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
17 | EHH-17 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Availability of suitable stone to construct breakwaters at A | Info and Data Analysis | 1 | There may be an effort to try to assume rock can be mined locally or nearby to construct breakwaters at Akun. No known quarries are available on Akun or Akutan. Rock Sources at Dutch Harbor are not known to produce rock in sufficient quantity or quality for this project. The closest known active quarries are located at Cape Nome or Sand Point. Rock may have to be transported from Cape Nome or Sand Point for the project If a local source of rock is not available, it could increase project cost | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | original likelihood: low Rock sourcing will be examined during feasibility |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:24 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
18 | PLP-18 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Wave conditions required for safe operation of ferry service | Info and Data Analysis | 1 | The team will need to decide on vessel dimensions and determine the sea conditions in which the vessel can transit the channel between Akun and Akutan. Assumption of design vessel characteristics should be vetted with community leaders or stakeholders such as APICDA to make a reasonable assumption of the characteristics of the design vessel. With any vessel assumption, there is a risk that the vessel that is eventually used for this purpose does not meet these assumptions and may not be able to operate in the conditions assumed in the study. If vessel cannot operate under assumed conditions, could lead to overstating benefits and underperformance of the project | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | original likelihood: low Wave conditions, operational conditions and vessel design will be examined during feasibilty |  |  | 13 | Planning - Plan Formulation | PLP | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:26 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
19 | EHH-19 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Percent dredge needs blasting for cost estimates | Info and Data Analysis | 1 | If assumption is low, can result in increased costs as well as possible increase in environmental impacts Increase in study costs, increase in enviromental impacts, Increase in study time Under estimation of blasting requirements would result in schedule and budget overruns due to increased blasting, increase disposal, and possibility of the unanticipated need for an EIS | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | Geotechnical data can be utilized to accurately determine amount of blasting needed in the project Ensure data from geotechnical study incorporated into cost estimates and feasibility report as soon as it becomes available Geotech data preliminary data shows some discrepancies in the collected data. Awaiting determination of how these discrepancies will be resolved |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-16 15:46 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
20 | PLP-20 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Delays could be incurred due to inclement weather | Site Conditions | 6 | If not accounted for via contingency, budget and schedule could be impacted. High winds and waves are not uncommon | 3 | Likely | Likely (50% to 70%) | Tolerate the risk |  |  | 13 | Planning - Plan Formulation | PLP | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-16 15:47 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
21 | EHH-21 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Changes in storm/wave frequency could impact subsis/commerc | Site Conditions | 6 | If weather events occur, project costs and time could increase Climate change/sea level rise are ongoing global events Follow USACE guidance developed to account climate change related uncertainty | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 15:49 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
22 | PLC-22 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Cultural resources | Site Conditions | 6 | would need to investigate, mitigate if occurs Cease construction, investigate, possibly mitigate If cultural resources are found, work would be stopped increasing time and costs associated with the project | 3 | Likely | Likely (50% to 70%) | Known cultural resources sites in project area |  |  | 14 | Planning - Cultural Resources | PLC | 3455 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:13 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
23 | PLE-23 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Dredge material disposal | Site Conditions | 6 | What is the most appropriate method for dredge material disposal Without proper dredge disposal analysis, it could have impacts to cost and environment If dredge material is disposed improperly it could lead to higher project costs and environmental consequences | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Disposal area coordinate points have be identified and no known HTRW in the project area |  |  | 16 | Planning - Environmental | PLE | 525 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:15 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
24 | PLE-24 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | CERCLA/HTRW materials | Site Conditions | 6 | No known contamination in the project area If CERCLA/HTRW are discovered, it would increase disposal costs If HTRW were found, it could lead to higher project costs and environmental consequences | 1 | Very Unlikely | Very Unlikely (5% to 30%) | No known HTRW in the project area |  |  | 16 | Planning - Environmental | PLE | 525 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:16 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
25 | EGT-25 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Additional geotechnical investigations in PED | Site Conditions | 6 | Exisiting geotechnical data used to estimate project quantities and methods If estimates were inaccurate, it could lead to an increase in project costs If geotechnical estimates were inaccurate, it could impact project costs and time | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | There is existing geotechnical data for much of the area, but not all of it |  |  | 3 | Engineering - Geotechnical | EGT | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-03-16 17:18 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
26 | EHH-26 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Shoreline erosion | Site Conditions | 6 | Shoreline erosion may occur due to project implementation Nearshore wave and circulation patterns could be changed due to project implementation which may increase erosion If shoreline erosion occurred at a higher rate, O&M costs could be impacted | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Modelling has taken into account longshore sedimentation rates and circulation patterns Beneficial use of dredge material and local gravel resources to mitigate erosion |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:23 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
27 | PLE-27 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Trident moves out of Akutan | Stakeholder, Sponsor or Partners | 9 | Trident may move from Akutan to Dutch Harbor . Raw seafood tax pays AEB 2% and Akutan 1%. Loss of this revenue may result in inability to pay for LSF features | 3 | Likely | Likely (50% to 70%) | Trident subsidary LFS Inc awarded 75 year lease of Unalaska - Captains Bay tidelands and are building a dock. Trident has stated that the Akutan facility needs to be updated. |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:24 | 0 | 7887 | John | Olson | 299 | 299 | 0 | 0 | 0
1 | PLP-1 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | EO 11988 Floodplain Management | Agency Policy and Process | 7 | EO 11988 states ":in order to avoid to the extent possible the long- and short-term adverse impacts associated with the occupancy and modifications of floodplains and to avoid direct or indirect support of floodplain development wherever there is a practicable alternative" Structural recommendations could be found non-compliant with EO 11988 due to inducing development in the Mossdale Tract area. | 3 | Likely | Likely (50% to 70%) | The previous study, the 2018 Interim Report, delayed recommendations for the Mossdale Tract area due to this issue, however the scope of the study includes a robust EO 11988 analysis combined with risk-informed planning to include a risk assessment and development of a Flood Plain Management Plan concurrent with the study. |  |  | 13 | Planning - Plan Formulation | PLP | 298 |  | 5 | Other | Not meeting compliance requirements with EO 11988 will lead to a negative Federal interest determination in regard to structural flood risk management in RD17 (Mossdale Tract). If this is the case, structural flood risk management measures will not move forward to PED and construction and the non-Federal sponsor's objectives of meeting SB 5 requirements will not be met. The outcome could result in a recommendation that does not meet the study objectives of the primary project purpose. | 10 | 3 | 0 | 300000 | 0 | $300,000 has been included in the scope of the study to mitigate this risk to the current level. | 0 | 0 | 0 | EO 11988 analysis is planned to be complete concurrent with TSP development. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-08 14:05 | 0 | 298 | Holly | Carpenter | 299 | 299 | 0 | 0 | 0
3 | PLE-3 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Study Delays: Economic Modeling Software Updates | Info and Data Analysis | 1 | Delay in study completion due to incorporation of updated economic modeling software. TotalRisk is in the process of being certified. | 2 | Unlikely | Unlikely (30% to 50%) | Plan to utilize TotalRisk with certification expected before TSP as coordinated with the vertical team. HEC-FDA will also be utilized to validate findings in the new modeling software and in case TotalRisk is not certified by TSP. |  |  | 15 | Planning - Economics | PLE | 5615 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-08 14:21 | 0 | 7687 | Miranda | Peters | 299 | 299 | 0 | 0 | 0
4 | PLE-4 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Study Delays: Ecosystem Restoration Modeling | Info and Data Analysis | 1 | Delay in study completion due to ecosystem restoration modeling, data collection and coordination timelines. Meeting was held on January 4, 2023, with USFWS to discuss potential models to be utilized in this study. Based on this meeting and earlier coordination, there is remaining risks that USFWS may recommend models that are currently not certified for evaluation of ER features. The District plans to utilize models with certification recently approved or expected soon for the LSJR area for HSI Mink, Black Shouldered Kite, Riparian Songbird, Yellow Warbler and Riparian Forest for both the ER and mitigation analysis requirements of the project. The District coordinated this assumption with the ECO-PCX on 16 December 2022 via email. Additionally, the models planned for use have been included in the draft review plan reviewed by the ECO-PCX. However, certification of additional models may be needed as the ER features are further refined. This scenario would require close coordination and cooperation with the ECO-PCX and USFWS to ensure TSP milestone is not delayed. | 3 | Likely | Likely (50% to 70%) | Early coordination and communication with USFWS and NMFS will allow the team adequate time to ensure the required agency coordination and data collection is achieved. There is remaining risks that USFWS could require additional models to be certified for the purpose of determining mitigation requirements. |  |  | 16 | Planning - Environmental | PLE | 8753 |  | 5 | Other | There may be conflicting priorities and timelines with the coordination agencies in terms of negotiations and data collection. These model runs are imperative to alternative selection. | 10 | 3 | 0 | 0 | 0 | Additional funding included within overall environmental budget to support coordination to utilize certified models or models under the certification process from the LSJR construction phase project. | 0 | 0 | 0 | None, the District currently plans to utilize HSI models that are certified or are anticipated to be certified ahead of the TSP milestone for NER analysis. There is remaining risks that USFWS could require additional models to be certified for the purposes of determining mitigation requirements. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-08 14:20 | 0 | 7687 | Miranda | Peters | 299 | 299 | 0 | 0 | 0
5 | PLP-5 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Study Delays: LifeSIM Modeling | Info and Data Analysis | 1 | Justification of OSE and compliance with the 5 January 2021 Policy Directive for Comprehensive Documentation of Benefits may not be met without modeling in Life SIM. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | LifeSIM is planned for this study. |  |  | 13 | Planning - Plan Formulation | PLP | 7687 |  | 5 | Other | Justification of OSE and compliance with the 5 January 2021 Policy Directive for Comprehensive Documentation of Benefits may not be met without modeling in Life SIM. Therefore the study team is planning to incorporate LifeSIM in the current study scope. | 5 | 2 | 0 | 0 | 0 | LifeSIM is included i n the scope of the study. | 0 | 0 | 0 | LifeSIM is included in the scope of the study. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-08 14:23 | 0 | 7687 | Miranda | Peters | 299 | 299 | 0 | 0 | 0
6 | EHH-6 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Study Delays: Inclusion of Inland Climate Change Analysis | Info and Data Analysis | 1 | Potential delay in study completion and increase in study costs due to inclusion of inland climate change projections over the period of analysis. The State of California is concerned about potential significant increases in flows in the San Joaquin River due to inland climate change impacts over the planning horizon. Relying only upon the historical record for estimating future hydrologic and hydraulic conditions could underestimate the flood risk in the Mossdale Tract area. | 4 | Very Likely | Very Likely (70% to 90%) | Potential delay in study completion and increase in study costs due to inclusion of inland climate change projections over the period of analysis. There is a medium chance that the inclusion on an inland climate change analysis may significantly impact both schedule and budget. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8752 |  | 5 | Other | Inclusion of inland climate change projections over the period of analysis poses a Medium Risk to performance due to potential delay in study completion, increase in study costs, and impacts to schedule. The PDT is working with the Climate, Preparedness and Resiliency (CPR) Community of Practice (CoP) to determine the appropriate level of analysis to capture potential inland climate change impacts on selecting a recommended plan. Incorporation of inland climate change impacts will extend the study schedule and increase the budget. Not incorporating inland climate change impacts may not be acceptable to the local sponsors and could impact the level of flood risk management recommended for the Mossdale Tract area. The team is planning to conduct a hybrid approach to utilizing inland climate change for a sensitivity analysis, but not within the economic justification for the project. | 10 | 3 | 0 | 300000 | 0 | There is a medium chance that the inclusion on an inland climate change analysis may significantly impact both schedule and budget. A hybrid approach using DWR data for sensitivity analysis (evaluate change to EAD, AEP, CNP) to verify if the plan selection is sensitive to inland climate change. Economic analysis and study recommendation would NOT account for inland climate change impacts; Not included in economic justification. | 0 | 120 | 0 | There is a medium chance that the inclusion on an inland climate change analysis may significantly impact both schedule and budget. The PDT will prioritize determining the TSP and then conduct additional sensitivity analysis modeling. If a full in-depth analysis is required for plan selection, then study team will request an additional waiver for funding and time to support the completion of the in-depth analysis and incorporation into the project plan selection and economic justification. No study delays if finding confirms hybrid approach using DWR data for sensitivity analyses is not needed. | 3 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 20:19 | 0 | 7687 | Miranda | Peters | 299 | 299 | 0 | 0 | 0
7 | RLE-7 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Poor Planning Decision: Identifying Real Estate | Resource Availability | 5 | The District recognizes the challenge in locating mitigation sites due to limited available real estate within the Mossdale Tract area and the large amount of mitigation that could be required for potential structural measure recommendations of proposed FRM features; risk of inadequate resources to fulfill mitigation required for project implementation. | 4 | Very Likely | Very Likely (70% to 90%) | The District recognizes the challenge in locating mitigation sites due to limited available real estate within the Mossdale Tract area and the large amount of mitigation that could be required for potential structural measure recommendations. Concurrently with NNBF and ER refinements and alternative analysis, the District will develop potential mitigation locations contributing to the mitigation plan development for structural measures that could be recommended under this study effort. |  |  | 18 | Real Estate | RLE | 7687 |  | 5 | Other | Assumption: The team will know early on what land will and will not be available for acquisition. This will inform the recommended plan features and locations. Despite the teams efforts in conducting appropriate outreach to gage availability of land for mitigation purposes, if there are inadequate resources to fulfill mitigation requirements for project implementation, impacts to overall project would be a major problem. | 10 | 3 | 0 | 0 | 0 | Due to the risk of inadequate resources to fulfill mitigation required for project implementation, the team is conducting appropriate outreach to ensure they are aware of which land would and would not be available for mitigation purposes | 0 | 0 | 0 | The team will know early on what land will and will not be available for acquisition. This will inform the recommended plan features and locations. With NNBF and ER refinements and alternative analysis, the District will develop potential mitigation locations contributing to the mitigation plan development for structural measures that could be recommended under this study effort. This early recognition of the need for mitigation sites and early coordination could allow for completion of the study mitigation plan concurrently with the overall study schedule. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 18:06 | 0 | 7687 | Miranda | Peters | 299 | 299 | 0 | 0 | 0
8 | PLP-8 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Poor Planning Decision: Levee Design Approval | Agency Policy and Process | 7 | Selection of a plan that complies with USACE levee design guidance, including vegetation on levees. Opposition of the plan unless variances are received to reduce vegetation removal. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 7687 |  | 5 | Other | Unlikely performance impact since the PDT will be focused on selecting a plan that will comply with USACE levee design guidance, including vegetation on levees, or applying for variance during PED and Construction. The PDT will adopt the recommendations from the 2018 interim study to address vegetation on levees and assess the need for a variance during the development of detailed designs in the Pre-Construction Engineering and Design or Construction phases. The Recommended Plan will comply with USACE levee design guidance. | -5 | 1 | 0 | 0 | 0 | Additional mitigation costs to implement the project. Depending on the amount, the mitigation costs could impact the project BCR. Unlikely since the PDT will be focused on selecting a plan that will comply with USACE levee design guidance, including vegetation on levees, or applying for variance during PED and Construction. | 0 | 0 | 0 | Unlikely since the PDT will be focused on selecting a plan that will comply with USACE levee design guidance, including vegetation on levees, or applying for variance during PED and Construction. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 18:12 | 0 | 7687 | Miranda | Peters | 299 | 299 | 0 | 0 | 0
9 | PLE-9 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Analytical Error: Economics | Info and Data Analysis | 1 | Vertical team opposition to economic justification without HEC-FDA. Study delay in responding to review comments and incorporating HEC-FDA later in the study process. TotalRisk is new software anticipated to be certified in 2023 and therefore additional review comments are anticipated to be generated due to the use of new software. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | Risk resolved - The study team plans to utilize both HEC-FDA and TotalRisk. |  |  | 15 | Planning - Economics | PLE | 5615 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 18:18 | 0 | 7687 | Miranda | Peters | 299 | 299 | 1 | 1 | 1
10 | PLE-10 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Analytical Error: Economic Justification | Agency Policy and Process | 7 | Vertical team opposition to economic justification without HEC-FDA. TotalRisk is new software anticipated to be certified in 2023 and therefore additional review comments are anticipated to be generated due to the use of new software. Study delay in responding to review comments and incorporating HEC-FDA later in the study process. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | Risk resolved - The study team plans to utilize both HEC-FDA and TotalRisk. Unlikely since the PDT will be focused on selecting a plan that will comply with USACE levee design guidance, including vegetation on levees, or applying for variance during PED and Construction. |  |  | 15 | Planning - Economics | PLE | 5615 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 | Risk resolved - The study team plans to utilize both HEC-FDA and TotalRisk. | 0 | 0 | 0 |  | 0 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 18:26 | 0 | 7687 | Miranda | Peters | 299 | 299 | 1 | 1 | 1
11 | PLE-11 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Identification of suitable habitat mitigation sites | Site Conditions | 6 | Identifying habitat mitigation sites has been challenging due to limited opportunities for suitable mitigation sites in the region and the need for a potentially large amount of habitat mitigation. The risk is that not enough habitat mitigation sites would be identified which could stall resource agency support for the project and delay implementation. | 3 | Likely | Likely (50% to 70%) | Medium risk carried forward with recommended COA 3. Delay in study completion due to identification of suitable mitigation sites for impacts from proposed FRM project features. |  |  | 16 | Planning - Environmental | PLE | 8753 |  | 2 | Environmental | Minimal if any impact to schedule/cost/performance since a mitigation strategy is being implemented. | 5 | 2 | 0 | 0 | 0 |  | 0 | 30 | 0 | The risk is that not enough habitat mitigation sites would be identified which could stall resource agency support for the project and delay implementation. | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-27 15:39 | 0 | 7687 | Miranda | Peters | 299 | 299 | 0 | 0 | 0
12 | EHH-12 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Inland Hydrology | Info and Data Analysis | 1 | Inland Hydrology is expected to change over the life of this project. The State of CA has done some analysis but it is not in alignment with the USACE guidance on this data process. The Sea Level and H&H COP do not currently have guidance for an acceptable method to account for inland hydrology change. Due to this the team is running a sensitivity analysis on the data, based on the information that the State has gathered to see if the proposed project will be resilient to future changes in inland hydrology. This is included in the current scope and this risk has been partially mitigated through scoping. | 2 | Unlikely | Unlikely (30% to 50%) | We are already seeing changes impacts to the hydrology in the Central Valley due to climate change. With more extreme weather, atmospheric rivers, and changes in the elevation of the snowpack, we are expecting to have a significant increase in the amount of flow that enters the river system. The likelihood that additional analysis beyond the sensitivity analysis is required to determine the TSP is low. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8752 |  | 1 | Asset Condition | If we missed the mark on inland climate change and flows are greater than expected then the risk to the project, community, environment, and agency reputation could be huge. We have been approved for an extension to mitigate to try and account for this but any change to policy could upgrade this to a major problem. | 5 | 2 | 0 | 200000 | 1000000 | Depending on how it is eventually decided how to address inland climate change, this could add a significant cost if guidance is published prior to the completion of the project. The current guidance only requires a qualitative analysis, which is the lowest cost provided. The current plan of doing a sensitivity analysis to make sure the project will have future resilience is the most likely cost and that is already accounted for in the current scope. If USACE guidance is developed prior to project completion, the project may have to consider developing new hydrology, hydraulics, FDA analysis, risk, and likely alternative selection, which is what the highest value is accounting for. | 0 | 180 | 770 | Only going by guidance of qualitative analysis, results in no expected project delays. The most likely scenario of doing the sensitivity analysis is already included in the current scope and results in no delay. If the USACE guidance is revised with a method to quantitatively analyze inland climate change, then that would add 2 years to the project schedule. | 3 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-08 14:01 | 0 | 8752 | Morgan | Marlatt | 302 | 302 | 0 | 0 | 0
1 | PLP-1 | 3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 488589 | Wrong selection of plan | Info and Data Analysis | 1 | Multiple water resources projects within study boundary would potentially have interaction with the C&SF Flood Resiliency Study and could lead to have multiple Future Without Projects at some point of the planning process. This could potentially lead the team to select the wrong TSP. | 3 | Likely | Likely (50% to 70%) | There is a possibility for the team to select the wrong Plan |  |  | 13 | Planning - Plan Formulation | PLP | 6246 |  | 7 | Agency Reputational | If another round of alternatives is needed, might impact trust with the stakeholders | 10 | 3 | 200000 | 0 | 600000 | Approximate range of how much funding might be required to incorporate another round of alternatives in other studies | 30 | 0 | 90 | Approximate range of how much time might be required to incorporate another round of alternatives in other studies | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 18:10 | 0 | 6246 | Zulamet | Vega-Liriano | 306 | 306 | 0 | 0 | 0
4 | EHH-4 | 3531 | Lower Missouri Brunswick L-246 | 496631 | Construction of Federal or Local Projects | Site Conditions | 6 | Construction or alteration to levees, reservoirs, bridges, and other projects can contribute to altered hydraulics. For example, nonfed levee raises increase water surface elevations and are likely to raise stages more frequently, loading L246 and Brunswick more frequently. Not accounting for these future raises, construction projects, etc. means that changes in hydrology and hydraulics are not accounted for. | 2 | Unlikely | Unlikely (30% to 50%) | It is likely that the nonfed levees have been raised since the 2019 flood and were not captured in recent LiDAR surveys. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 5436 |  | 5 | Other | This risk is a minor problem and, if addressed, would provide improvement. If not addressed, all alternatives will still be compared to the same conditions. If addressed, then the selection of the recommended plan will be based of off the most up to date conditions. | 5 | 2 | 0 | 20000 | 0 | Including updated information related to nearby projects would require reanalysis of the hydraulic modeling effort. Potential cost depends on when the data comes available in the planning process and how much hydraulic reanalysis would have to occur. | 0 | 15 | 0 | Additional time would be required to update the hydraulic model with updated conditions. Additionally, the alternative models would need to be rerun. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-03 17:55 | 0 | 4830 | Erin | Reinkemeyer | 299 | 299 | 0 | 0 | 0
5 | ECV-5 | 3531 | Lower Missouri Brunswick L-246 | 496631 | Test Risk entered by developer | Agency Policy and Process | 7 | Test risk entered by developer Hardee Mahoney | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 9 | Engineering - Civil | ECV | 8774 |  | 5 | Other |  | 5 | 0 | 0 | 500 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-03 16:17 | 0 | 8774 | Hardee | Mahoney | 299 | 299 | 1 | 0 | 1
5 | ECV-5 | 3531 | Lower Missouri Brunswick L-246 | 496631 | Test Risk entered by developer | Agency Policy and Process | 7 | Test risk entered by developer Hardee Mahoney | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 9 | Engineering - Civil | ECV | 8774 |  | 5 | Other |  | 5 | 0 | 0 | 500 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-03 16:17 | 0 | 8774 | William | Mahoney | 299 | 299 | 1 | 0 | 1
1 | EPE-1 | 3544 | Test A Project | 000000 | TEST risk 1 | Contract Acquisition | 3 | description | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 21 | Construction - Project Engineer | EPE | 2331 |  | 8 | Agency Strategy |  | 5 | 2 | 5 | 0 | 15 |  | 5 | 0 | 15 |  | 2 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-30 15:46 | 0 | 138 | Erin | Rooks | 306 | 306 | 0 | 0 | 0
2 | OPS-2 | 3544 | Test A Project | 000000 | Test Risk 2 | Legal or Regulatory Actions | 10 |  | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 11 | Operations | OPS | 8653 |  | 6 | Compliance |  | 5 | 2 | 1 | 0 | 100000 |  | 0 | 33 | 0 |  | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-01-19 22:19 | 0 | 8653 | Brad | Firlie | 306 | 299 | 0 | 0 | 0
3 | PLP-3 | 3544 | Test A Project | 000000 | 11 | Legal or Regulatory Actions | 10 |  | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 8653 |  | 5 | Other | 11 | 5 | 2 | 11 | 11 | 12 | 1 | 1 | 2 | 3 |  | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-01-19 22:25 | 0 | 8653 | Brad | Firlie | 299 | 302 | 0 | 0 | 0
4 | EEL-4 | 3544 | Test A Project | 000000 | Test 002 | Contract Performance | 4 | Short desc | 3 | Likely | Likely (50% to 70%) |  |  |  | 7 | Engineering - Electrical | EEL | 8653 |  | 1 | Asset Condition |  | 5 | 2 | 400000 | 0 | 950000 | None | 0 | 20 | 0 |  | 2 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-01-24 13:49 | 0 | 8775 |  |  | 306 | 299 | 0 | 0 | 0
5 | PLC-5 | 3544 | Test A Project | 000000 | Risk Test 0854 | Stakeholder, Sponsor or Partners | 9 |  | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 14 | Planning - Cultural Resources | PLC | 8653 |  | 6 | Compliance |  | 5 | 2 | 500000 | 800000 | 800000 |  | 0 | 100 | 0 |  | 2 | 7 | 7 | Inactive - Decision Made | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-03-23 19:36 | 0 | 138 | Erin | Rooks | 306 | 299 | 0 | 0 | 0
6 | PLC-6 | 3544 | Test A Project | 000000 | Test 24 Jan 2023 0909 | Agency Policy and Process | 7 | aen;vinaiovnain afan eif'ju39 urh98yyu[[- j'co | 1 | Very Unlikely | Very Unlikely (5% to 30%) | 4 u[94d[9yu09t2j[9g=0-]v |  |  | 14 | Planning - Cultural Resources | PLC | 1 | William Blake | 3 | Human Health and Safety |  | 5 | 2 | 0 | 50 | 0 |  | 0 | 800 | 0 |  | 4 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-01-24 14:11 | 0 | 138 | Erin | Rooks | 299 | 299 | 0 | 0 | 0
7 | OPS-7 | 3544 | Test A Project | 000000 | risk a | Contract Performance | 4 | writing description here | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 11 | Operations | OPS | 8653 |  | 6 | Compliance |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 350 | 0 | writing evidence here | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-01-31 19:42 | 0 | 138 | Erin | Rooks | 299 | 299 | 0 | 0 | 0
8 | OTH-8 | 3544 | Test A Project | 000000 | Test Save Measure | Site Conditions | 6 | Test Save Measure | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 12 | Other | OTH | 8653 |  | 1 | Asset Condition |  | 5 | 2 | 0 | 100000 | 0 |  | 20 | 0 | 60 |  | 2 | 1 | 1 | Active | 6 | Construction | 17 | 17 | Notice to Proceed | 2023-05-25 13:33 | 0 | 8775 |  |  | 299 | 306 | 0 | 0 | 0
9 | EHH-9 | 3544 | Test A Project | 000000 | abc | Legal or Regulatory Actions | 10 |  | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 486 |  | 5 | Other |  | 5 | 2 | 0 | 50 | 0 |  | 0 | 5 | 0 |  | 2 | 1 | 1 | Active | 6 | Construction | 18 | 18 | Construction Start Date | 2023-02-27 15:41 | 0 | 138 | Erin | Rooks | 299 | 299 | 0 | 0 | 0
10 | SAF-10 | 3544 | Test A Project | 000000 | 3/6 Test | Legal or Regulatory Actions | 10 |  | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 24 | Safety | SAF | 486 |  | 5 | Other |  | 10 | 2 | 0 | 100000 | 0 |  | 0 | 100 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-07 14:59 | 0 | 8775 |  |  | 299 | 299 | 0 | 0 | 0
11 | COM-11 | 3544 | Test A Project | 000000 | ABC TEST risk | Communications | 2 | description | 3 | Likely | Likely (50% to 70%) |  |  |  | 20 | Public Affairs | COM | 8653 |  | 5 | Other |  | 10 | 3 | 0 | 5000 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 18 | 18 | Construction Start Date | 2023-03-20 14:26 | 0 | 138 | Erin | Rooks | 299 | 299 | 0 | 0 | 1
12 | EEL-12 | 3544 | Test A Project | 000000 | test risk | Info and Data Analysis | 1 | description | 3 | Likely | Likely (50% to 70%) |  |  |  | 7 | Engineering - Electrical | EEL | 138 |  | 3 | Human Health and Safety |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 50 | 0 |  | 2 | 1 | 1 | Active | 6 | Construction | 18 | 18 | Construction Start Date | 2023-04-17 14:39 | 0 | 138 | Erin | Rooks | 299 | 299 | 0 | 0 | 0
13 | EEL-13 | 3544 | Test A Project | 000000 | short desription | Communications | 2 |  | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 7 | Engineering - Electrical | EEL | 1 | William Blake | 2 | Environmental |  | 5 | 2 | 0 | 5000 | 0 |  | 0 | 5 | 15 |  | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 8 | 8 | Design Start | 2023-03-30 15:41 | 0 | 138 | Erin | Rooks | 299 | 302 | 0 | 0 | 0
14 | PLE-14 | 3544 | Test A Project | 000000 | ABC | Contract Performance | 4 | afeae | 2 | Unlikely | Unlikely (30% to 50%) | add later |  |  | 15 | Planning - Economics | PLE | 2687 |  | 2 | Environmental |  | 10 | 3 | 0 | 0 | 50 | gsrr | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 17 | 17 | Notice to Proceed | 2023-04-17 13:44 | 0 | 138 | Erin | Rooks | 306 | 299 | 0 | 0 | 1
15 | EGT-15 | 3544 | Test A Project | 000000 | Limited geotechnical investigation, limited data | Info and Data Analysis | 1 | Different site conditions that could lead to increased costs, schedule, poor performance of infrastructure being built | 3 | Likely | Likely (50% to 70%) | large levees over large geographical areas likely have different site conditions |  |  | 3 | Engineering - Geotechnical | EGT | 1944 |  | 4 | Operations |  | 10 | 3 | 0 | 500000 | 0 |  | 0 | 180 | 0 |  | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-04-17 14:38 | 0 | 138 | Erin | Rooks | 299 | 299 | 0 | 0 | 0
16 | PRM-16 | 3544 | Test A Project | 000000 | Test risk | Stakeholder, Sponsor or Partners | 9 | description | 3 | Likely | Likely (50% to 70%) |  |  |  | 17 | Project Management | PRM | 2687 |  | 5 | Other |  | 5 | 2 | 5000 | 7500 | 10000 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-05-19 14:28 | 0 | 138 | Erin | Rooks | 302 | 302 | 0 | 0 | 1
17 | EPE-17 | 3544 | Test A Project | 000000 | Add new risk | Legal or Regulatory Actions | 10 | description | 3 | Likely | Likely (50% to 70%) | narrative |  |  | 21 | Construction - Project Engineer | EPE | 138 |  | 2 | Environmental |  | 10 | 3 | 24999 | 50000 | 75000 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 18 | 18 | Construction Start Date | 2023-05-25 13:27 | 0 | 138 | Erin | Rooks | 302 | 302 | 0 | 0 | 1
18 | EGT-18 | 3544 | Test A Project | 000000 | test333 | Info and Data Analysis | 1 | asdf | 2 | Unlikely | Unlikely (30% to 50%) | asdf asdfa asdf |  |  | 3 | Engineering - Geotechnical | EGT | 8653 |  | 1 | Asset Condition | asdf | 5 | 2 | 0 | 10000000 | 10000000000 | asdf | 0 | 300 | 500 | asdf | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-05-31 21:52 | 0 | 9033 | Chris | Dixon | 302 | 302 | 0 | 0 | 0
19 | OPS-19 | 3544 | Test A Project | 000000 | Test 26 June 2023 | Legislative or Political | 8 | Test description | 4 | Very Likely | Very Likely (70% to 90%) |  |  |  | 11 | Operations | OPS | 138 |  | 2 | Environmental |  | 10 | 4 | 0 | 50 | 400 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-06-26 16:55 | 0 | 138 | Erin | Rooks | 302 | 299 | 0 | 0 | 1
1 | EAI-1 | 3545 |  |  | Shoreline placement of Rindge Dam impounded sediment mostly | Communications | 2 | Although the July 2016 field surveys did not identify surfgrass subtidally east of the pier, they could not be certain of that determination for the area less than 10-feet MLLW since the survey vessel could not obtain video in the shallow depths. Subsequently, the sponsor, through visual surveys during low tide, confirmed surfgrass presence in small patches in a boulder field immediately downcoast of the Malibu Pier placement site. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | Proximity immediately downcoast of placement location |  |  | 8 | Engineering - Architectural and Interior | EAI | 2331 |  | 5 | Other |  | 5 | 2 | 0 | 5000 | 0 | 1. Halts shoreline placement of mostly sands. 2. Requires reformulation of placement strategy. 3. May require out of kind mitigation, including artificial reef construction with kelp planting. | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-01-24 14:11 | 0 | 2331 | Hamna | Zaheer | 299 | 299 | 0 | 0 | 0
1 | PLC-1 | 3552 |  |  | Poor Planning Decision | Communications | 2 | Identify and rank study priorities. Develop study objectives based on these priorities. | 2 | Unlikely | Unlikely (30% to 50%) | Alternatives have been formulated to specifically address the highest study priorities. |  |  | 14 | Planning - Cultural Resources | PLC | 2331 |  | 5 | Other | If study priorities are not accurately identified, the recommended plan may not address the most severe biological needs of the system. | 10 | 3 | 0 | 5000 | 0 | Study priorities are misidentified or ranked improperly. | 50 | 0 | 100 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-01-24 13:23 | 0 | 2331 | Hamna | Zaheer | 299 | 306 | 0 | 0 | 0
3 | ECV-3 | 3552 |  |  | Commodity growth rate projections and fleet forecast needed | Info and Data Analysis | 1 | If future commodity or fleet projections are changed after modeling effort is complete, large schedule delays will occur because portion of modeling will need to be redone | 3 | Likely | Likely (50% to 70%) | The commodity growths rates drive the number of TEUs coming to the local ports, therefore, the number of vessels. Any change to the forecast would cause additional analysis and model runs. |  |  | 9 | Engineering - Civil | ECV | 2331 |  | 5 | Other | Vertical team acceptance of Commodity Growth rate projections & future fleet forecast Make no updates in the future. Conduct Sensitivity Analysis at this point on the Commodity growth rates. | 10 | 3 | 0 | 5000 | 0 |  | 0 | 50 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-01-24 13:56 | 0 | 2331 | Hamna | Zaheer | 299 | 299 | 0 | 0 | 0
1 | EPE-1 | 3554 |  |  | Climate change are uncertain and could construction | Info and Data Analysis | 1 | description | 4 | Very Likely | Very Likely (70% to 90%) |  |  |  | 21 | Construction - Project Engineer | EPE | 8692 |  | 7 | Agency Reputational |  | 5 | 2 | 0 | 50000 | 0 |  | 100 | 200 | 200 |  | 4 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-01-25 20:35 | 0 | 138 | Erin | Rooks | 299 | 306 | 0 | 0 | 0
1 | PLP-1 | 3555 | St. Augustine Back Bay CSRM | 479265 | 3x3x3 Scope, Schedule, and Budget | Agency Policy and Process | 7 | Due to the scope, and size and complexity of the study area, there is a risk to the study schedule and budget, and study may not reach a Chief's Report within 3-years of signing of the FCSA. | 5 | Extremely Likely | Extremely Likely (90% to 100%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 4614 |  | 8 | Agency Strategy | Project will not be 3x3 compliant | 10 | 4 | 0 | 3000000 | 0 |  | 0 | 1095 | 1095 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-26 16:07 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
2 | PLC-2 | 3555 | St. Augustine Back Bay CSRM | 479265 | Cultural Resources Surveys | Info and Data Analysis | 1 | Cultural resources surveys will be needed depending on location and potential measures, | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 14 | Planning - Cultural Resources | PLC | 8781 |  | 5 | Other | If surveys are not completed, project design would have to be changed to mitigate potential impacts to existing cultural resources, resulting in increased budget and time delays | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 15:32 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
3 | PLE-3 | 3555 | St. Augustine Back Bay CSRM | 479265 | Environmental Surveys - Wetlands | Info and Data Analysis | 1 | Development of mitigation plan dependent on surveys to determine absence/presence and condition of existing wetlands. Survey spatial extent is dependent on TSP footprint. | 4 | Very Likely | Very Likely (70% to 90%) | Existing knowledge of wetland presence within the study area |  |  | 16 | Planning - Environmental | PLE | 7848 |  | 5 | Other | Potential impacts to environmental resources, changes to project design would be needed to mitigate impacts, resulting in increased budget and time delays | 5 | 2 | 0 | 0 | 0 | This item is included in the study budget | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-04 19:49 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 1 | 1
4 | PLP-4 | 3555 | St. Augustine Back Bay CSRM | 479265 | Future Development | Site Conditions | 6 | Assume all redevelopment is up to new standards | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 390 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 15:42 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
5 | PLP-5 | 3555 | St. Augustine Back Bay CSRM | 479265 | Existing Local Measures | Site Conditions | 6 | Degradation of existing seawalls | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 390 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 15:43 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
6 | RLE-6 | 3555 | St. Augustine Back Bay CSRM | 479265 | Real Estate Requirements | Stakeholder, Sponsor or Partners | 9 | Public participation and acceptance of required standard estates. The number of stakeholders and property owners in the study area footprint is significant. Some private lands will likely be required for the project. Any real estate that can't be acquired without going to court could negatively impact the acquisition schedule. | 3 | Likely | Likely (50% to 70%) |  |  |  | 18 | Real Estate | RLE | 8817 |  | 5 | Other |  | 10 | 3 | 0 | 1 | 0 |  | 0 | 126 | 253 |  | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-04-26 16:05 | 0 | 4614 | Katherine | Bailey | 299 | 306 | 0 | 0 | 0
7 | OTH-7 | 3555 | St. Augustine Back Bay CSRM | 479265 | Inlet surge barrier alternative modeling | Info and Data Analysis | 1 | May need additional/high fidelity modeling for design of inlet closure alternatives | 2 | Unlikely | Unlikely (30% to 50%) | PDT can make well-informed assumptions on how inlet closure alternatives will perform based on existing models, subject to concurrence from vertical team |  |  | 12 | Other | OTH | 390 |  | 5 | Other | Utilizing the high fidelity models would provide minor improvement to understanding of inlet closure alternatives | -5 | 1 | 50000 | 0 | 100000 |  | 0 | 365 | 365 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-26 15:50 | 0 | 4614 | Katherine | Bailey | 306 | 299 | 0 | 0 | 0
8 | PLP-8 | 3555 | St. Augustine Back Bay CSRM | 479265 | Non-NED recommendation | Stakeholder, Sponsor or Partners | 9 | Tentatively Selected Plan identified is not the NED plan | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 390 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-20 19:44 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
9 | ECV-9 | 3555 | St. Augustine Back Bay CSRM | 479265 | Changes in Engineering Modeling Scope | Info and Data Analysis | 1 | The schedule and budget have been created prior to the Initial Flood Driver Screening for the study area results. These results will inform the path forward for addressing compound flood hazards (surge, rainfall, riverine with tides and SLC) or a more simplistic approach addressing surge with tides and SLC. The scope and budget have been created assuming the most complex modeling scenario. | 3 | Likely | Likely (50% to 70%) |  |  |  | 9 | Engineering - Civil | ECV | 8814 |  | 5 | Other | The non-Federal sponsor has voiced concern regarding flood risk from rainfall and riverine sources. The team should work with the non-Federal sponsor for buy in of the surge with tide and SLC approach for cohesion moving forward. | 5 | 2 | -100000 | -50000 | 0 | This reduction in the modeling scope would reduced the schedule and budget of the study. | -255 | 0 | 0 | This reduction in the modeling scope would reduced the schedule and budget of the study. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-23 12:26 | 0 | 8814 | Michelle | Vieira | 306 | 306 | 0 | 0 | 0
11 | PLP-11 | 3555 | St. Augustine Back Bay CSRM | 479265 | Update to WRDA 2022 Implementation Guidance | Info and Data Analysis | 1 | The publication of WRDA 2022 implementation guidance could cause the study to change the engineering and economic modeling approach. "WRDA 2022 S8106 would allow for study scopes to expand in two ways: (1) expand coastal storm and inland flood feasibility studies to incorporate other flood risk (e.g., due to erosion, tides, rainfall, subsidence, groundwater emergence), and (2) expand feasibility studies to include water supply, water conservation, and measures to reduce water resource impacts of extreme weather events, including drought." https://www.usace.army.mil/Missions/Civil-Works/Project-Planning/Legislative-Links/WRDA-2022/ | 3 | Likely | Likely (50% to 70%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 390 |  | 5 | Other |  | 10 | 3 | 0 | 0 | 500000 | Publication of implementation guidance could effect engineering and economic modeling, scope, schedule, and budget. | 0 | 0 | 365 | Publication of implementation guidance could effect engineering and economic modeling, scope, schedule, and budget. | 3 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-26 16:08 | 0 | 8814 | Michelle | Vieira | 306 | 306 | 0 | 0 | 0
12 | PLE-12 | 3555 | St. Augustine Back Bay CSRM | 479265 | Risk Reduction and Economic Benefits Beyond Study Area | Info and Data Analysis | 1 | Due to the nature of the City of St. Augustine municipal boundary and the surrounding water bodies, it is likely that risk reduction and economic benefits will occur outside of the study area (dependent on PSE). | 4 | Very Likely | Very Likely (70% to 90%) |  |  |  | 15 | Planning - Economics | PLE | 162 |  | 5 | Other | It will be imperative to the study to understand the total benefits to the the study area and surrounding areas to accurately capture a BCR. This may also include using best engineering judgement to determine benefit extends (PSE of a surge barrier for example) without high fidelity modeling. | -10 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-23 13:11 | 0 | 8814 | Michelle | Vieira | 299 | 299 | 0 | 1 | 1
13 | PLE-13 | 3555 | St. Augustine Back Bay CSRM | 479265 | CBRA Compliance | Agency Policy and Process | 7 | The USFWS may not consider several alternatives to be compliant with the Coastal Barrier Resource Act (CBRA). There are two CBRA system units within the study area. | 3 | Likely | Likely (50% to 70%) |  |  |  | 16 | Planning - Environmental | PLE | 390 |  | 8 | Agency Strategy |  | 10 | 3 | 50000 | 100000 | 150000 |  | 90 | 180 | 270 |  | 3 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-20 12:38 | 0 | 390 | Martin | Durkin | 302 | 302 | 0 | 0 | 0
14 | PRM-14 | 3555 | St. Augustine Back Bay CSRM | 479265 | PDT Workload & Turnover | Resource Availability | 5 | PDT workload on other projects and turnover of key PDT members over the course of the study could impact schedule and budget. | 3 | Likely | Likely (50% to 70%) |  |  |  | 17 | Project Management | PRM | 8994 |  | 5 | Other |  | 5 | 2 | 50000 | 100000 | 150000 |  | 90 | 180 | 365 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-20 12:42 | 0 | 390 | Martin | Durkin | 302 | 302 | 0 | 0 | 0
15 | EHH-15 | 3555 | St. Augustine Back Bay CSRM | 479265 | Interior Drainage | Info and Data Analysis | 1 | Uncertainty of impacts of alternatives to interior drainage systems, and adjustments that may be necessary to incorporate | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8814 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-04-26 15:20 | 0 | 4614 | Katherine | Bailey | 299 | 299 | 0 | 0 | 0
16 | PLE-16 | 3555 | St. Augustine Back Bay CSRM | 479265 | Possibility of having no NED justified plan | Agency Policy and Process | 7 | If alternative accounts' benefits are not apparent team recommendation will be study termination. | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 15 | Planning - Economics | PLE | 162 |  | 8 | Agency Strategy |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-26 19:45 | 0 | 162 | Vongmony | Var | 299 | 299 | 0 | 1 | 1
17 | PLE-17 | 3555 | St. Augustine Back Bay CSRM | 479265 | Identification of economic study area. | Info and Data Analysis | 1 | Structures not included in the inventory could incur damage. | 2 | Unlikely | Unlikely (30% to 50%) | If a structure should be included in the inventory, the damage to the structure should not be significant. |  |  | 15 | Planning - Economics | PLE | 162 |  | 8 | Agency Strategy | If additional structures not in the inventory would incur damage, the damage would likely be insignificant. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-26 19:57 | 0 | 162 | Vongmony | Var | 299 | 299 | 0 | 0 | 0
1 | PLP-1 | 3571 | Boston Metropolitan Area, MA |  | Large complex study area | Info and Data Analysis | 1 | Large coastal flood risk area to evaluate and develop strategies to reduce risk. Coastline length, entire study area: 266 miles. Flow paths impact multiple communities. | 2 | Unlikely | Unlikely (30% to 50%) | Study takes longer than anticipated. |  |  | 13 | Planning - Plan Formulation | PLP | 249 |  | 5 | Other |  | 5 | 0 | 0 | 250000 | 0 | Professional judgment. | 0 | 180 | 0 | Professional judgment | 3 | 1 | 1 | Active | 3 | Planning | 26 | 26 | Shared Vision | 2023-06-20 22:13 | 0 | 249 | Barbara | Blumeris | 299 | 299 | 1 | 0 | 0
2 | EHH-2 | 3571 | Boston Metropolitan Area, MA |  | Sea Level Change | Info and Data Analysis | 1 | Uncertainty in the rate at which sea level change will occur. | 3 | Likely | Likely (50% to 70%) | SLC rates |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 249 |  | 8 | Agency Strategy | Study will look at different amounts of SLC. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 3 | Planning | 27 | 27 | Recommendation | 2023-06-20 22:23 | 0 | 249 | Barbara | Blumeris | 299 | 299 | 0 | 1 | 1
3 | PLE-3 | 3571 | Boston Metropolitan Area, MA |  | Benefit Calculation | Info and Data Analysis | 1 | large study area, reliance on NSI, may introduce error, | 2 | Unlikely | Unlikely (30% to 50%) | In Segment 2 conduct studies to verify NSI data for watershed scale study. |  |  | 15 | Planning - Economics | PLE | 8274 |  | 1 | Asset Condition | Minor as watershed study, guidance indicated acceptable to rely on exiting information., | 5 | 2 | 0 | 50000 | 0 | professional judgment | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 3 | Planning | 27 | 27 | Recommendation | 2023-06-20 22:31 | 0 | 249 | Barbara | Blumeris | 299 | 299 | 0 | 0 | 1
4 | PLP-4 | 3571 | Boston Metropolitan Area, MA |  | Stakeholder buy-in | Stakeholder, Sponsor or Partners | 9 | Stakeholder buy in as stakeholder points of view may vary. | 2 | Unlikely | Unlikely (30% to 50%) | Outreach conducted for the shared Vision milestone |  |  | 13 | Planning - Plan Formulation | PLP | 249 |  | 5 | Other | May need to extend schedule to achieve buy-in on strategies to reduce coastal flood risk. | 5 | 2 | 0 | 0 | 0 |  | 0 | 100 | 0 | may take longer than scheduled to reach consensus in the regional plan | 2 | 1 | 1 | Active | 3 | Planning | 27 | 27 | Recommendation | 2023-06-20 22:59 | 0 | 249 | Barbara | Blumeris | 299 | 299 | 0 | 1 | 0
5 | PLP-5 | 3571 | Boston Metropolitan Area, MA |  | Study will rely on concept level design | Info and Data Analysis | 1 | Study will rely on concept level design of strategy features at the 10 to 30 percnet design level, introduces uncertainty in effectivness and feasibility of propsed strategies | 2 | Unlikely | Unlikely (30% to 50%) | Design level to be perfomed for study known to participants. |  |  | 13 | Planning - Plan Formulation | PLP | 249 |  | 5 | Other | Level of design of meausres may create minor problems in developing strategies. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 3 | Planning | 27 | 27 | Recommendation | 2023-06-20 22:49 | 0 | 249 | Barbara | Blumeris | 299 | 299 | 0 | 0 | 1
6 | PLP-6 | 3571 | Boston Metropolitan Area, MA |  | Political Priorties at Fedeal, State and local levels | Stakeholder, Sponsor or Partners | 9 | Political Priorties at Fedeal, State and local levels may vary and change over time. | 3 | Likely | Likely (50% to 70%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 249 |  | 5 | Other | Varying priorites across jurisdictions, Federal. State, local will need to be recognized in development of the regional plan. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 3 | Planning | 27 | 27 | Recommendation | 2023-06-20 22:56 | 0 | 249 | Barbara | Blumeris | 299 | 299 | 0 | 1 | 1
4 | EHH-4 | 3572 | City of Boston Coastal Storm Risk |  | Inaccurate Floodplain for Formulation and Economic Analysis | Info and Data Analysis | 1 | NACCS uses save points throughout Boston Harbor and interpolates those data points across the terrain showing a 1D result of where the water ends up and incorporates SLC at the first year and the last year in the G2CRM planning model. Will the model provide accurate depiction of the floodplain extents and flood pathway entry point for formulation and economic analysis? | 3 | Likely | Likely (50% to 70%) | Without specific refinement, and updating the storm suite, it is likely that the model will not accurately reflect extra-tropical events, nor will it have the refined mesh to depict an accurate floodplain over a 100-year planning horizon. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 5 | Other | An inaccurate floodplain could result in reformulation; significant redesign; post-authorization in the future. | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-24 14:18 | 0 | 4490 | Jeffrey | Herzog | 299 | 299 | 0 | 1 | 1
5 | PLE-5 | 3572 | City of Boston Coastal Storm Risk |  | ECONOMIC DAMAGES IN THE FUTURE WITHOUT PROJECT CONDITION | Info and Data Analysis | 1 |  | 3 | Likely | Likely (50% to 70%) |  |  |  | 15 | Planning - Economics | PLE | 2495 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-29 15:03 | 0 | 4490 | Jeffrey | Herzog | 299 | 299 | 0 | 1 | 1
6 | EHH-6 | 3572 | City of Boston Coastal Storm Risk |  | Climate Change Impacts to Floodplain | Info and Data Analysis | 1 | In a dense urban environment with significant tide swings (+9 feet) differences between water surface elevations and floodplains within each curve are significant. Over a 50-year period of economic analysis and a 100-year planning horizon, the impacts of SLC in the study area are also significantly different. The impacts can influence comprehensive benefits analysis; critical resource impacts; as well as impacts to natural resources. | 4 | Very Likely | Very Likely (70% to 90%) | There is a significant difference in preliminary curves at the low/intermediate/ and High SLC scenarios. It is likely that the formulation will change depending on the accuracy of the FWOP floodplain at both the 50-year and 100-year horizons. 50-year for quantitative analysis and 100-year for qualitative analysis. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 3 | Human Health and Safety | Depending on the model setup conditions and input criteria, the floodplains could understate the risk while still being policy compliant. | 10 | 4 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 18:52 | 0 | 4490 | Jeffrey | Herzog | 299 | 299 | 0 | 1 | 1
7 | PLE-7 | 3572 | City of Boston Coastal Storm Risk |  | Programmatic Agreement (Sec. 106) | Legal or Regulatory Actions | 10 | Depending on the alternatives selected, the entire study area is full of historic properties and potential archeological artifacts as well as National Historic Landmarks and significant historic and cultural landscapes. Historic, architectural and archaeological assessments and surveys will likely be required as the study progresses. If areas such as the Naval Shipyard and historic wharfs are identified for significant construction, significant surveys, i.e. in-water surveys may be required prior to the PA being signed. Offshore work would also require remote sensing archaeological surveys depending upon the location and the proposed alternative. | 2 | Unlikely | Unlikely (30% to 50%) | There is a study cost increase risk if in-water surveys are required prior to executing the PA. Additionally, historic properties assessments and archaeological surveys, both on shore or in water, may be required for specific alternatives identified leading to the TSP. Depending the upon the significance of the historic property or landscape, this could result in additional costs and possible scope modifications either during the FS or PED. |  |  | 16 | Planning - Environmental | PLE | 4490 |  | 5 | Other | If invasive or detailed surveys become required to complete a PA on the Study it will create potential cost and schedule delays. | 10 | 3 | 0 | 300000 | 0 | An initial historic and archaeological assessment of the project study area will be required during the FS to identify historic properties. This assessment will help inform development of the Section 106 PA which will need to be coordinated and executed once the TSP is identified and by the end of the FS. | 0 | 180 | 0 | If in-water surveys would require AE Contracting and remote sensing equipment. | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-01-30 16:59 | 0 | 4490 | Jeffrey | Herzog | 299 | 299 | 0 | 0 | 0
8 | RLE-8 | 3572 | City of Boston Coastal Storm Risk |  | Acquisition of Real Estate | Stakeholder, Sponsor or Partners | 9 | The number of stakeholders and property owners in the study area footprint is significant. Many areas that will require structural measures are not publicly owned by the City of Boston. Other areas may be identified for managed retreat or buyout as the recommended plan. They are either private or under the control of a different public entity. In order to construct or implement, there may be a significant real estate undertaking; any real estate that can't be acquired could impact the effectiveness of the plan, potentially causing a redesign. | 3 | Likely | Likely (50% to 70%) | A redesign post authorization will potentially impact the authorized project, the cost, or the environmental impacts. |  |  | 18 | Real Estate | RLE | 4490 |  | 5 | Other |  | 5 | 2 | 0 | 500000 | 0 | If a redesign is necessary due to real estate acquisition issues it will require both Engineering and NEPA work. | 0 | 270 | 0 | To develop an EDR and potentially a Supplemental NEPA Document post authorization. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 15 | 15 | BCOES Certification | 2023-01-31 16:46 | 0 | 4490 | Jeffrey | Herzog | 299 | 299 | 0 | 0 | 0
10 | PLP-10 | 3572 | City of Boston Coastal Storm Risk |  | Plan Formulation to SLC Curves | Info and Data Analysis | 1 | USACE CSRM Studies incorporate sea level change into formulation. Policy directs formulation to USACE Curves, the high, intermediate and low scenarios. Teams traditionally formulate to all three curves, or they formulate to the intermediate curve and run sensitivity on the other two. Formulating to the low curve in a study area such as Boston could significantly understate risk; formulating to the high curve could overstate risk and remove opportunities for softer, adaptable solutions. | 4 | Very Likely | Very Likely (70% to 90%) | Formulating for SLC is not an exact science and it is driven by the conditions of the study area, outputs of the model, as well as critical thresholds. Without risk management, it is very likely the team will formulate to the intermediate curve, because it's often been confused as the accepted practice and risk would be understated in the study area. |  |  | 13 | Planning - Plan Formulation | PLP | 4490 |  | 6 | Compliance | If the study team, inlcuding the sponsor, recommends a plan based on the High SLC scenario, but the PL&C team recommends the Intermediate SLC scenario based on uncertainty it could be a major problem. The result could be either reformulation, or a need for an LPP/NED exception to go with the High SLC scenario. | 10 | 3 | 0 | 0 | 0 |  | 0 | 60 | 180 | It is likely there will be some discussion with the ATR and PL&C Team as to which curve is proper, why, and what is driving the decision. When considering the number and level of reviews, it is anticipated and built into the study schedule for 60 days. | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-01 19:07 | 0 | 4490 | Jeffrey | Herzog | 299 | 302 | 0 | 1 | 0
12 | EHH-12 | 3572 | City of Boston Coastal Storm Risk |  | Coastal Model Development Delays | Info and Data Analysis | 1 | Delays associated with development numerical coastal models. Regardless of NACCS or MC-FRM, there are significant changes necessary to develop an accurate existing and future without project model. Delays to coastal modeling could cascade and affect Economics and Cost. | 4 | Very Likely | Very Likely (70% to 90%) | The study area is very complex and there are several projects and actions by others that need to be developed for the numerical modeling. As large as the study area, it is likely that there will be challenges in developing the FWOP picture. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 5 | Other | There could be delays in releasing the draft report. | 5 | 2 | 0 | 25000 | 0 | If there are issues, the study team will likely need to bring in assistance. | 0 | 60 | 120 | If there are delays it will likely impact economics and cost disciplines and prolong the schedule. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-23 19:55 | 0 | 4490 | Jeffrey | Herzog | 299 | 302 | 0 | 0 | 0
13 | PGM-13 | 3572 | City of Boston Coastal Storm Risk |  | Incremental Funding | Resource Availability | 5 | Incremental funding of the study will impact schedule and resource availability. The study funding stream indicates a federal need of $750K in FY23 and FY24, followed by $500K in FY25. Any delay or denial of this funding will result in a schedule delay commensurate with the reduced funding. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | The study is being funded through Workplan and Presidents Budget requests. These requests are outside the sphere of influence for CENAE. If there is a delay or shortfall in any of these funding streams, the schedule will be impacted. The FY'23 Workplan request is $500K; currently there is zero money allocated to the Study. The FY'24 PBUD is $550K, which is $200K less than requested. Based on this shortfall, the study is one full year of federal funding behind schedule and will impact schedule by one year. |  |  | 22 | Programs Management | PGM | 4490 |  | 7 | Agency Reputational | The study is already scheduled for five years, in a City that recognizes an immediate need for intervention. Adding another year due to funding shortfalls will have a domino effect on PED and Construction schedules. | 5 | 2 | 0 | 0 | 0 |  | 0 | 365 | 365 | One year will be added to the schedule based on the funding stream shortfalls. Depending as to where in the study funding stream shortfalls are made up, it will impact the overall study delay. | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 18:16 | 0 | 4490 | Jeffrey | Herzog | 299 | 306 | 0 | 1 | 0
14 | PLE-14 | 3572 | City of Boston Coastal Storm Risk |  | Impacts due to Logan International Airport | Legal or Regulatory Actions | 10 | Logan International Airport and its airspace and flyways are in the study area. Based on needed elevation for structural solutions, flyway, runway end safety zones, and obstruction clearance rules may be impacted. | 3 | Likely | Likely (50% to 70%) | Without risk management and cooperating with the FAA, it is likely that an NNBF planned for Belle Isle Marsh, or Wood Isle Marsh would impact study completion. |  |  | 16 | Planning - Environmental | PLE | 4490 |  | 6 | Compliance |  | 10 | 3 | 0 | 5000 | 15000 | The FAA could require additional bird hazard studies or other studies to demonstrate the performance impacts on Logan International Airport. | 0 | 30 | 180 | Significant bird studies or surveys could cost a lot of money. However, there is extensive information and studies available for the areas in question. | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-01 19:21 | 0 | 4490 | Jeffrey | Herzog | 302 | 302 | 0 | 0 | 0
15 | OTH-15 | 3572 | City of Boston Coastal Storm Risk |  | Roadways as non-project segments | Agency Policy and Process | 7 | There are several elevated roadways that serve as non-project segment barriers. These segments are not designed or constructed to serve that purpose. If USACE formulates around these segments, they could become risk items later in a risk analysis. | 4 | Very Likely | Very Likely (70% to 90%) | Without risk management, it is likely that the study team will formulate without consideration of the non-project segments and only formulate to tie in closure structures for the underpasses of these segments. |  |  | 12 | Other | OTH | 3630 |  | 6 | Compliance | If it is determined that closure structures are not compliant or too great of a risk, reformulation could be necessary. Reformulation could also increase the study budget due to NEPA impacts and engineering survey needs depending on the recommendation. | 10 | 3 | 0 | 10000 | 50000 | The greatest impact of this risk is reformulation where it is determined that the risk is too great for a simple closure structure tied into an existing non-project segment. The more likely impact is additional study and analysis to ensure tie in is structurally sound and does not exacerbate risk. | 0 | 0 | 45 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 19:35 | 0 | 4490 | Jeffrey | Herzog | 302 | 306 | 0 | 0 | 0
16 | OTH-16 | 3572 | City of Boston Coastal Storm Risk |  | Life Safety Risk of the Alternatives | Agency Policy and Process | 7 | Life safety risk of the alternatives must be evaluated per the Comprehensive Benefits Memo as part of the Net Benefits Plan. The ability of the alternatives to impacts life safety risk and the team's ability to describe that impact through the results of consequences modeling will be evaluated by OWPR. | 4 | Very Likely | Very Likely (70% to 90%) | Life Safety analysis in the study phase can be qualitative or semi-quantitative depending on the degree of risk determined by the PDT. Without risk management and involvement of risk cadre, it is very likely that a qualitative assessment would be completed. That assessment would be evaluated by OWPR and determined whether it is compliant and satisfactory or requires additional work. |  |  | 12 | Other | OTH | 4490 |  | 6 | Compliance | If sufficient life safety analysis can't be demonstrated, it may require reformulation. | 10 | 4 | 0 | 50000 | 0 | If it is determined that Life Safety is not sufficient, could require additional analysis, or potentially reformulation. This has Planning, NEPA, and Engineering impacts. | 0 | 120 | 0 |  | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 19:52 | 0 | 4490 | Jeffrey | Herzog | 299 | 299 | 0 | 0 | 0
17 | PLP-17 | 3572 | City of Boston Coastal Storm Risk |  | Nonstructural Real Estate Costs | Agency Policy and Process | 7 | USACE policy for nonstructural measures is in development and there is no standard estate and no determination whether elevation/floodproofing requires an interest in real estate. | 4 | Very Likely | Very Likely (70% to 90%) | There will likely be some building adaptation or other nonstructural measures to buildings in the study area. The Enterprise is still developing costs, requirements, and policy. Even when first published, it will likely still have impacts on formulation. |  |  | 13 | Planning - Plan Formulation | PLP | 4490 |  | 6 | Compliance | Policy could increase nonstructural LERRS and change the benefits so significantly that it changes the TSP and require reformulation. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 150 | It is likely that the impact will be somewhere between 0 and 5 months while the team works to understand and incorporate nonstructural LERRS. If nonstructural measures are not used, it is zero impact. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-27 18:02 | 0 | 4490 | Jeffrey | Herzog | 299 | 306 | 0 | 1 | 0
18 | OTH-18 | 3572 | City of Boston Coastal Storm Risk |  | Utilities in the Project Area | Site Conditions | 6 | Failure to identify utiities potentially affected by proposed structural solution may impact schedule, cost, and, design. | 3 | Likely | Likely (50% to 70%) | Dense urban environment, mapping utilities, private and public is not always accurate, or done at all. |  |  | 12 | Other | OTH | 3630 |  | 6 | Compliance | Cost impacts of relocating utilities could extend beyond the Chief's discretionary authority and require a Post Authorization Change. | 10 | 3 | 0 | 150000 | 500000 | If utilities are discovered that impact constructability, or implementation, it could increase costs significantly. | 0 | 180 | 720 | A significant redesign or need to execute surveys/borings could significantly impact schedule. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 11 | 11 | Complete Real Estate Acquisition | 2023-03-01 20:18 | 0 | 4490 | Jeffrey | Herzog | 302 | 302 | 0 | 0 | 0
19 | EGT-19 | 3572 | City of Boston Coastal Storm Risk |  | SLC impacting Geology and Geotech | Site Conditions | 6 | Sea level rise leads to higher groundwater elevations in areas of fill in the City of Boston. The areas of fill are currently susceptible to liquefaction and liquefaction susceptibility is exacerbated by rising sea level. | 3 | Likely | Likely (50% to 70%) | Liquefaction of coastal areas of fill leads to lateral spreading and settlement of overlying coastal protection levees and structures. |  |  | 3 | Engineering - Geotechnical | EGT | 3630 |  | 5 | Other |  | 10 | 0 | 0 | 1300000 | 30000000 | The impact of the analysis in PED could change the foundation recommendations of the features authorized in the Feasibility Study. It is likely that the Feasibility Study analysis will paint an accurate picture and only the cost of borings will be necessary in PED to confirm. However, if there is a significant change in conditions, it could significantly increase the cost of the feature's foundation. It could also change the NEPA impacts. | 0 | 180 | 720 | Schedule impacts could range from 6 months to 2 years in PED depending on how different the conditions are from what is determined in Feasibility. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 10 | 10 | Concept Design Phase (35%) | 2023-03-01 20:33 | 0 | 4490 | Jeffrey | Herzog | 302 | 302 | 1 | 0 | 0
20 | EGT-20 | 3572 | City of Boston Coastal Storm Risk |  | Materially differing site condition | Site Conditions | 6 | Site characterization for potential subsurface construction will not be conducted until PED phase. | 3 | Likely | Likely (50% to 70%) | Construction costs could increase significantly depending on unanticipated foundation conditions on shore or off shore. |  |  | 3 | Engineering - Geotechnical | EGT | 3630 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 120 | Depending on the alternatives in the Final Array, the Engineering team may need longer to gather enough data for the risk informed design process. Additionally, the qualitative risk assessment and the CSRA will need to account for the uncertainty of subsurface conditions. If not, the risk of insufficient construction costs may be realized. | 2 | 1 | 1 | Active | 4 | Planning | 5 | 5 | Senior Leaders Briefing | 2023-03-01 20:42 | 0 | 4490 | Jeffrey | Herzog | 299 | 306 | 1 | 1 | 0
21 | PLE-21 | 3572 | City of Boston Coastal Storm Risk |  | Determining a proposed action impacts EFH or ESA Resources | Site Conditions | 6 | Identification of EFH resources at any site late in the feasibility study process would add time to the schedule and increase study cost. | 4 | Very Likely | Very Likely (70% to 90%) | Without risk management it is very likely that we will identify either waterside construction or actual in-water work that could impact EFH. If it is waterside construction that is identified as part of the Feasibility Level design, post-ADM, it could have significant impacts on completing the NEPA document. |  |  | 16 | Planning - Environmental | PLE | 4490 |  | 6 | Compliance |  | 5 | 2 | 0 | 100000 | 250000 | If baseline surveys or additional investigation is necessary post ADM, it will impact cost and schedule, depending as to where in the study area it is. If it requires mitigation, then it will require planning and modeling on top of the potential surveys. | 0 | 60 | 180 | If surveys and mitigation planning is necessary it will take much longer. However, the likelihood is, information will be on hand and it is a matter of mitigation planning only. | 2 | 1 | 1 | Active | 4 | Planning | 5 | 5 | Senior Leaders Briefing | 2023-03-01 21:50 | 0 | 4490 | Jeffrey | Herzog | 302 | 302 | 0 | 0 | 0
22 | PLE-22 | 3572 | City of Boston Coastal Storm Risk |  | Recommending features that cut off access to water | Stakeholder, Sponsor or Partners | 9 | Building of structures could reduce access to water's edge and associated recreational opportunities that those areas provide. | 4 | Very Likely | Very Likely (70% to 90%) | Without risk management and comprehensive benefits planning it is very likely that NED planning will point to hardening shoreline and blocking access to the water as part of risk management. |  |  | 16 | Planning - Environmental | PLE | 4490 |  | 7 | Agency Reputational |  | 10 | 3 | 0 | 0 | 0 |  | 0 | 180 | 720 | The worst-case scenario is an unwilling sponsor and a terminated study. The more likely scenario is going out for public review after TSP and getting significant push-back requiring some reformulation. Reformulation will likely require a second release for NEPA. | 4 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-01 21:48 | 0 | 4490 | Jeffrey | Herzog | 299 | 302 | 0 | 1 | 0
23 | OTH-23 | 3572 | City of Boston Coastal Storm Risk |  | HTRW material at any project site | Stakeholder, Sponsor or Partners | 9 | Identification of HTRW during PED investigation will impact Sponsor's ability to turn over LERRDS and could impact schedule and budget | 4 | Very Likely | Very Likely (70% to 90%) | There are contaminated areas in the study area, specifically in the upper Neponset River and along Chelsea Creek. There are no Superfund sites in the direct area where the study is looking. |  |  | 12 | Other | OTH | 4490 |  | 5 | Other |  | 10 | 4 | 0 | 0 | 0 |  | 0 | 365 | 1440 | If HTRW is discovered that requires Sponsor remediation, it could take anywhere from 1-year to indefinitely. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 11 | 11 | Complete Real Estate Acquisition | 2023-03-01 21:56 | 0 | 4490 | Jeffrey | Herzog | 299 | 302 | 0 | 1 | 0
24 | PLP-24 | 3572 | City of Boston Coastal Storm Risk |  | City of Boston Leading Public Involvement | Communications | 2 | This is an opportunity. The Sponsor scheduled $250K WIK dedicated to Public Involvement and Outreach. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | The city has 7-years of working on Climate Ready Boston which is the foundation for the Corps Study. They have the relationships, they understand the language barriers and interpretive needs and they know the hot-button issues in each neighborhood. |  |  | 13 | Planning - Plan Formulation | PLP | 4490 |  | 7 | Agency Reputational |  | -10 | 1 | 0 | -250000 | 0 |  | -180 | -30 | 0 | Their experience will be a significant time savings both in actual outreach, but also in responding to inquiries about who and what we didn't do for outreach. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 22:02 | 0 | 4490 | Jeffrey | Herzog | 299 | 302 | 0 | 0 | 0
25 | EHH-25 | 3572 | City of Boston Coastal Storm Risk |  | ERDC Refinement of the CHS Model specific to Boston CSRM | Info and Data Analysis | 1 | Scheduling a Modeling Validation Period will ensure that the study team has the correct FWOP picture and approach to make risk informed planning decisions. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | CHS and G2CRM will provide a policy compliant product; however, does it provide the necessary data to give the study team the necessary information to make the correct decisions? This period will compare two separate coastal modeling approaches and two economic models to ensure that the right strategy and models are selected. The models will use existing data from a complex neighborhood to validate. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 4 | Operations |  | -10 | 1 | -250000 | 150000 | 350000 | Without the refinement period, the study will likely move forward and develop a policy compliant product. However, in PED when more detail and an SQRA/SAR are necessary, it could be determined that the feasibility modeling was incorrect. Based on experience, the effort to correct this is about $500k. This triangulation shows that the study could break even at $350K for the effort or realize up to a $250K savings. | -270 | -270 | 270 | The opportunity for schedule savings is not linear. If rework in the study later on is required, it would likely take 9 months based on experience. However, the 6-month refinement period to update CHS for the specific study is free time because it was already going to be used by the team to identify inputs to the existing and FWOP condition. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-23 20:00 | 0 | 4490 | Jeffrey | Herzog | 302 | 299 | 0 | 0 | 0
26 | PLE-26 | 3572 | City of Boston Coastal Storm Risk |  | Comprehensive Benefits Strategy and EJ | Agency Policy and Process | 7 | Comp Benefits (Jan '21 Memo) and EJ Outreach/inclusion (Jan '23 IG) are two planning areas of consideration that could impact plan selection. | 4 | Very Likely | Very Likely (70% to 90%) | The City of Boston is overwhelmingly EJ by definition of the CEJST (1.0). Reasons include linguistic isolation, traffic density and volume, and workforce development related vulnerabilities. Additionally, there are several intangible risks, impacts, and benefits that need to be considered in Boston that fall under the Comprehensive Benefits Strategy. |  |  | 15 | Planning - Economics | PLE | 2495 |  | 7 | Agency Reputational |  | 5 | 2 | 0 | 0 | 200000 | Without risk management, the impacts of incomplete comprehensive benefits analysis could be reformulation. The impacts of incomplete EJ Outreach is a non policy compliant NEPA Document that require rework and a second release. | 30 | 0 | 180 | If rework is necessary and a second release is necessary, the impact could be as great as 6 months. | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-01 22:26 | 0 | 4490 | Jeffrey | Herzog | 306 | 306 | 0 | 0 | 0
27 | EHH-27 | 3572 | City of Boston Coastal Storm Risk |  | Resource Availability to Support CHS Model Refinement | Resource Availability | 5 | Partnering with ERDC for refining CHS creates a risk due to timing. We are making the request for support at the end of the FY 2nd Quarter when Workload is at its peak for resources. If ERDC can't support the scope and refinement of the CHS model, it could delay the ability to accurately model the existing and future without project conditions. | 4 | Very Likely | Very Likely (70% to 90%) | It is very likely that ERDC's workload for 3rd and 4th Quarter FY23 is already planned out and full. NAE is requesting to add additional requirements to the ERDC staff to support refinement of CHS. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 25000 | If ERDC's capacity is already reached and OT is necessary to meet the needs of the District, there could be an additional cost beyond burdened labor rates. | 0 | 0 | 30 | The Team factored full workload when developing the schedule for the ERDC work. 30 days would likely be as a result of already scheduled leave of absence, or an issue with the model itself. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-29 15:03 | 0 | 4490 | Jeffrey | Herzog | 306 | 306 | 0 | 0 | 0
28 | PLE-28 | 3572 | City of Boston Coastal Storm Risk |  | Economic Model Development | Info and Data Analysis | 1 | G2CRM is the preferred model in conjunction with CHS for economic analysis of Coastal Studies. The risk is under or overestimating damages in the future without project conditions which could impact formulation and alternative selection. G2CRM does not in itself incorporate SLC or wave runup, it is a post processing exercise for year one and year 50 to identify the impacts of SLC. | 3 | Likely | Likely (50% to 70%) | Without risk identification and risk management, it is likely that the study would underestimate damages in a FWOP due to SLC and wave runup. |  |  | 15 | Planning - Economics | PLE | 2495 |  | 6 | Compliance | It is a minor problem that would require additional formulation. As long as the issue is identified prior to TSP and release of the draft report, there would only be minor problems associated with reformulation. | 5 | 2 | 0 | 0 | 150000 | On the highest end, the estimate includes reformulation and re-running the economic model. | 0 | 0 | 90 | This error would potentially impact the alternative identified as the TSP. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-29 14:53 | 0 | 4490 | Jeffrey | Herzog | 306 | 306 | 0 | 0 | 0
1 | EGT-1 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Underseepage - Borings not adequate to capture Piping Risk A | Site Conditions | 6 | Borings not adequate to capture areas where underseepage/piping failure risk areas not captured. Underestimating the size and number of seepage berms and/or relief wells in feasibility that have to be added in final design. This leads to underestimating construction and real estate costs in feasibility. | 2 | Unlikely | Unlikely (30% to 50%) | If we capture an adequate sampling of soils across the site we are like to get size and number of required relief wells correct. In final design it will be likely that locations shift. |  |  | 3 | Engineering - Geotechnical | EGT | 4051 |  | 6 | Compliance | The number and size of seepage berms will be captured in final design | 5 | 2 | 0 | 150000 | 0 | Large. Number of relief wells is underestimated they are $150,000.00 per relief wells with collector. Seepage berms require real estate and material and are typically 200 feet or so from levee and typically extend multiple stations. Past construction and current trends used to estimate. | 0 | 180 | 0 | If seepage berms are underestimated they will require that Sponsor aquire additional real estate for construction. Minor. Final design will have more borings and number and size of relief wells and underseepage berms will be captured in final. | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-04-11 03:09 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
2 | EGT-2 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Underestimate Levee Settlement | Info and Data Analysis | 1 | Inadequate borings are collected to get good feasibility design estimate of settlement. This leads to need to increase height of levees during final design. | 2 | Unlikely | Unlikely (30% to 50%) | We plan to capture adequate data to determine magnitude or risk in design |  |  | 3 | Engineering - Geotechnical | EGT | 8248 |  | 5 | Other | It will be captured in final design | 5 | 2 | 0 | 50000 | 0 | The footprint of the levee would change requiring additional real estate. Construction costs would increase due to increase in levee height. We plan to collect enough borings to capture magnitude of settlement and needed levee height. | 0 | 180 | 0 | Past experience indicates that acquiring real estate can be very time consuming and can lead to delays. Typically it is controlled by sponsor and occurs at their desired schedule. This occurred on St. Joseph levee project where sponsor was not super eager to move project along. | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 10 | 10 | Concept Design Phase (35%) | 2023-04-14 18:23 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
3 | EGT-3 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Foundation Soil Strength underestimated | Info and Data Analysis | 1 | Not enough borings to get good estimate of soil strength, leading to understimating levee footprint and underestimating foundation size of any floodwalls that are designed. | 2 | Unlikely | Unlikely (30% to 50%) | We plan to capture adequate subsurface data to get good estimate of foundation soil strength |  |  | 3 | Engineering - Geotechnical | EGT | 8248 |  | 5 | Other | We will capture foundation soil strenght in more detail in final design. | 5 | 2 | 0 | 75000 | 0 | Additional Real estate would be required for levee and shallow foundations of floodwalls. Would require deeper deep foundations of any pile supported floodwalls. | 0 | 365 | 0 | Sponsor will need to acquire additional real estate and additional subsurface data collected | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-04-14 18:28 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
4 | EHH-4 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Utilize FY23 LOMO System River Model | Info and Data Analysis | 1 | Utilize LOMO System Plan HEC-RAS with minimum updates | 2 | Unlikely | Unlikely (30% to 50%) | The system plan model will not include level of detail required to fully analyze the scope of the project. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8248 |  | 7 | Agency Reputational | The scope of the full LOMO RAS model is not directly aligned with the spin-off study scopes. | 5 | 2 | 0 | 50000 | 0 | Model additional site detail including bridge structure, adjustments to calibrate to Jefferson City USGS gage, and tributaries. | 0 | 180 | 0 | Delays H&H analysis until Oct. 2023. Reliance on another project schedule. | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 18:32 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
5 | EHH-5 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Accurate modeling of FWOP condition | Site Conditions | 6 | Accurately modeling of FWOP conditions. | 2 | Unlikely | Unlikely (30% to 50%) | Hitachi indicated desire to move out if they have another flood. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 4051 |  | 5 | Other | Future impacts typically discounted back to present value. | 5 | 2 | 0 | 10000 | 0 | Provide additional analysis/rework FWOP conditions | 0 | 30 | 0 | Rework/additional analysis time | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 18:37 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
6 | RLE-6 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Unwilling sellers | Stakeholder, Sponsor or Partners | 9 | Multiple unwilling sellers have declined offers from the Non Federal Sponsor. | 3 | Likely | Likely (50% to 70%) | There are 3 property owners already stated unwilling to sell. Further more there is business property owner unwilling to sell at fair market value. |  |  | 18 | Real Estate | RLE | 8248 |  | 5 | Other |  | 5 | 2 | 0 | 50000 | 0 |  | 0 | 180 | 0 |  | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 11 | 11 | Complete Real Estate Acquisition | 2023-04-14 18:40 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
7 | PLE-7 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Jurisdictional wetlands impacts to alternatives | Site Conditions | 6 | Previous wetland delineations have identified jurisdictional wetlands throughout the study area. The risk of wetland impacts are heightened. | 3 | Likely | Likely (50% to 70%) | Previous wetland delineations have identified wetlands throughout the study area. |  |  | 16 | Planning - Environmental | PLE | 5621 |  | 5 | Other | Wetland impacts can be minimized and mitigated. | 5 | 2 | 0 | 10000 | 0 | Fieldwork is necessary to confirm locations of wetlands within the study area. Additional work may be needed to modify alternatives to avoid/minimize wetland impacts. | 0 | 30 | 0 | Time needed for fieldwork to confirm locations of wetlands within the study area. Additional time may be needed to modify alternatives to avoid/minimize wetland impacts. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-14 18:42 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
8 | PLE-8 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | System Plan developing CAR- spin-off time frame may need gre | Agency Policy and Process | 7 | Coordination pursuant to FWCA is required. Ongoing FWCA coordination under the Lower Missouri River System Plan study may be able provide some input from USFWS to the Jefferson City study in the form of planning aid letters and a coordination act report. However, it is unclear if this coordination act report will be available soon enough to be utilized for the Jefferson City study. | 3 | Likely | Likely (50% to 70%) | Current estimates for USFWS FWCA input for the Lower Missouri River System Plan study indicate that planning aid letters will be finalized in time for the Jefferson City study to utilize them, but the coordination act report might not be. |  |  | 16 | Planning - Environmental | PLE | 8248 |  | 7 | Agency Reputational | Given that FWCA coordination with USFWS is already underway for the Lower Missouri River System Plan study, additional coordination for the Jefferson City spinoff study is unlikely to be substantial. | 5 | 2 | 0 | 50000 | 0 | USFWS may determine that the planning aid letters produced for the System Plan study, in combination with a planning aid letter specific to the Jefferson City study, may be sufficient. However, a study-specific coordination act report has not yet been ruled out. | 0 | 30 | 0 | Time may be needed to negotiate FWCA scope. Once negotiated, much of the work performed by USFWS can be done in parallel to USACE's work on the feasibility study. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-14 18:45 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
9 | PLE-9 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Federally listed bats roosting in project area | Site Conditions | 6 | An initial site visit confirmed the presence of trees that likely serve as adequate summer roosting by multiple species of federally listed bats. It is possible that these species are present in the study area during the summer roosting season. | 3 | Likely | Likely (50% to 70%) | Site visit confirmed the presence of adequate habitat. |  |  | 16 | Planning - Environmental | PLE | 8248 |  | 7 | Agency Reputational | Informal Section 7 consultation is likely to only result in a seasonal tree clearing restriction. | 5 | 2 | 0 | 1000 | 0 | Informal consultation for potential bat impacts is very likely necessary for alternatives that remove trees. If the proposed action does not remove trees, Section 7 consultation would not be necessary for a "no effect" determination. | 0 | 14 | 0 | If no tree clearing is proposed, then it is likely that no Section 7 consultation for these bat species would be required. However, if tree clearing is proposed then USFWS may need one or two weeks to complete informal consultation for these species. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-14 18:47 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
10 | EHH-10 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Floodway Impact | Legal or Regulatory Actions | 10 | Inadequate determination of floodway and floodplain impacts when analyzing alternatives. | 2 | Unlikely | Unlikely (30% to 50%) | USACE procedures and documentation practices will include analysis of impacts with selection of alternatives. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8248 |  | 5 | Other | Not fully analyzing would deviate from standard USACE practices. | 5 | 2 | 0 | 40000 | 0 | Costs associated with analysis and documentation of upstream and downstream impacts. Expand model to fully encompass affected profile. | 0 | 30 | 0 | Analysis incorporated into standard USACE practices. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 18:58 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
11 | ECV-11 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Survey | Site Conditions | 6 | Accuracy of survey impacts H&H and civil design and risk that additional survey data is needed (field or bathymetric). | 3 | Likely | Likely (50% to 70%) | Accuracy/availability of as-built information for features including bridges and existing infrastructure/utilities. |  |  | 9 | Engineering - Civil | ECV | 8248 |  | 5 | Other | Assumptions could be made based on aerial imagery, site visits, available LiDAR. | 5 | 2 | 0 | 20000 | 0 | Cost of survey crew and data processing | 0 | 30 | 0 | Time necessary for survey and data processing and updating original assumptions | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 19:00 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
12 | PLE-12 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Sole beneficiary | Agency Policy and Process | 7 | Policy dictates that a sole beneficiary analysis is required; project risk that 25% of benefits could go to one landowner; sensitive policy area that requires VT coordination per exhibit G6 in Planning Guidance Notebook ER 1105-200. | 3 | Likely | Likely (50% to 70%) | small floodplain with two principal landowners |  |  | 15 | Planning - Economics | PLE | 3052 |  | 6 | Compliance | Sole beneficiary would jeopardize federal interest determination. | 10 | 3 | 0 | 10000 | 0 | Time and money doing required vertical team coordination | 0 | 30 | 0 | Time and money doing required vertical team coordination | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 19:01 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
13 | EGT-13 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Borrow location changes to somewhere where there aren't exis | Site Conditions | 6 | Determine if soils are satisfactory material, enough quantity to construct project. Would need additional borings in order to complete. | 3 | Likely | Likely (50% to 70%) | Past experience |  |  | 3 | Engineering - Geotechnical | EGT | 8248 |  | 5 | Other | The need for more borings would be a minor problem in the planning phase but could become a major problem if not discovered until the PED phase. | 5 | 2 | 0 | 100000 | 0 | Additional borings and analysis | 0 | 180 | 0 | Time to coordinate borings, rights of entry, and other logistics. | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-28 23:16 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
14 | EGT-14 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Borrow location is incorrectly identified or inadequate amou | Site Conditions | 6 | Additional siting and borings would be needed. | 3 | Likely | Likely (50% to 70%) | Past experience |  |  | 3 | Engineering - Geotechnical | EGT | 4051 |  | 5 | Other | Past experience, critical piece to move ahead to constructible project. | 10 | 3 | 0 | 100000 | 0 | additional borings and analysis would need to be performed | 0 | 180 | 0 | Additional days for borings, analysis, right of entry, and other logistics | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-04-28 23:18 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
15 | PRM-15 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Stakeholder would like to use a Locally Preferred Plan to co | Stakeholder, Sponsor or Partners | 9 | Use of Locally Preferred Plan could be a higher cost than the smaller Levee footprint. Also, if this is being used as a reason to mitigate the issue of non-willing sellers, | 3 | Likely | Likely (50% to 70%) | Discussion with sponsors throughout project, prior experience |  |  | 17 | Project Management | PRM | 4051 |  | 7 | Agency Reputational | There is a high risk that the sponsor will not want to move forward with the plan that isn't the LPP. | 10 | 3 | 0 | 19999 | 0 | Labor costs to work additional waivers, VT discussions, sponsor coordination, evaluation, etc. | 0 | 90 | 0 | Time in schedule to work additional waivers, VT discussions, sponsor coordination, evaluation, etc. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-28 23:25 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
16 | PLE-16 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Jeff City Airport | Site Conditions | 6 | Presence of local airport may limit our ability to propose borrow areas and wetland creation for mitigation near the airport, as these things may attract birds and increase collision risk. | 3 | Likely | Likely (50% to 70%) | The airport is located approximately in the middle of study area, so any borrow sites or wetland mitigation sites would have a high likelihood of being located near the airport. |  |  | 16 | Planning - Environmental | PLE | 5621 |  | 2 | Environmental | Early coordination with FAA and airport personnel should USACE to identify constraints for borrow area locations (if needed) and wetland mitigation area (if needed). Corps currently anticipates that constraints can be satisfied by locating these areas at an adequate distance to the airport. | 5 | 2 | 0 | 50000 | 0 | Coordination will be necessary between the Corps, Federal Aviation Administration, and airport personnel to discuss the potential for increased collision hazards near the airport. It is possible that borrow sites and wetland mitigation sites may need to be located further away from the airport, which could potentially raise real estate costs. | 0 | 30 | 0 | Coordination with FAA and airport personnel will be required to fully document the constraints may be placed on project designs due to the presence of the airport. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-28 23:28 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
17 | ECV-17 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Unidentified Utilities | Site Conditions | 6 | Relocation of utilities would be required | 3 | Likely | Likely (50% to 70%) | PDT experience with recent levee projects |  |  | 9 | Engineering - Civil | ECV | 4051 |  | 5 | Other | Solutions have been found in past projects | 5 | 2 | 0 | 0 | 0 |  | 0 | 90 | 0 | Utility owners are required to perform the relocation, could impact schedule if not found until construction or requires additional design. | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-04-28 23:38 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 1 | 0
18 | EHH-18 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Cumulative effects isn't as extensive as needed | Agency Policy and Process | 7 | The Prior Study at L-142 ruled that the cumulative effects wasn't as extensive as needed. The team will need to ensure that the cumulative effects at analyzed far enough upstream and downstream of the project study, | 2 | Unlikely | Unlikely (30% to 50%) | Risk is unlikely since the team has learned from previous study. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 4051 |  | 5 | Other | Performing this analysis will be a minor improvement to the previous study and ensure that this study continues to move forward. | -5 | 1 | 0 | 10000 | 0 | H&H will make sure modeled alternatives are modeled far enough upstream and downstream and entered into the system model. | 0 | 30 | 0 | Additional modeling and reviews. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 18:52 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
19 | PLE-19 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | First floor elevations | Site Conditions | 6 | First floor elevation is uncertain and single biggest driver of damages and benefits in riverine FRM. Economist need to be in the field and make survey in order to get first floor elevations | 3 | Likely | Likely (50% to 70%) | Viewing elevations from maps is often inaccurate. The purpose of the field survey is to ensure that we have accurate first floor elevations to prevent this from happening. |  |  | 15 | Planning - Economics | PLE | 3052 |  | 5 | Other | Damages and benefits will be incorrect - either high or low and the BC ratio will be incorrect as well. | 10 | 3 | 0 | 6000 | 0 | Additional field visit for two personnel and updating maps as needed. | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 18:58 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 1
20 | PRM-20 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Qualified Personnel | Resource Availability | 5 | Many experienced PDT members have left the District or have moved onto more senior level positions. Many resources are also overresourced. | 3 | Likely | Likely (50% to 70%) | Many staff lack experience on Planning studies and resources are stretched thin. |  |  | 17 | Project Management | PRM | 4051 |  | 5 | Other | Monthly LIRs with resource providers on all LoMo projects and reporting of any resource concerns and missed milestones. | 5 | 2 | 0 | 20000 | 0 | Bringing PDT members up to speed, mentoring newer PDT members, | 0 | 60 | 0 | Additional time for training, learning policies, limited staff to add multiple PDT members of same discipline | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-01 19:05 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
21 | PLE-21 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Evaluate previously authorized project | Legal or Regulatory Actions | 10 | Per guidance, any previously authorized project must be evaluated during the planning phase as one of the alternatives. | 4 | Very Likely | Very Likely (70% to 90%) | There is a previously authorized project so it must be evaluated. |  |  | 15 | Planning - Economics | PLE | 3052 |  | 5 | Other | Evaluation should be fairly straight forward. | 5 | 2 | 0 | 12000 | 0 | Labor for additional evaluation | 0 | 10 | 0 | Additional time for evaluation | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 19:14 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
22 | OTH-22 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Stakeholder concerns with Right Bank | Communications | 2 | The study location is on the left bank of the river. However, stakeholders are concerned with Wears Creek and interior flooding on the right bank. Additional communication effort will be needed to emphasize the project area. | 4 | Very Likely | Very Likely (70% to 90%) | Stakeholder concerns about addressing flooding on Wears Creek have already been brought up on the site visit. |  |  | 12 | Other | OTH | 8248 |  | 5 | Other | Continued communication of the study area | 5 | 2 | 0 | 6000 | 0 | Additional labor and outreach | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 19:19 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 1
23 | PLE-23 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Policy Waiver to NED plan selection | Agency Policy and Process | 7 | It is currently not determined if the NED plan will be justified. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 15 | Planning - Economics | PLE | 3052 |  | 5 | Other | Justification can be difficult. | 10 | 2 | 0 | 10000 | 0 | Additional labor for waiver | 0 | 60 | 0 | additional time for waiver | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-01 19:24 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
24 | EGT-24 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | PL84-99 eligibility of secondary levee | Agency Policy and Process | 7 | The current Capital View levee would become a secondary levee if a new levee is constructed behind it, threatening its eligibility in the PL 84-99 program. | 3 | Likely | Likely (50% to 70%) | ER 500-1-1, page 5-6, para 5-3, a secondary levee is ineligible unless it protects human life. |  |  | 3 | Engineering - Geotechnical | EGT | 8248 |  | 5 | Other | Capital View levee getting kicked out of the PL84-99 program in order to build a second levee is a show stopper for the stakeholders. | 10 | 3 | 0 | 20000 | 0 | Additional labor working through policy | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 19:37 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 1
25 | PRM-25 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Changes in design criteria | Agency Policy and Process | 7 | Ever changing policies and design criteria impacting the study progress after scoping is complete. | 3 | Likely | Likely (50% to 70%) | Guidance and policy is always changing. |  |  | 17 | Project Management | PRM | 4051 |  | 5 | Other | Varies depending on the guidance/policy/criteria update and impacts to the study | 5 | 2 | 0 | 50000 | 0 | Varies depending on the guidance/policy/criteria update and impacts to the study | 0 | 180 | 0 | Varies depending on the guidance/policy/criteria update and impacts to the study | 3 | 1 | 1 | Active | 4 | Planning | 6 | 6 | Chief’s Report/Director’s Report | 2023-05-01 19:42 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
26 | PLC-26 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Cultural surveys | Site Conditions | 6 | Cultural surveys will not be performed during feasibility phase | 3 | Likely | Likely (50% to 70%) | Possibility of finding something during cultural surveys during PED |  |  | 14 | Planning - Cultural Resources | PLC | 8248 |  | 5 | Other | Depending on what is found from the survey, impacts on the project alignment could be significant. | 10 | 3 | 0 | 100000 | 0 | Cost of surveys and/or additional redesign if something is found during PED | 0 | 180 | 0 | Additional days for redesign | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-05-01 19:45 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
27 | ECV-27 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | New Utilities | Site Conditions | 6 | New utilities or changes to existing utilities between Feasibility and PED | 2 | Unlikely | Unlikely (30% to 50%) | The team is obtaining all known utility surveys in the area. The area is not well developed therefore additional utilities will not be as likely. |  |  | 9 | Engineering - Civil | ECV | 4051 |  | 5 | Other | This is a frequent occurrence during many project design phases | 5 | 2 | 0 | 10000 | 0 | additional redesign | 0 | 60 | 0 | additional redesign | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 10 | 10 | Concept Design Phase (35%) | 2023-05-01 19:48 | 0 | 4051 | Colleen | Roberts | 299 | 299 | 0 | 0 | 0
1 | PLE-1 | 3576 | Owyhee | 479131 | Inadequate water for all year round habitat | Site Conditions | 6 | Irrigation demands and arid conditions limit water availability for aquatic habitat restoration. | 5 | Extremely Likely | Extremely Likely (90% to 100%) |  |  |  | 16 | Planning - Environmental | PLE | 2594 |  | 2 | Environmental | will not be able to maximize benefits | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-02-02 17:33 | 0 | 2919 | Kathryn | Herzog | 299 | 299 | 0 | 1 | 1
1 | PLP-1 | 3593 | Lower Mississippi River Comprehensive Management Study |  | MR&T may not operate as believed | Info and Data Analysis | 1 | MR&T may not operate as believed, which adds uncertainty risks to modeling and risks to design outcomes. | 4 | Very Likely | Very Likely (70% to 90%) | 1/4 diversion features are now obsolete due to existing conditions varying from modeled conditions. Studies show that MS River geomorphology is constantly changing from a complex set of natural and anthropogenic causes, many of which are outside of the study area. The State of Louisiana continues to permit diversions which may alter the management of the Lower Mississippi River, so the future-with and future-without project conditions may not be accurately modeled. |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other | MR&T system unknowns risk inaccurate modeling FWOP and future-with project conditions. Inaccurate modeling risks an inaccurate Recommended Plan and flawed designs. | 10 | 3 | 0 | 0 | 0 | At this time, cost and cost impact cannot be determined. Modeling cost estimates are based on the number of alternatives, the type of models, the number of runs, the scenarios run, etc. | 0 | 0 | 0 | At this time, schedule delays cannot be determined. Scoping, data collection, and the modeling schedule depend on factors such as the number of alternatives, the model types (for example 1D, 2D, or 3D H&H models), if existing models are available or if models need to be built. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-23 21:10 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
2 | PLP-2 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Budget limitations | Resource Availability | 5 | Risk: Study budget cannot support the full authorized scope of Lower Mississippi River reevaluation. This could lead to Study Risk (Analytical error, study delays, study cost increase, poor planning decision) Consequence: There could be analytical error, poor planning decisions made if a limited budget does not allow sufficient modeling for the area of influence. Asking for additional funds to pursue the full relevant system could add study delays and study cost increase. | 4 | Very Likely | Very Likely (70% to 90%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 8 | Agency Strategy |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:23 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
3 | PLP-3 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Budget Limitations | Contract Performance | 4 | Risk: Study budget cannot support the full authorized scope of Lower Mississippi River reevaluation, resulting in Outcome Risk (hazard risk and project performance risk). Consequence: If budget limitations reduce the PDT's ability to adequately model or evaluate the comprehensive system, constructed features may not adequately address the problems, may not resolve the intended "adverse outcomes" from existing structures, and may add unexpected risks to system. For example, an insufficient analysis on a system-wide sediment budget may result in future unanticipated instabilities. | 3 | Likely | Likely (50% to 70%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 4 | Operations |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-02-24 20:28 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
4 | PLP-4 | 3593 | Lower Mississippi River Comprehensive Management Study |  | External partner and community engagement | Communications | 2 | Risk: Delayed external partner and community engagement could delay momentum. Identifying the full scope of stakeholders will take some time. This could result in Schedule delays. Consequence: Schedule delays could arise if poor or delayed communication results in non consensus or friction points. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 60 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:31 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
5 | PLP-5 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Architecture of Sub-PDTs | Agency Policy and Process | 7 | Due to the size of this mega study, the Governance structure will need multiple sub-PDTs. The PDTs may be divided by Problem area, geographically, or by Mission Area. Different risks may accompany each method for dividing the sub-PDTs. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:39 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
6 | PLP-6 | 3593 | Lower Mississippi River Comprehensive Management Study |  | System-wide sub-PDT | Agency Policy and Process | 7 | The Governance structure will likely include a technical sub-PDT body responsible for maintaining consistency on a system-wide scale (ie for H&H modeling, Ecosystem Restoration modeling, lessons learned, legal, etc.) Different risks may accompany the Governance structure depending on what functions the system-wide sub-PDT body includes or excludes. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:43 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
7 | PLP-7 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Impact Area Unknown | Info and Data Analysis | 1 | Impact area of study is yet unknown. Impact area is influenced by study area, which has yet to be clearly defined. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:46 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
8 | PLP-8 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Study Area Undefined | Info and Data Analysis | 1 | The left and right bounds of the study area have yet to be defined. This contributes some uncertainty to the problems, opportunities, and influence area. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:49 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
9 | PLP-9 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Modifying Mississippi River System | Contract Performance | 4 | Despite best modeling efforts, the impacts of modifying the hydraulic and hydrologic functions of the Lower MS River cannot be known until after construction is complete. Discrepancies between the modeled system and actual system could pose operational risks and hazards, and could also add uncertainties to maintenance needs. | 3 | Likely | Likely (50% to 70%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other | Altering the hydraulics and hydrology of the Lower MS River could have major positive or negative consequences, with a variety of negative outcomes including environmental impacts and legal challenges. | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:55 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
10 | PLP-10 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Operations modification or override | Contract Performance | 4 | There is currently uncertainty surrounding if the PDT will evaluate modifying operations of the LMR or if current operations will be overridden to overhaul the existing system. Modifying or overriding the current LMR operations each has its own risks. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:06 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
11 | PLP-11 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Period of Analysis | Info and Data Analysis | 1 | The period of analysis has not yet been defined. Selecting a 50-year, 100-year, or 200-year period of analysis each have their own risks. Longer periods of analysis may provide for a greater longevity of solutions based on estimated risks. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:10 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
12 | PLP-12 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Competiting interests among States or Districts | Stakeholder, Sponsor or Partners | 9 | Competing interests among States and Districts could complicate definition of problems and opportunities, resulting in a delayed study timeline | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:12 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
13 | PLP-13 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Exclusion of New Madrid seismic zone from analysis | Info and Data Analysis | 1 | Inclusions and exclusions of problems considered for analysis will impact the level of risk adopted. A future earthquake in the New Madrid seismic zone may be excluded from the problems identified due to study budget limitations; in this case the risk will need to be assessed. The earthquake has a low likelihood within the period of analysis but high consequence. | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:26 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
14 | PLP-14 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Coincident event | Info and Data Analysis | 1 | The current system cannot handle a coincident event of storm surge combined with river high water. There are outcome risks including hazard risks and project performance risks if the coincident is not adequately considered. Inclusions and exclusions of problems considered for analysis will impact the level of risk adopted in this study. | 4 | Very Likely | Very Likely (70% to 90%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 10 | 4 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:31 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
15 | PLP-15 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Reversing adverse outcomes from existing construction | Legal or Regulatory Actions | 10 | Adverse outcomes from previous existing construction may not be able to be overcome with the new proposed projects. This may result in stakeholder disappointment or even exacerbated adverse effects with legal implications. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-02-24 21:35 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
16 | PLP-16 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Schedule delay | Agency Policy and Process | 7 | Risk: Risk of 9 months lost time and decreased efforts that can be invested in the study if the study start date is based on the Implementation Guidance, which specified a study start date upon receipt of funds (May 2022 date) instead of at an originally anticipated October 2023 FCSA signing. This could result in study delays, outcome risk, poor planning decision Consequence: Regional system may not be considered thoroughly enough to "reverse" adverse effects from existing efforts, and may cause new adverse effects. Miscalculating risks and consequences across the whole Lower Mississippi River system could result in new adverse impacts. Evidence: Mega studies typically require 5years. Coastal Texas Study, the largest mega study to date, required 120 active PDT members for only one state (Texas) . The study already had a 2-year Master Plan that preceded the study start and still took 5 years. If LMR Comp only has 4 years total due to lost time, the need to serve 6 states across multiple districts with diverging interests, 4 years does not seem realistic to create a meaningful re-working of the entire Lower Mississippi River system. This opportunity to reenvision the river will likely only once in a lifetime, so it is crucial to have sufficient time for meaningful work. Risk Management: To reduce risk, P0 team will coordinate further. P0 Team will seek an Exemption to IG to identify a start date of right now, a start date at a future FCSA date, start date of when P0 PDT timeline ends, or have a Memorandum of Understanding (MOU) | 5 | Extremely Likely | Extremely Likely (90% to 100%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:38 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
17 | PLP-17 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Counsel concerns with IG | Legal or Regulatory Actions | 10 | Counsel has concerns with the way IG is written. Date that 5-year schedule begins. IG says study begins "upon receipt of funds". Sorting out the start date could cause schedule delays. Not delaying the schedule could result in delayed milestones. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:40 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
18 | PLP-18 | 3593 | Lower Mississippi River Comprehensive Management Study |  | FCSA inclusion unknown | Agency Policy and Process | 7 | Because the study is 100% Federally-funded, an FCSA may not be executed. The FCSA signing typically starts the 5-year timeline for a study. The IG states that the 5-year schedule begins upon receipt of funds. Too little working time negatively impacts capabilities within study effort. With a once -in-a-generation opportunity to reenvision the LMR, there is a risk of insufficient analysis if enough time is not granted to this effort. Risk Reduction: Prepare Exemption packet. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:47 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
19 | PLP-19 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Study area yet to be defined | Stakeholder, Sponsor or Partners | 9 | The left and right limits of the study area have yet to be defined. Changing limits may not be acceptable to existing partners on past studies. Stakeholders are impacted by left and right bounds. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:50 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
20 | PLP-20 | 3593 | Lower Mississippi River Comprehensive Management Study |  | New policies may add analysis time | Legal or Regulatory Actions | 10 | New policies, such as new Environmental Justice and Drought policies, may add study analysis time or legal challenges. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:52 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
21 | PLP-21 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Project construction impacts on operation | Contract Performance | 4 | It is critical to maintain smooth operation of the Mississippi River during project construction, as the river operation impacts the food supply security of the world. If there are construction delays or operational challenges, there are larger economic and global security risks that may result. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-02-24 21:55 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
22 | PLP-22 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Duration betw Alternatives Milestone to TSP | Resource Availability | 5 | Evaluation of multiple Alternatives across business lines and across different geographic areas could stretch out the timeline. Modeling needs will not be known until we have a list of Alternatives. | 4 | Very Likely | Very Likely (70% to 90%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 346 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-17 19:37 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
23 | PLP-23 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Duration between ADM and Final Report | Resource Availability | 5 | Design considerations for Feasibility Design Phase could be significant (Mitigation Planning/ Navigation Impacts/ FRM Impact/ Existing Operations Impact). Schedule highly dependent on TSP and scope of Public/Legal/Policy Comments. | 4 | Very Likely | Very Likely (70% to 90%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 346 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 5 | 5 | Senior Leaders Briefing | 2023-04-17 19:38 | 0 | 6361 | Demetria | Christo | 299 | 299 | 0 | 0 | 0
2 | CNT-2 | 3631 | RumaylanDetention Facility | 509717 | Bond Waiver | Contract Acquisition | 3 | Bonds provide a guarantee that a contractor will fulfill all of their obligations under a construction contract. Without bonds, and if KTR defaults, there is no surety to take over contract to completion; there is no financial compensation to the owner in case a contractor fails to complete the contract. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | There are no banks in Syria. There is no way to bond. |  |  | 1 | Contracting | CNT | 8912 |  | 5 | Other |  | 10 | 4 | 0 | 34717281 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 24 |  | 41 | 41 | Contract Required Complete | 2023-02-26 22:55 | 0 | 8912 | Molly | Shannon | 299 | 299 | 0 | 0 | 1
1 | RLE-1 | 3652 | DE Inland Bay/Bay Coast | 402963 | Acquisition | Stakeholder, Sponsor or Partners | 9 | The acquisition of houses that are not suitable to be raised may need to be acquired. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 18 | Real Estate | RLE | 863 |  | 5 | Other | The unexpected acquisition of houses could be a major impact to performance given the additional time, effort, and cost added if acquisition is needed. | 10 | 3 | 0 | 0 | 1000000 | Estimated cost at $1 million until we have additional real estate information. | 0 | 365 | 1095 | 3 years assumed for the longest time to acquire a home. Will be updated if more info is obtained. | 3 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-04-25 12:38 | 0 | 8780 | Laura | Searles | 306 | 302 | 0 | 0 | 0
2 | OTH-2 | 3652 | DE Inland Bay/Bay Coast | 402963 | $2 Million Study Budget Limitation | Agency Policy and Process | 7 | The total study budget is $2 million with no ability for non-federal sponsor contributions. With a smaller budget, the PDT will need to formulate on lessons learned and will potentially not be able to formulate to the highest standard. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | This will significantly impact the project since the FCSA is signed and based on communication with the non-federal sponsor. |  |  | 12 | Other | OTH | 3290 |  | 8 | Agency Strategy | This risk constrains the geographic scope and the examination of alternatives. It also constrains the level of detail able to be explored and there are no opportunities for adding additional members of the PDT for expertise. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-24 17:16 | 0 | 8780 | Laura | Searles | 302 | 299 | 0 | 1 | 0
3 | PLE-3 | 3652 | DE Inland Bay/Bay Coast | 402963 | CBRA Compliance | Agency Policy and Process | 7 | USFWS may not accept several alternatives, and there are multiple CBRA units in our study area. | 4 | Very Likely | Very Likely (70% to 90%) | It is very likely that the USFWS will not allow certain alternatives to move forward. |  |  | 16 | Planning - Environmental | PLE | 863 |  | 5 | Other | The PDT will likely make decisions to avoid CBRA Areas which may impact the performance of the alternatives. | 5 | 2 | 0 | 5000 | 25000 | If we try to circumvent the compliance, the PDT could spend additional money with no positive result. | 0 | 25 | 150 | If we try to circumvent the compliance, the PDT could spend additional time with no positive result. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-12 14:43 | 0 | 8780 | Laura | Searles | 302 | 302 | 0 | 0 | 0
4 | RLE-4 | 3652 | DE Inland Bay/Bay Coast | 402963 | Real Estate Requirements | Stakeholder, Sponsor or Partners | 9 | Public participation and acceptance of required standard estates. The number of stakeholders and property owners in the study area is significant. Some private lands may be required for the project. Any real estate that cannot be acquired without court processes may negatively impact the acquisition schedule. | 3 | Likely | Likely (50% to 70%) |  |  |  | 18 | Real Estate | RLE | 863 |  | 5 | Other |  | 5 | 2 | 0 | 10000 | 150000 |  | 0 | 160 | 720 |  | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 11 | 11 | Complete Real Estate Acquisition | 2023-05-12 14:48 | 0 | 863 | Andrew | Roach | 302 | 302 | 0 | 0 | 0
5 | EHH-5 | 3652 | DE Inland Bay/Bay Coast | 402963 | Inlet Surge Barriers Feasibility | Info and Data Analysis | 1 | May need additional/high fidelity modeling for design of inlet alternatives | 2 | Unlikely | Unlikely (30% to 50%) | Inlet barrier alternatives have significant constraints on feasibility, including CBRA, estimated cost derived from similar studies, real estate risk, and environmental impact. H&H is one risk component of overall high risk alternative. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 863 |  | 5 | Other |  | 5 | 2 | 50000 | 75000 | 500000 | If Inlet barrier alternatives are moved forward past the AMM, based on modeling that would be needed, the internal cost could be up to 500000 | 0 | 365 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-24 17:18 | 0 | 863 | Andrew | Roach | 302 | 299 | 0 | 0 | 0
6 | PLP-6 | 3652 | DE Inland Bay/Bay Coast | 402963 | Study Area Expanding after AMM | Stakeholder, Sponsor or Partners | 9 | Study authorization allows for study area of entire coast of Delaware. NFS focus for coastal storm risk is on Inland Bays. NFS has related that multiple studies are ongoing in Wilmington Area for flood risk management. NAP has recently completed the Dredged Material Utilization study, which has been authorized in WRDA 2020 and amended in WRDA 2022. This would provide coastal storm risk reduction for communities on Delaware Bay Coast. Inland Bays area has had very little attention for back-bay flood risk reduction. Study risk is including additional areas beyond the Inland Bays post-AMM. | 4 | Very Likely | Very Likely (70% to 90%) | Early planning decision made in concert with NFS and relayed and agreed to by NFS leadership. |  |  | 13 | Planning - Plan Formulation | PLP | 863 |  | 5 | Other | If larger study area is carried through, project could run out of funding and be terminated. | 10 | 3 | 75000 | 0 | 200000 | Additional EN modeling and economic modeling and data collection. If inclusion of DE Bay coast and residual risk of DMU communities, cost would be lower. If inclusion of Wilmington Area, cost would be high. | 90 | 0 | 365 | If inclusion of DE Bay coast and residual risk of DMU communities, time would be lower. If inclusion of Wilmington Area, time would be high. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-24 17:49 | 0 | 863 | Andrew | Roach | 306 | 306 | 0 | 0 | 0
7 | PRM-7 | 3652 | DE Inland Bay/Bay Coast | 402963 | PDT Workload and Turnover | Resource Availability | 5 | PDT workload on other projects and turnover of key PDT members over the course of the study could impact schedule and budget. | 4 | Very Likely | Very Likely (70% to 90%) | PDT members have already begun to turnover during first study phase. |  |  | 17 | Project Management | PRM | 3290 |  | 5 | Other | Impact to schedule and budget. | 5 | 2 | 50000 | 100000 | 150000 |  | 90 | 180 | 360 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-28 14:20 | 0 | 863 | Andrew | Roach | 302 | 302 | 0 | 0 | 0
8 | EHH-8 | 3652 | DE Inland Bay/Bay Coast | 402963 | Interior Drainage | Info and Data Analysis | 1 | Uncertainty of impacts of alternatives to interior drainage systems, and adjustments that may be necessary to incorporate. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 863 |  | 5 | Other |  | 5 | 2 | 0 | 15000 | 50000 |  | 0 | 25 | 250 |  | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 10 | 10 | Concept Design Phase (35%) | 2023-05-12 15:05 | 0 | 863 | Andrew | Roach | 302 | 302 | 0 | 0 | 0
9 | PLE-9 | 3652 | DE Inland Bay/Bay Coast | 402963 | Identification of economic study area | Info and Data Analysis | 1 | Structures not included in structure inventory could incur damage. | 2 | Unlikely | Unlikely (30% to 50%) | Using combined NSI and sponsor data for study area. May miss structures incurring damage outside of study area. |  |  | 15 | Planning - Economics | PLE | 863 |  | 5 | Other |  | 5 | 2 | 0 | 5000 | 50000 |  | 0 | 5 | 25 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-12 15:18 | 0 | 863 | Andrew | Roach | 302 | 302 | 0 | 0 | 0
10 | PLE-10 | 3652 | DE Inland Bay/Bay Coast | 402963 | Structure Characteristics | Info and Data Analysis | 1 | NSI and local structure data may not accurately characterize the structure characteristics such as type of structure, first floor elevation, etc. Many structures have been elevated in the study area and this condition may not be captured in data. | 3 | Likely | Likely (50% to 70%) |  |  |  | 15 | Planning - Economics | PLE | 863 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-28 14:39 | 0 | 863 | Andrew | Roach | 299 | 299 | 0 | 0 | 0
11 | EHH-11 | 3652 | DE Inland Bay/Bay Coast | 402963 | Sea Level Change Impacts to the Floodplain | Info and Data Analysis | 1 | There is a significant difference in preliminary curves at the low/intermediate/ and High SLC scenarios. It is possible that the formulation will change depending on the accuracy of the FWOP floodplain at both the 50-year and 100-year horizons. 50-year for quantitative analysis and 100-year for qualitative analysis. | 3 | Likely | Likely (50% to 70%) | Given the current projections of sea level rise, this risk is likely to impact the plans and implementation of design over time. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 863 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-24 17:51 | 0 | 8780 | Laura | Searles | 299 | 299 | 0 | 1 | 1
12 | OTH-12 | 3652 | DE Inland Bay/Bay Coast | 402963 | Utilities in the Project Area | Site Conditions | 6 | Failure to identify utilities affected by proposed structural solutions may impact schedule, cost, and design. | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 12 | Other | OTH | 3290 |  | 6 | Compliance |  | 5 | 2 | 0 | 100000 | 500000 | Dense urban environment, mapping utilities, private and public is not always accurate, or done at all. If utilities are discovered that impact constructability, or implementation, it could increase costs significantly. | 0 | 180 | 500 |  | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-05-01 12:23 | 0 | 8780 | Laura | Searles | 302 | 302 | 0 | 0 | 0
13 | EGT-13 | 3652 | DE Inland Bay/Bay Coast | 402963 | Materially different site conditions | Site Conditions | 6 | Site characterization for potential subsurface construction will not be conducted until the PED Phase. Construction costs could increase significantly depending on subsurface conditions and unanticipated foundation conditions on or off-shore. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 3 | Engineering - Geotechnical | EGT | 3290 |  | 5 | Other |  | 5 | 2 | 0 | 50000 | 500000 |  | 0 | 50 | 299 | Depending on the alternatives in the Final Array, the Engineering team may need longer to gather enough data for the risk informed design process. Additionally, the qualitative risk assessment and the CSRA will need to account for the uncertainty of subsurface conditions. If not, the risk of insufficient construction costs may be realized. | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-05-01 12:29 | 0 | 8780 | Laura | Searles | 302 | 302 | 0 | 0 | 0
14 | COM-14 | 3652 | DE Inland Bay/Bay Coast | 402963 | Recommending Features that Cut off access to water | Stakeholder, Sponsor or Partners | 9 | Building of structures could reduce access to the water's edge or to existing docks that would impact the recreational use of the areas. Without risk management and comprehensive benefits planning it is likely that NED planning will point to hardening shoreline and blocking access to the water as part of risk management. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 20 | Public Affairs | COM | 3290 |  | 7 | Agency Reputational | The worst-case scenario is an unwilling sponsor and a terminated study. The more likely scenario is going out for public review after TSP and getting significant push-back requiring some reformulation. Reformulation will likely require a second release for NEPA. | 5 | 2 | 0 | 9998 | 50000 | Pushback from the communities could cause the plans to be stymied and additional funding spent. | 0 | 20 | 70 | Pushback from the communities could cause the plans to be stymied and additional funding spent. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-24 17:53 | 0 | 8780 | Laura | Searles | 302 | 302 | 0 | 0 | 0
15 | EHH-15 | 3652 | DE Inland Bay/Bay Coast | 402963 | Sea Level Change Model Assumption | Info and Data Analysis | 1 | Actual sea level elevation change could be greater than existing forecast models' range and resulting plans may be under-engineered. | 2 | Unlikely | Unlikely (30% to 50%) | Due to increased recent storms nationwide and given the range of possible sea level rise scenarios, there remains a chance that true mean sea level rise will fall outside of model expectations. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 863 |  | 8 | Agency Strategy |  | 5 | 2 | 0 | 5000 | 100000 | Cost varies depending on the assumed risk incorporated in the construction phase, but cost will likely be unrealized until additional data increases accuracy of current models. If sea level rise is higher in real time than what was modeled, then the rate and volume of sand erosion could be much higher. That would necessitate more frequent and or larger volumes of sand replenishment. If sea level rise is lower than what was modeled, then we may be over engineering a solution and less material/frequent nourishment would be needed. | 0 | 0 | 250 | If the team is directed to conduct additional modeling under a different sea level change scenario it would lengthen the impact analysis and evaluation phase, this could postpone dates to reach TSP. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-12 15:07 | 0 | 8780 | Laura | Searles | 302 | 306 | 0 | 0 | 0
17 | EGT-17 | 3652 | DE Inland Bay/Bay Coast | 402963 | Availability of Compatible Sediment Material | Site Conditions | 6 | Beach Nourishment and NNBF options such as marsh or wetland restoration may be ineffective or unjustifiable due to cost if not enough compatible sediment material is available. A realization of the risk might be that finding additional or alternative material for use would require additional time and would likely be much more costly than using materials found close to the site. | 4 | Very Likely | Very Likely (70% to 90%) | The risk is currently very likely since there are not any beneficial reuse areas identified that are not already in use for Beach Restoration. |  |  | 3 | Engineering - Geotechnical | EGT | 3290 |  | 5 | Other |  | 5 | 2 | 0 | 100000 | 200000 |  | 0 | 365 | 0 |  | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 8 | 8 | Design Start | 2023-05-01 18:11 | 0 | 8780 | Laura | Searles | 302 | 299 | 0 | 0 | 0
19 | PLE-19 | 3652 | DE Inland Bay/Bay Coast | 402963 | HTRW On the Project Sites | Legal or Regulatory Actions | 10 | There are two Superfund sites within the study area. Both are located in Millsboro, one at 199 Mitchell Street and one at 225 W Dupont Boulevard. One of the alternative includes small barriers on tributaries that are adjacent to the Superfund Site located at 199 Mitchell Street. | 2 | Unlikely | Unlikely (30% to 50%) | Given current conditions, the Alternative to put small barriers on a few tributaries in Millsboro may be directly next to or impacted by a Superfund site. |  |  | 16 | Planning - Environmental | PLE | 863 |  | 6 | Compliance | If we were to determine that the barrier for Alternative 3 at the tributary needs to cross the Superfund site at Mitchell avenue, it would impact the performance of the protection given and might cause more issues in that area. | 5 | 2 | 0 | 2000 | 20000 |  | 0 | 20 | 365 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-24 17:33 | 0 | 8780 | Laura | Searles | 302 | 302 | 0 | 0 | 0
20 | PLE-20 | 3652 | DE Inland Bay/Bay Coast | 402963 | Risk of Not Completing EA within the 1 yr Timeline | Agency Policy and Process | 7 | Risk that if decision to draft an EA is made early on in the process, the EA timeline of 1 year will go into effect but EA would not be able to be completed within 1 year, following the feasibility study timeline. A waiver for time requirements on an EA would need to be requested. | 3 | Likely | Likely (50% to 70%) | Likely if decision is made to draft EA. |  |  | 16 | Planning - Environmental | PLE | 5627 |  | 5 | Other |  | 5 | 0 | 1000 | 0 | 5000 | Funds would be needed to prepare and coordinate EA timeline waiver submittal and processing. | 10 | 0 | 30 | Time needed to prepare and submit EA timeline waiver. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-24 17:31 | 0 | 5627 | Vanessa | Ciaramellano Campbell | 306 | 306 | 1 | 0 | 0
21 | PLE-21 | 3652 | DE Inland Bay/Bay Coast | 402963 | EIS Potential Need for Additional Funding | Resource Availability | 5 | If significant impacts are anticipated and an EIS is to be prepared, additional funds and time would be needed for the preparation (when compared to an EA). Additional funding needed for an EIS may impact overall limited feasibility study budget of $2 million. | 2 | Unlikely | Unlikely (30% to 50%) | May occur if measures anticipated to have significant impacts move forward. |  |  | 16 | Planning - Environmental | PLE | 5627 |  | 5 | Other |  | 10 | 3 | 100000 | 150000 | 200000 |  | 365 | 0 | 730 | Time limit of two years to complete an EIS per new NEPA rules. | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-24 17:21 | 0 | 5627 | Vanessa | Ciaramellano Campbell | 302 | 306 | 0 | 0 | 0
22 | PLC-22 | 3652 | DE Inland Bay/Bay Coast | 402963 | Cultural Resource Investigations | Legislative or Political | 8 | Although the project is not expected to have more than negligible adverse impacts on historic properties, there is a risk that additional cultural resource investigations would be required if we do not know the information now. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Given that the existing cultural resources have been reviewed before in a few locations in this area, there is limited data right now and additional investigations might be needed. |  |  | 14 | Planning - Cultural Resources | PLC | 8780 |  | 5 | Other |  | 5 | 2 | 0 | 15000 | 0 |  | 0 | 50 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-16 16:22 | 0 | 8780 | Laura | Searles | 299 | 299 | 0 | 0 | 0
23 | OTH-23 | 3652 | DE Inland Bay/Bay Coast | 402963 | Additional Traffic and Surveys Analysis | Site Conditions | 6 | Currently, the PMP does not include or assume costs for traffic analysis or surveys for the site in the Planning phase. | 2 | Unlikely | Unlikely (30% to 50%) | This is likely to impact the project since without surveyed data, the plans in PED phase might be inaccurate and lead to mistakes in design. |  |  | 12 | Other | OTH | 3290 |  | 5 | Other |  | 5 | 2 | 0 | 50000 | 0 |  | 0 | 100 | 0 |  | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-06-16 16:25 | 0 | 8780 | Laura | Searles | 299 | 299 | 0 | 0 | 0
1 | PRM-1 | 3653 | 2024 Dredging Project, Military Ocean Terminal Concord (MOTCO), CA. |  | Overlapping projects with the boat ramp, dredging and levee | Site Conditions | 6 | Unexpected additional environmental compliance coordination and review required for the Boat Ramp project at MOTCO. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 17 | Project Management | PRM | 4571 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 9 | Design | 32 | 32 | Receive Concept (30%) | 2023-03-14 20:11 | 0 | 4571 | Brian | Gerrity | 299 | 299 | 0 | 0 | 0
1 | PLP-1 | 3654 | Keystone Dam – Wedge (495646) |  | Review Risk (level of review) | Agency Policy and Process | 7 | Our current schedule assumes that we would not have any significant changes to the analysis or TSP that would require us to go back through ATR or QCC. If we did need to revisit the ATR or QCC, the October 2023 DSOG would not be feasible. The current path is that we are only refining the previously identified TSP. Anything outside of this would trigger re-formulation and would keep us from presenting our TSP to the DSOG in October. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 28 |  | 5 | Other |  | 5 | 0 | 0 | 200000 | 0 | Accounts reformulation, DQC, ATR and QCC. | 0 | 365 | 0 | It would be a one year total schedule slip. It would take 6 months to get back to DSOG with a TSP, but we would miss the 1 June approval date deadline. | 4 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-13 19:51 | 0 | 28 | Jami | Buchanan | 299 | 299 | 1 | 0 | 0
2 | PLE-2 | 3654 | Keystone Dam – Wedge (495646) |  | NEPA Related Schedule Risks | Agency Policy and Process | 7 | We currently assume the NEPA document will not need significant refinement after DSOG and will be ready for public review within 2-3 weeks after DSOG. If the DSOG significantly changes the TSP and substantial re-coordination or revisions to the NEPA document are required we will need to add time into the schedule. Depending on the magnitude of changes, this may affect our ability to secure a 1 June approval for the DSMR. | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 16 | Planning - Environmental | PLE | 28 |  | 6 | Compliance | Could be major depending on the magnitude of changes. | 5 | 2 | 0 | 25000 | 0 |  | 0 | 60 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-13 19:58 | 0 | 28 | Jami | Buchanan | 299 | 299 | 0 | 0 | 0
3 | PRM-3 | 3654 | Keystone Dam – Wedge (495646) |  | Contract for Risk Assessment Work | Contract Acquisition | 3 | It was recommended to the PDT that they contract with an external structural expert to support the team in the reevaluation of two structural failure modes. The onboarding process for this external resource has been lengthy and has delayed the ECRA update. This affects not only the ECRA but the re-evaluation of RMPs and puts the schedule at risk. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | The schedule has already been impacted. It is now a matter of the magnitude of that impact. |  |  | 17 | Project Management | PRM | 28 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 90 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-13 20:07 | 0 | 28 | Jami | Buchanan | 299 | 299 | 1 | 1 | 0
4 | PRM-4 | 3654 | Keystone Dam – Wedge (495646) |  | Sufficiency of the Refined ECRA | Agency Policy and Process | 7 | We are assuming that the updated ECRA will be accepted by the July DSOG. If it is not, there will be budget and schedule impacts to account for further refinement. | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 17 | Project Management | PRM | 28 |  | 5 | Other |  | 5 | 0 | 0 | 75000 | 0 |  | 0 | 90 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-13 20:31 | 0 | 28 | Jami | Buchanan | 299 | 299 | 1 | 0 | 0
5 | PLP-5 | 3654 | Keystone Dam – Wedge (495646) |  | DSOG Refinements to TSP | Agency Policy and Process | 7 | There is a risk that DSOG may or may not endorse all of the measures in the TSP. Refinements to the TSP could be costly and time consuming, putting the schedule at risk. | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 28 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 | Cost impact is unknown. | 0 | 0 | 0 | Schedule impact is unknown. | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-13 20:31 | 0 | 28 | Jami | Buchanan | 299 | 299 | 1 | 0 | 0
6 | EHH-6 | 3654 | Keystone Dam – Wedge (495646) |  | Reevaluation of Hydrology Based on Policy Changes | Agency Policy and Process | 7 | The way the agency evaluates risk associated with the Probable Maximum Flood changed during development of the DSMS. The PDT will perform an evaluation using this new methodology. The results have the potential to impact the identified TSP, potentially requiring a larger dam raise than what has been previously evaluated. | 4 | Very Likely | Very Likely (70% to 90%) | The degree of change is currently unknown. The PDT will re-evaluate the new proposed top of dam and evaluate risk under the new PMF condition. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 28 |  | 5 | Other |  | 5 | 0 | 0 | 50000 | 0 |  | 0 | 30 | 0 | This assumes this analysis does not impact plan formulation. (ie. the dam cannot be raised high enough) | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-13 20:27 | 0 | 28 | Jami | Buchanan | 299 | 299 | 1 | 0 | 0
1 | EGT-1 | 3671 |  |  | Big Scary Risk | Site Conditions | 6 | Sink Holes everywhere | 5 | Extremely Likely | Extremely Likely (90% to 100%) | Geotechnic surveys |  |  | 3 | Engineering - Geotechnical | EGT | 6867 |  | 2 | Environmental | doesn't work to keep out carp | 10 | 4 | 10000 | 10000 | 500000 | So much evidence | 1 | 100 | 365 |  | 4 | 1 | 1 | Active | 6 | Construction | 21 | 21 | Project Acceptance | 2023-05-18 20:26 | 0 | 6867 | Kayleigh | Thomas | 299 | 306 | 0 | 0 | 0
2 | ECV-2 | 3671 |  |  | Other RIsk | Contract Performance | 4 |  | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 9 | Engineering - Civil | ECV | 6847 |  | 5 | Other |  | 5 | 0 | 0 | 50000 | 0 |  | 0 | 150 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-20 19:59 | 0 | 6867 | Kayleigh | Thomas | 299 | 299 | 1 | 0 | 0
6 | EHH-6 | 3677 | Capstone |  | Hurricane Model Uncertainty | Info and Data Analysis | 1 | Understanding of hurricane frequency and magnitude, model selected, influence from sea level rise, impacts from climate change, are a risk to the project. Impacts to the plan selection and design. | 3 | Likely | Likely (50% to 70%) | There is uncertainty inherent in any model. We are certain about the range of uncertainty of the selected hurricane model based on the model documentation. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7329 |  | 8 | Agency Strategy |  | 5 | 2 | 0 | 0 | 80000 | If existing model is acceptable, no additional cost to project. If new model is needed, development of new model is anticipated to cost $80,000. | 30 | 60 | 363 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:35 | 0 | 7329 |  |  | 306 | 302 | 0 | 0 | 0
9 | PLC-9 | 3677 | Capstone |  | Historic properties in a historic district | Site Conditions | 6 | There are X number of historic districts, x number of historic properties. We need to be able to identify the properties that will be effected by flooding or are below X elevation. The source/database of identification of the properties may not be complete. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | Not all historic properties are within the database. We do know that there are a significant number of historic properties but where they are located within the flooding area that was identified is unknown. |  |  | 14 | Planning - Cultural Resources | PLC | 8953 |  | 6 | Compliance | SHPO coordination can effect the project outcome and identification of TSP | 10 | 4 | 0 | 500000 | 0 | You would need additional surveys to identify areas to minimize data gaps. | 0 | 180 | 0 | Gathering additional data does take time and could impact construction going forward. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 14:21 | 0 | 8952 |  |  | 299 | 299 | 0 | 0 | 0
13 | EHH-13 | 3677 | Capstone |  | 200-year level of protection requested by non-fed sponsor | Info and Data Analysis | 1 | The Non-Federal Sponsor's objective is to achieve a 200-year interval level of protection for urban and urbanizing areas. The uncertainty is regarding the level of accuracy with 200-year modeling and projections, and how to analyze that, how it effects economics, and therefore the overall future justification of the project and proposed TSP. | 4 | Very Likely | Very Likely (70% to 90%) | Team expertise and prior project experience |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8934 |  | 8 | Agency Strategy | Will influence alternatives development and TSP outcome | 10 | 4 | 50000 | 100000 | 250000 | Assumptions based on team expertise, assumptions of study area, and prior experience | 0 | 60 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:27 | 0 | 8934 |  |  | 302 | 299 | 0 | 0 | 0
14 | EHH-14 | 3677 | Capstone |  | Model Accuracy | Info and Data Analysis | 1 | Model uses H&H data that is older than 10 years | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Water surface elevations have not significantly changed in the last few years. The water surface elevation data should still be applicable. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 5627 |  | 5 | Other |  | -5 | 0 | 0 | 0 | 100000 | On the low end if the model needs minimal updates, the cost would be minimal. If model needs to be updated the costs might be up to 100K. | 30 | 0 | 90 | If updates are needed to model, 3 months are needed. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:23 | 0 | 5627 | Vanessa | Ciaramellano Campbell | 306 | 306 | 1 | 0 | 0
15 | EHH-15 | 3677 | Capstone |  | Effects of Sea Level Rise on Project Design | Site Conditions | 6 | Sea level rise may exceed water levels in everglades that we are basing designs on | 4 | Very Likely | Very Likely (70% to 90%) | We may choose a sea level curve model result to design to that differs from future actual sea level rise conditions/elevations |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7650 |  | 2 | Environmental | if sea level rise projections do not accurately capture the future sea level rise and storm surge risk, the project may not perform as projected | 10 | 4 | 500000 | 800000 | 1500000 | Cost comparison of measures needed based on low, med, high sea level rise | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:24 | 0 | 7650 | Keith | Hannon | 302 | 299 | 0 | 0 | 1
16 | PLC-16 | 3677 | Capstone |  | Unknown Historical Shipwrecks | Site Conditions | 6 | There is a potential for cultural resources to impact further widening or deepening of the channel, specifically a historical (pirate) shipwreck in the area of the dredging. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | The channel has been established for a substantial amount of time, so most cultural resources have probably been discovered prior to any dredging the may occur. Risk will increase if the channel is widened or a new channel is established. |  |  | 14 | Planning - Cultural Resources | PLC | 7308 |  | 2 | Environmental | The assumption is the discovered cultural resources would be a relatively small archaeological site, which would not substantial impact the overall project goal. | 5 | 2 | 0 | 1000000 | 0 | If cultural resources are discovered, there would have to be an excavation and recovery of the resources. | 0 | 730 | 0 | If cultural resources are discovered, the schedule would be pushed back by 2 years due to excavation and hurricane season. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-03-14 14:26 | 0 | 7308 |  |  | 299 | 299 | 0 | 0 | 0
18 | EHH-18 | 3677 | Capstone |  | Hurricane Model Uncertainty | Info and Data Analysis | 1 | Hurricane Frequency, Hurricane intensity, Model Selection, Hurricane influence from sea level rise, Hurricane variability from the gulf stream -Knowing the full extent of the hazard will determine our selection | 3 | Likely | Likely (50% to 70%) | Historic model validation, some spaghetti model lines are right sometimes and other times they are wrong |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7707 |  | 8 | Agency Strategy | Model Section will impact all csrm studies and decision making | 10 | 3 | 80000 | 0 | 3000000 | If existing model is successful, we assume the run costs would be $80k. If model is unsuccessful, estimated cost of new model is $3M | 30 | 120 | 363 | Lot of unknowns | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 14:30 | 0 | 7893 |  |  | 306 | 302 | 0 | 0 | 0
19 | EHH-19 | 3677 | Capstone |  | Hurricane model uncertainty | Info and Data Analysis | 1 | Uncertainty involved with forecasting the timing, frequency, and intensity of hurricane events. Secondary info uncertainty is related to hurricane related storm surge and sea level rise with regard to changing conditions in the future under climate change. The risk is directly associated with designing to a specific level of frequency and intensity, but with future conditions changing under climate change, the design may turn out being inadequate with inaccurate predictions. | 3 | Likely | Likely (50% to 70%) | Model accuracy is never 100%. Even the most current models are subject to changing environmental conditions. Model outputs should provide uncertainty likelihood in their results. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7329 |  | 3 | Human Health and Safety | Model selection has the potential to impact the project greatly. | 10 | 3 | 80000 | 0 | 3000000 | Model cost $80,000 to runs as is, if the need arises to create a new model with future climate changes incorporated the price could inflate to 3 mil. | 30 | 120 | 363 | Model run as is could be within 30-120 days. If new model needs created it could push schedule significantly. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 14:30 | 0 | 7707 |  |  | 306 | 302 | 0 | 0 | 0
20 | EPE-20 | 3677 | Capstone |  | Potential to negatively impact water rights in project area | Stakeholder, Sponsor or Partners | 9 | Existing water rights by farmers or others may be negatively impacted by project features aiming to reduce flood risk. For example, if a reservoir is selected it may impact downstream water uses. Or new levees could damage irrigation rights. | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 21 | Construction - Project Engineer | EPE | 5210 |  | 5 | Other |  | 5 | 0 | 0 | 20000 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-03-14 14:18 | 0 | 5210 |  |  | 299 | 299 | 1 | 0 | 1
25 | EHH-25 | 3677 | Capstone |  | Utilizing existing outdated H&H model | Info and Data Analysis | 1 |  | 1 | Very Unlikely | Very Unlikely (5% to 30%) | unlikely because water levels have not changed above the threshold needed to create a new model. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 731 |  | 5 | Other |  | -5 | 1 | 100000 | 200000 | 750000 |  | 0 | 0 | 90 |  | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:28 | 0 | 8007 |  |  | 306 | 306 | 0 | 0 | 0
26 | PLE-26 | 3677 | Capstone |  | HTRW Identified | Site Conditions | 6 | Presence of HTRW may limit or constrain areas of disturbance, requiring elimination or re-evaluation of measures and alternatives. | 3 | Likely | Likely (50% to 70%) | Historic contamination, commonly encountered in deep draft harbors |  |  | 16 | Planning - Environmental | PLE | 4441 |  | 5 | Other | Maintenance dredging and associated studies should reduce the amount of uncertainty, so any additional HTRW encountered should be on the margins of the channel | 5 | 2 | 0 | 100000 | 0 | Re-evaluation of measures will be required | 90 | 0 | 180 | Re-evaluation and additional sampling may be required | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-06-06 13:04 | 0 | 7949 | Jennie | Brancho | 299 | 306 | 0 | 0 | 0
27 | PLP-27 | 3677 | Capstone |  | Public Perception | Stakeholder, Sponsor or Partners | 9 | Public perception and willingness to collaborate on the project. Risk of neighboring landowners and stakeholders to object the project and impair implementation. | 3 | Likely | Likely (50% to 70%) | Ecosystem restoration project would likely be seen as beneficial to the community, but existing stakeholder perspectives are unknown. Adjacent landowners may be unwilling to allow necessary access to land for project implementation and maintenance. |  |  | 13 | Planning - Plan Formulation | PLP | 9132 |  | 1 | Asset Condition | Scope of project may be reduced if cooperation cannot be achieved with neighboring landowners. | 5 | 2 | 0 | 0 | 2000000 | Cost per acre near the project site is $200,000 | 0 | 0 | 365 | Up to one year of additional time added to the schedule to accommodate public meetings, engagement with landowners, legal process to obtain land, etc. | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-06-06 13:15 | 0 | 9132 | Cara | Pattullo | 306 | 306 | 0 | 0 | 0
29 | PLC-29 | 3677 | Capstone |  | Possible Tribal impacts for San Joaquin River | Site Conditions | 6 | Unknown cultural resources in project study area could affect cost (possible Archeological surveys required). Could affect ability to work in certain areas. | 3 | Likely | Likely (50% to 70%) |  |  |  | 14 | Planning - Cultural Resources | PLC | 6000 |  | 1 | Asset Condition |  | 10 | 3 | 50000 | 250000 | 500000 |  | 180 | 0 | 540 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-06-06 13:07 | 0 | 6587 | Madeleine | Dewey | 302 | 306 | 0 | 0 | 0
30 | EGT-30 | 3677 | Capstone |  | Lack of geotechnical data. | Site Conditions | 6 | Due to leaking levees, it is suspected that geotechnical issues will be a problem within the project area. Unknown geotechnical conditions may drastically change effective measures and project cost. | 3 | Likely | Likely (50% to 70%) | We believe this is likely because of known seepage and slope stability of existing levees. |  |  | 3 | Engineering - Geotechnical | EGT | 5902 |  | 1 | Asset Condition | Constructed aspects of the project could not be feasible or could fail due to poor geotechnical data. | 10 | 3 | 200000 | 3000000 | 3000000 | Experience | 0 | 1095 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-06 13:07 | 0 | 6807 | Steele | Mcfadden | 299 | 299 | 0 | 0 | 0
33 | PLE-33 | 3677 | Capstone |  | Population Growth and Development in the Project Area | Info and Data Analysis | 1 | We are unsure about the rate of population growth and urban development in Norfolk in the future without project and future with project conditions. Possible sources of this data would include US census bureau population projections, and the City of Norfolk's 2030 Master Plan. If population growth and/ or development rates are inaccurately forecasted, the PDT may not be able to accurately capture economic benefits. | 2 | Unlikely | Unlikely (30% to 50%) | Track actual vs projected growth in Norfolk over the past 30 years. Cross reference census and master plan data to see if there is a difference. |  |  | 15 | Planning - Economics | PLE | 8070 |  | 5 | Other | Not a large risk to project performance. | 5 | 2 | 0 | 0 | 50000 | Cost of additional economic effort for sensitivity analysis and cross referencing growth rates. | 0 | 0 | 60 | This task may add up to 60 days to the project schedule. The PDT may be able to run this task concurrently with HEC-FDA analysis. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-06 13:15 | 0 | 8070 | Nickolas | Emilio | 306 | 306 | 0 | 0 | 0
35 | EHH-35 | 3677 | Capstone |  | achievability of flow rate? | Site Conditions | 6 | It may not be possible to restore the flow based on constraints of the built environment. | 3 | Likely | Likely (50% to 70%) | Previous project designed to redirect flow to allow for development. This constraint may impede the ability to restore flow to this area. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7507 |  | 1 | Asset Condition |  | 10 | 3 | 0 | 400000 | 0 | H&H will likely have to perform robust modeling to assess the ability to restore flow in newly developed area. | 180 | 180 | 270 |  | 4 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-06 13:10 | 0 | 3573 | Christopher | Solek | 299 | 306 | 0 | 0 | 0
38 | EGT-38 | 3677 | Capstone |  | Subsurface conditions | Site Conditions | 6 | Some site specific measures may require geotechnical investigations to adequately manage cost contingencies. Existing subsurface data may be limited or not exist in the area of some structural measures. Assumptions and use of exiting data may lead to high cost contingencies. | 3 | Likely | Likely (50% to 70%) | Geotechnical data is limited. Some areas may have no subsurface information. Conservative estimates on subsurface work may be required leaded to high cost contingencies. |  |  | 3 | Engineering - Geotechnical | EGT | 4826 |  | 5 | Other |  | 5 | 0 | 20000 | 400000 | 600000 | Cost of approximately 10 borings at 3 locations. | 0 | 0 | 0 | This would have no schedule impact. This could be performed immediately once site specific measures are realized. | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-06 13:10 | 0 | 4826 | Ryan | Crane | 302 | 299 | 1 | 0 | 1
2 | EHH-2 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Sea Level Rise Model Assumption | Info and Data Analysis | 1 | Actual sea level elevation change could be greater than existing forecast models' range and resulting plans may be under-engineered. | 2 | Unlikely | Unlikely (30% to 50%) | Due to increased recent storms nationwide and given the range of possible sea level rise scenarios, there remains a fair chance of true mean sea level rise falling outside of model expectations. #Note: Need additional feedback on this |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3850 |  | 8 | Agency Strategy | Risk that proposed, recommended plan, would be insufficient or overconstructed to solve the erosion problem. | 10 | 3 | 0 | 0 | 1 | Cost varies depending on the assumed risk incorporated in the construction phase, but cost will likely be unrealized until additional data increases accuracy of current models. If sea level rise is higher in real time than what was modeled, then the rate and volume of sand erosion could be much higher. That would necessitate more frequent and or larger volumes of sand replenishment. If sea level rise is lower than what was modeled, then we may be over engineering a solution and less material/frequent nourishment would be needed. #Need further feedback to access risk cost | 0 | 0 | 0 | If the team is directed to conduct additional modeling under a different sea level change scenario it would lengthen the impact analysis and evaluation phase, this would postpone dates to reach TSP. #Need further feedback to access schedule impact | 1 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-03-22 22:24 | 0 | 8413 | Jorge | Hernandez-Limon | 306 | 299 | 0 | 0 | 0
4 | EHH-4 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Economic & Hydraulic Model Approval | Agency Policy and Process | 7 | Economic and hydraulic models are assumed to be approved for single use within the time constraints of the study. Deviation from our assumed times will increase duration of project and cost. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Based on our previous communication with CSRM-PCX, we have reason to believe that the approval of the model is unlikely to be rejected or delayed. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3850 |  | 6 | Compliance | Rejecting a model would result in setbacks for the project and increased costs, as using alternative models may require additional coordination and a learning curve. | 5 | 2 | 0 | 0 | 0 | Model approval delays would prolong the analysis phase of the project and increase cost while approval is pending. Model rejection would require alternative analysis methodology, significantly increasing labor costs. | 0 | 0 | 0 | Either a delay or rejection of our models will result in schedule setbacks until we either receive approval, or under worst case scenario, find alternative methodology if required to do so. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-23 22:26 | 0 | 8413 | Jorge | Hernandez-Limon | 299 | 299 | 0 | 0 | 0
5 | EHH-5 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Assume Availability of Compatible Sediment Material | Site Conditions | 6 | Beach nourishment may be ineffective with incompatible sediment material currently available. A realization of said risk would require additional time to seek out alternative sediment sources, likely a time draining and costly process. | 2 | Unlikely | Unlikely (30% to 50%) | The site has been nourished prior with available sediment, so it is likely that the available sediment is compatible. # Need more feedback - on amount of sediment available and if it will be sufficient. While prior efforts for nourishment have been done, I believe the scale of our project would be larger and so the amount of sediment needed may not be met. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3850 |  | 5 | Other | Seeking out alternative sediment sources and determining an appropriate method of deliver would be time consuming and therefore increase labor cost for the planning phase. | 10 | 3 | 0 | 0 | 0 | Additional time to find alternative sediment and conduct further analysis to ensure it meets project requirements will increase labor costs, in addition to planning the sediment alternative delivery method. The total project cost would increase, as alternative sediment sources will be more expensive. | 0 | 0 | 0 | Finding alternative sediment will take time, alongside any further analysis required to ensure meets NEPA compliance and required sediment composition. Additionally, the sediment will need to be delivered, and the delivery method will also need additional time. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-24 22:16 | 0 | 8413 | Jorge | Hernandez-Limon | 299 | 299 | 0 | 0 | 0
6 | EHH-6 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Dredge Vehicle Availability | Site Conditions | 6 | Assuming that there is a hydraulic cutterhead dredge, a vessel used to mix dredged sediment to ensure it is uniform. If the alternative hopper type dredge vessel was used, it could result in an incompatible sediment borrow material rendering the nourishment ineffective. We would need to source an appropriate dredge vehicle elsewhere. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Given that this area has previously been nourished regularly, appropriate equipment is expected to have been used and should still be available. #Need feedback on communications with Oceanside or relevant agency on vehicle availability. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3850 |  | 5 | Other | Risk may have small impacts on cost for the planning phase in terms of labor time. #Are there any other potential impacts? | 5 | 2 | 0 | 0 | 0 | Missing the appropriate dredge vessel could increase cost through additional labor cost due to time invested locate an appropriate vessel. | 0 | 0 | 0 | Locating an appropriate vessel, and could take time depending on proximity to providers. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-24 22:49 | 0 | 8413 | Jorge | Hernandez-Limon | 299 | 299 | 0 | 0 | 0
7 | PLE-7 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Project Implementation Impact on Threatened Species | Site Conditions | 6 | Assuming that timing and duration of project implementation will avoid and/or minimize impacts to endangered and threatened species in the project area. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Endangered and threatened species in the area could be placed at unintended risk, potentially violating one of our acts ("endangered species") and increase costs if remediation is necessary. The project is fairly narrow in scope and much of the work (dredging) has been ongoing before, leading to the assumption that project will cause large not external damage. |  |  | 16 | Planning - Environmental | PLE | 953 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 4 | 4 | Inactive – Entered by Error | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-04-03 16:27 | 0 | 8413 | Jorge | Hernandez-Limon | 299 | 299 | 0 | 0 | 0
8 | PLP-8 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Planning Budget Limitation | Agency Policy and Process | 7 | The budget allocated was based on the 2016 labor rates, and so the current funding is out of step with current needs. Due to limited budget, planners time commitment will be limited on project to approximately 25% of weekly available hours, below the suggested amount. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | Prior planning experience suggests a higher time preferred than budget allows; additional funding is unlikely, and we will need to adjust accordingly. |  |  | 13 | Planning - Plan Formulation | PLP | 995 |  | 5 | Other | With limited planning time availability, the report will need to have significantly higher involvement from other team members. | 10 | 4 | 0 | 0 | 0 | No cost change as there are no additional funds available. | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-27 22:39 | 0 | 8413 | Jorge | Hernandez-Limon | 299 | 299 | 0 | 0 | 0
9 | PLE-9 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Project Implementation Impact on Threatened Species | Site Conditions | 6 | Assumption that timing and duration of project implementation will avoid and/or minimize impacts to endangered and threatened species in the project area. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Endangered and threatened species in the area could be placed at unintended risk, potentially violating Endangered Species Act and increase costs if remediation is necessary. The project is narrow in scope and much of the work (dredging) has been ongoing before, leading to the view that the project will have a controlled and limited impact. It would require a very unlikely introduction of |  |  | 16 | Planning - Environmental | PLE | 953 |  | 5 | Other | Under the unlikely scenario of schedule setbacks, depending on the scale of the issue team may have issues with budget a limited budget if significant labor needs to be invested to mitigate negative externalities. | 5 | 2 | 0 | 0 | 0 | The introduction of new unaccounted for threatened species or unanticipated expansion of project scope during the planning phase would increase time and labor for the teams to plan and mitigate around concerns. | 0 | 0 | 0 | The introduction of new unaccounted for threatened species or unanticipated expansion of project scope during the planning phase would increase time and introduce schedule setbacks depending on the scale of the problem. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-03 17:15 | 0 | 8413 | Jorge | Hernandez-Limon | 299 | 299 | 0 | 0 | 0
1 | PRM-1 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Studying two separate FRM (levee) system | Resource Availability | 5 | This feasibility study investigates two entirely separate FRM systems with two NFSs. This is essentially two separate studies rolled into one with the study limitations (3 years and $3 million). The study may require additional time and funding. And it is uncertain if the NFSs will support an extension. However, at this time, it is not clear if the study will need an 3X3X3 exemption. | 3 | Likely | Likely (50% to 70%) | Due to the complexity of the FRM systems and the measures that may be included in the Recommended plan, it is likely that additional time and/or funds will be needed or we will need to rescope the study if the NFSs are not interested in a larger effort. However, at this time it's not know if an exemption will be required. |  |  | 17 | Project Management | PRM | 337 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 | If this risk occurs, there may be an impact to the study budget. However, at this time an estimate is not available. | 0 | 0 | 0 | If this risk is occurs, then it may impact the study schedule. However, at this time its too early to determine the impact. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-12 19:39 | 0 | 337 | Janet | Cote | 299 | 299 | 1 | 0 | 0
2 | PRM-2 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Study with two separate Non-Federal Sponsors | Stakeholder, Sponsor or Partners | 9 | This feasibility study investigates two entirely separate FRM systems with two NFSs. The NFSs each have different needs, concerns and objectives. While the systems, though share some characteristics, have different problems. Additionally, the two NFSs have no tolerance for expending funds on the others system. The NFSs may not agree with elements of planning process (e.g. fund allocation, 3X3X3 exemption) even though they must move together through the feasibility phase. | 3 | Likely | Likely (50% to 70%) | Through weekly continued coordination, the PDT understands the NFSs concerns and what they are willing to support. |  |  | 17 | Project Management | PRM | 337 |  | 8 | Agency Strategy | If this risk occurs and the NFSs do not agree on a way forward, this may impact the completion of the study. | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-06-12 19:46 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 1 | 1
3 | PLP-3 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Correct Interpretation of the Section 216 authority | Agency Policy and Process | 7 | The Section 216 implementation guidance and 2005 Memo in Reconstruction are vague, which could lead to incorrect interpretation. Incorrect interpretation of the authority could result in not included elements that should be considered or inclusion of elements that are not appropriate to the study authority. This could lead to confusion during the planning process and coordination with the NFS. It could also lead to delays in the the implementing the planning process | 2 | Unlikely | Unlikely (30% to 50%) | The PDT is working with a Planning mentor and are coordinating with the FRM-PCX to ensure that the authority is correctly interpreted. |  |  | 13 | Planning - Plan Formulation | PLP | 337 |  | 8 | Agency Strategy | By not interpreting the authority correctly, the PDT could develop an incomplete plan, leaving out essential elements of the plan to rehabilitate the levee systems. Conversely, if element not supported by the authority are included in the recommended plan, then this could lead to the PDT having to reformulate the RP. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | If the authority is misinterpreted, then the PDT could waste time by analyzing elements not supported by the authority. Or could leave out elements that should be included, which are identified later in the study. This would also lead to study delays. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-12 19:57 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 1 | 0
4 | EHH-4 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Needed H&H Modeling | Info and Data Analysis | 1 | The PDT is currently uncertain how much H&H modeling will be required to identify the TSP. H&H modeling may be required to resize the pump stations and to develop NED benefits. However, the PDT is uncertain if resizing the equipment in the pump stations is necessary. And we are uncertain about how much modeling will be required to complete the benefits analysis. Too much modeling will result in wasted time and funding. While too little modeling would result in not enough information to understand the future conditions, risk reduction and benefits gained by the future TSP. | 3 | Likely | Likely (50% to 70%) | The PDT has spend significant time discussing this topic and we are still uncertain. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 5072 |  | 5 | Other |  | 5 | 0 | 0 | 600000 | 0 | It is estimated that additionally funding would be required if the PDT needs to develop an H&H model for both Hartford and East Hartford that would model interior drainage. There are other potential options that would reduce this cost. For example, the MDC has storm water modeling for Hartford. We need to make contact with the agency to see if they would be willing to share their modeling with the USACE. | 0 | 0 | 0 | Developing an H&H model for both Hartford and East Hartford would require a significant amount of time, however an estimate of that duration has not been developed to date. Before spending time on this estimate, the PDT will attempt other alternative. We will also discuss this question with the FRM-PCX to determine exactly what is needed, so that extraneous work isn't completed. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 17:08 | 0 | 337 | Janet | Cote | 299 | 299 | 1 | 0 | 0
5 | PLP-5 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Interpreting new Environmental Justice Guidance | Agency Policy and Process | 7 | The latest implementation guidance on Environmental Justice leave many questions unanswered and there the USACE doesn't have much experience implementing the new guidance. There is a risk that the PDT will incorrectly interpret the new guidance. This will result in wasted effort and loss of time if the PDT is asked to do additional work to satisfy the requirement. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 337 |  | 6 | Compliance | The risk of not full understanding the new EJ guidance is non-compliance with USACE policy and the EO. | 5 | 2 | 0 | 0 | 0 | Although this risk could lead to additional work, it's not believed that it would impact the $3mil study cost. | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 14:01 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 1 | 1
6 | PLC-6 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Elevation of the levee embankment and/or floodwalls. | Agency Policy and Process | 7 | If the PDT recommends the elevation of the levee embankments and/or floodwall, this measure will significantly impact the viewshed. This would result in a more broad NEPA/Section 106 analysis in addition to potential mitigation requirements. This risk would result in increased project costs, feasibility study costs and time. | 2 | Unlikely | Unlikely (30% to 50%) | The PDT doesn't fully understand the concerns of the NFSs so does not know if there is a need to increase the height of the floodwalls and levee embankments. |  |  | 14 | Planning - Cultural Resources | PLC | 337 |  | 6 | Compliance | This risk would result in the need to balance compliance with NEPA and other environmental laws with the need to rehabilitate the levee systems. As a result, additional time and money would be required to complete the impacts analysis of the view shed and to determine potential mitigation strategies. Additionally, mitigation could impact the project costs. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-06-13 14:14 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 1 | 1
7 | PLC-7 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Protection of historic structures vs protection of community | Stakeholder, Sponsor or Partners | 9 | Structures that are part of the levee systems may be historic and should be added to the National Register of Historic Places. If the PDT recommends that these structures should be replaced, the PDT will have to coordinate with the CT SHPO. This would result in the need for additional time and funding to complete coordination with the CT SHPO and to develop/implement mitigation plans. Additionally historic documentation, if required, would need to be completed during the PED Phase and prior to construction. | 4 | Very Likely | Very Likely (70% to 90%) | Many structures that make up the levee systems are over 50 years old and could be added to the National List of Historic Structures. The protection of these historic assets will have to be balanced against the needs of rehabilitation the levees and protection of the communities behind the FRM systems. With the information currently available to the PDT, most historic structures (other then those related directly to the levee systems) are locate away from the rivers. The PDT believes that this risk will relate only to the structures associated with the levee system (e.g., pump stations). |  |  | 14 | Planning - Cultural Resources | PLC | 793 |  | 2 | Environmental | This risk balances the needs of the levee systems and the communities that they protect with the requirements to protect historic resources. | 5 | 2 | 0 | 100000 | 0 | If the levee system is found to be eligible for the National Register of Historic Places and the tentatively selected plan results in an "adverse effect" upon significant historic properties, then a Memorandum of Agreement is required along with appropriate mitigation measures, most likely historic documentation. Cost is TBD and an estimate only. | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 17:56 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 0 | 1
8 | PLE-8 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Coordination with the resources agencies | Stakeholder, Sponsor or Partners | 9 | Staffing shortages and turnover at the resource agencies may impact coordination efforts. This risk could result in needing additional time to complete NEPA coordination or incomplete coordination. | 2 | Unlikely | Unlikely (30% to 50%) | Concern about this risk was high at the beginning of the feasibility study. But the resources agencies have been responsive to the PDTs coordination efforts. We hope that this will continue to be the case. |  |  | 16 | Planning - Environmental | PLE | 4693 |  | 6 | Compliance | This risk could result in incomplete compliance with NEPA and other environmental laws or additional time to complete require compliance. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-13 17:10 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 1 | 1
9 | PLP-9 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Lack of existing data | Info and Data Analysis | 1 | There is a concern that there is insufficient data to describe the study area and to adequately describe the existing, future without and change condition. USACE guidance requires that the existing and FWOP conditions are described in the feasibility report. The PDT is concerned that this isn't enough available data to allow the adequate description of the existing and FWOP conditions. Additionally, the Section 216 authority requires that elements included in the RP be a result of a changed physical or economic condition. The PDT has heard lots of anecdotal descriptions of the changed conditions that are experiences that the FRM systems. The risk is that there isn't sufficient existing data to support the anecdotal evidence to prove a changed condition. If sufficient data is not found to support anecdotal evidence, then some measures might not be included in the plan and an incomplete solution would be recommended. | 2 | Unlikely | Unlikely (30% to 50%) | At this point in the study, we are uncertain of the likelihood of this risk. |  |  | 13 | Planning - Plan Formulation | PLP | 337 |  | 6 | Compliance | This risk impacts the compliance with USACE guidance and the Section 216 authority. It could result in the completeness of the feasibility report and environmental compliance. It could also result in an incomplete solution being recommended. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 15:02 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 1 | 1
10 | EGT-10 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Data describing penetrations through the systems | Site Conditions | 6 | The PDT is concerned that there isn't adequate data that describes the penetrations through the two levee systems. Inadequate data would result in incorrect identification of needed measures necessary for the rehabilitation of the levee system and/or incorrect design to address the seepage due to penetrations through the levee embankments. | 4 | Very Likely | Very Likely (70% to 90%) | The NFSs have stated that they don't have complete information describing the penetrations through the levee embankments. |  |  | 3 | Engineering - Geotechnical | EGT | 3632 |  | 5 | Other | This risk could impact both time and cost of the feasibility phase. It could also impact the quality of the designs that are developed to address the weaknesses of the levee caused by the penetrations through the levees. | 5 | 2 | 0 | 0 | 0 | This risk might impact the budget of the feasibility phase by requiring additional funding to compete the designs/methods to address the seepage concerns due to embankment penetrations. This risk could also impact the PED and construction phase, if the actual conditions turn out to be different from those that were used to develop designs/methods. However, at this time, the exact cost impact is not known. | 0 | 0 | 0 | There could be impacts to the schedule of the Feasibility phase as described previously in the Cost Impact Section. However, at this time, the exact cost impact is not known. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 17:11 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 0 | 0
11 | RLE-11 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Complexity of Real Estate/Ownership of Property | Site Conditions | 6 | Both FRM (levee) systems are made up of a complex system of easements and land ownership. | 3 | Likely | Likely (50% to 70%) |  |  |  | 18 | Real Estate | RLE | 5073 |  | 6 | Compliance |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | If proper ownership is not identified, then... | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-06-13 17:14 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 1 | 0
12 | EGT-12 | 3711 | Hartford and East Hartford, CT Section 216 Levee Rehabilitation Study | 465097 | Existing Boring Data | Info and Data Analysis | 1 | There is a lack of existing boring date for the East Hartford FRM (levee) system. | 3 | Likely | Likely (50% to 70%) |  |  |  | 3 | Engineering - Geotechnical | EGT | 337 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-06-13 15:19 | 0 | 337 | Janet | Cote | 299 | 299 | 0 | 0 | 0
1 | PLE-1 | 3771 | Atka Navigation Improvements |  | Designation of dredged material placement site | Site Conditions | 6 | Designation of a dredged material placement site will be required as part of this feasibility study. Not enough is understood at this to verify the appropriate management of the dredged material or the amount of blasting that will likely be required to provide safe navigation. | 2 | Unlikely | Unlikely (30% to 50%) | Coordination with regulatory agencies has already begun and will be managed as the project progresses and more data is available. |  |  | 16 | Planning - Environmental | PLE | 6223 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-11 23:45 | 0 | 6223 | Erin | Stockdale | 299 | 299 | 0 | 0 | 1
1 | EPE-1 | 3772 | Bluestone DSA |  | Existing Concrete Harder than Expected | Site Conditions | 6 | Concrete has a higher than expected compressive strength which could result in hihger demo costs. (Expected non issue, check with sandy) Concrete demolition has begun in the stilling basin (Weir, Apron) while demoing the concrete in the primary apron it is possible to find concrete with higher strengths and making the demoing harder. This will most likely be in a localized area in a monolith. No strength provided to the contractor in design documents. Could be inferred based on bearing plate design 3000psi. (wearing items faster than expected, method of construction slower than gov expected, without issue though. FY23 UPDATE: Currently just over 50% excavation/demo. Let side existing Apron, baffles, existing cofferdam remain to be demo'd | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 21 | Construction - Project Engineer | EPE | 8955 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 | Marginal | 0 | 0 | 0 | Marginal | 1 | 1 | 1 | Active | 6 | Construction | 19 | 19 | Commissioning of Systems | 2023-04-12 18:58 | 0 | 8955 | Jacquelyn | Lewis Pilet | 299 | 299 | 0 | 0 | 0
2 | EPE-2 | 3772 | Bluestone DSA |  | Open Anchor Holes During Event Leads to Slab Replacement | Site Conditions | 6 | Open anchor holes exposed during a spill even could lead to slab replacement. If this were to occur there is possible dam failure. Risk to apron if hole are left open. If this occurs and a monolith is jacked it could result in replacement of slab. Similar to an "Act of God" event if the open anchor holes were exposed to spillway flow there is a potential for dam failure. (Do not model) FY23 Update No update. Left for tracking purpose. Not modeled | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 21 | Construction - Project Engineer | EPE | 8955 |  | 5 | Other |  | 10 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 6 | Construction | 20 | 20 | Construction Completion | 2023-04-13 12:19 | 0 | 8955 | Jacquelyn | Lewis Pilet | 299 | 299 | 0 | 0 | 0
3 | PRM-3 | 3772 | Bluestone DSA |  | Project Close-Out Duration | Communications | 2 | The estimated duration of project close-out could vary. | 4 | Very Likely | Very Likely (70% to 90%) |  |  |  | 17 | Project Management | PRM | 8955 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 180 | 180 | 365 |  | 4 | 1 | 1 | Active | 6 | Construction | 20 | 20 | Construction Completion | 2023-04-13 12:22 | 0 | 8955 | Jacquelyn | Lewis Pilet | 299 | 306 | 0 | 1 | 0
1 | PLE-1 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Communicating a prelim alternative that may change | Legal or Regulatory Actions | 10 | Communicating a prelim alternative that may change | 3 | Likely | Likely (50% to 70%) | Communicating before TSP Agency workshop after charette |  |  | 16 | Planning - Environmental | PLE | 3454 |  | 5 | Other |  | 10 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:25 | 0 | 7996 | Robin | Carr | 306 | 299 | 1 | 1 | 1
2 | EHH-2 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Climate change/ sea level rise | Site Conditions | 6 |  | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 9135 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:29 | 0 | 7996 | Robin | Carr | 299 | 299 | 1 | 1 | 1
3 | EHH-3 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Sedimentation Rate | Site Conditions | 6 |  | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 9135 |  | 5 | Other |  | 10 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:33 | 0 | 7996 | Robin | Carr | 299 | 299 | 0 | 1 | 1
4 | EGT-4 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Composition of Material at Site | Site Conditions | 6 | Foundation impacts | 3 | Likely | Likely (50% to 70%) |  |  |  | 3 | Engineering - Geotechnical | EGT | 9135 |  | 5 | Other |  | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:36 | 0 | 7996 | Robin | Carr | 299 | 299 | 0 | 1 | 1
5 | ECS-5 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Sources of Rock | Contract Performance | 4 | Sourcing cheaper rock from Canada and policy problems. | 3 | Likely | Likely (50% to 70%) | Likely we won't be able to source from Canada. |  |  | 2 | Engineering - Cost | ECS | 9139 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:39 | 0 | 7996 | Robin | Carr | 299 | 299 | 1 | 1 | 1
6 | PLP-6 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Data Gaps | Site Conditions | 6 | Data not available and not recognized as needed until later in planning process | 2 | Unlikely | Unlikely (30% to 50%) |  |  |  | 13 | Planning - Plan Formulation | PLP | 7996 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 96 | 96 | Decision Document Approval | 2023-04-27 21:47 | 0 | 7996 | Robin | Carr | 299 | 299 | 1 | 1 | 1
7 | PLC-7 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Weather impacts for cultural Surveys | Site Conditions | 6 |  | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | Calculated for when already likely to have good conditions. |  |  | 14 | Planning - Cultural Resources | PLC | 9138 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 96 | 96 | Decision Document Approval | 2023-04-27 21:54 | 0 | 7996 | Robin | Carr | 299 | 299 | 1 | 1 | 1
2 | PLP-2 | 3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 445445 | Real Estate Requirements on Other Federal Lands | Resource Availability | 5 | Selecting a plan that requires real estate acquisition on other federal lands would violate Corps policy and prevent transmission of a Chief's Report to Congress. | 4 | Very Likely | Very Likely (70% to 90%) | There is a checkerboard pattern of land ownership under and around the Salton Sea, which makes formulating meaningful alternatives that avoid federal lands challenging. Alternatives that focus elsewhere in the watershed (i.e., along the tributaries) would not adequately address the scale of the problem or satisfy the objectives of the study. |  |  | 13 | Planning - Plan Formulation | PLP | 3233 |  | 5 | Other | Any recommended plan that requires real estate on other federal agency land would not be policy compliant, which would prevent that plan from being authorized, funded, and constructed. Ecosystem degradation at the Salton Sea would exacerbate and persist. | 10 | 4 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-25 23:58 | 0 | 3233 | Corrine | Stetzel | 299 | 299 | 0 | 1 | 1
4 | PLP-4 | 3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 445445 | Public Perception | Communications | 2 | Issues at the Salton Sea are highly visible and controversial. Although different groups support different potential solutions, each group likely agrees that there have been too many studies with not enough action. A vocal group in the community strongly favors water importation solutions. This makes the transparency of the USACE study process and the robustness of a Recommended Plan important. | 3 | Likely | Likely (50% to 70%) | Lack of public support is likely if the decision document does not transparently show the planning process and/or include a robust set of final array alternatives that include solutions put forth and supported by community groups. |  |  | 13 | Planning - Plan Formulation | PLP | 3233 |  | 5 | Other | The consequences of losing public support could be high for both the Corps and our Partners. Consequences could include reputational damage to our respective agencies as well as a recommended plan not receiving funding because community and community leadership do not support it. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-13 17:46 | 0 | 5416 | Lindsay | Floyd | 299 | 299 | 0 | 1 | 1
5 | PLE-5 | 3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 445445 | Presence of Selenium in Soils | Site Conditions | 6 | Selenium is a naturally-occurring element, but because the Salton Sea is a terminal lake, selenium from the Colorado River concentrates in the Sea. At concentrated levels, selenium can be taken up in the tissues of plants and animals and bioaccumulates. It can impact the reproductive systems of birds and other animals. Selecting a plan that disturbs selenium deposits or could facilitate bioaccumulation in the food web would require sponsors to remediate prior to any Federal investment. | 3 | Likely | Likely (50% to 70%) | There are known selenium sinks in the Sea. |  |  | 16 | Planning - Environmental | PLE | 4822 |  | 2 | Environmental | Avoiding selenium deposits may impact plan selection. | 5 | 2 | 0 | 10000 | 0 | It is USACE policy that our sponsors would need to remediate properties before a project can be implemented, which poses a unique challenge because selenium will continue to enter the Sea through the CO River and its tributaries. Our risk management strategies include conducting environmental site assessments and avoiding known selenium deposits when possible. | 0 | 120 | 0 | Environmental site assessments may be needed to manage the risk. | 3 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-13 17:59 | 0 | 5416 | Lindsay | Floyd | 299 | 299 | 0 | 0 | 0
6 | EHH-6 | 3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 445445 | Variable Future Inflows | Agency Policy and Process | 7 | Existing modeling for future inflow to the Salton Sea currently has a lot of uncertainty and low confidence. It will be difficult to predict future inflows with existing data given unknowns around local rainfall trends, climate change, policy changes, Colorado River management, and evaporation rates. This could lead to selecting a plan that does not perform well under future inflow scenarios. | 4 | Very Likely | Very Likely (70% to 90%) | Current H&H modeling effort for the Salton Sea are too broad to confidently recommend a single plan. Models do not fully capture the changing hydrology landscape at the Sea with regards to climate change, water policy, and inflows. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3233 |  | 5 | Other | Understanding H&H is foundational to selecting a plan that will perform as expected under future inflow scenarios. There is a risk that a plan may be recommended that will not perform well and possible reformulation will be needed. | 10 | 3 | 0 | 1400000 | 0 | Selecting a plan that doesn't perform well under future inflow scenarios could result in needing to reformulate through a GRR. To mitigate this risk, the team proposes holding a water budget workshop with subject matter experts, collecting additional data, calibrating models, and modeling groundwater interactions. | 0 | 150 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-13 19:06 | 0 | 5416 | Lindsay | Floyd | 299 | 299 | 0 | 0 | 0
7 | PLE-7 | 3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 445445 | Ecological Modeling | Agency Policy and Process | 7 | There are not suitable existing USACE ecological models that can effectively be used to assess the habitat in the study area. While several ecological models exist for similar bird types in the Eastern U.S., the models should be adapted to an arid southwestern environment, and additional models will be needed to cover all the habitat types identified for restoration. This could result in missing habitat types and inaccurate habitat unit calculations which in turn could impact identification of the NER plan and plan selection. | 5 | Extremely Likely | Extremely Likely (90% to 100%) | There is high likelihood of potentially inaccurate measurement of ecosystem outputs since existing models are not adapted to the arid southwest. There also likely will be incomplete measurements of ecosystem outputs as only 2 of 5 identified habitats types are represented by existing modeling. Additionally, models do not account for water quality parameters such as salinity, dissolved oxygen, and other pollutants. This may only be managed by developing USACE models that are specific to the Salton Sea to develop habitat units. |  |  | 16 | Planning - Environmental | PLE | 5923 |  | 5 | Other | There is a risk that inaccurate measurement of ecosystem outputs could impact identification of the NER plan and plan selection. | 10 | 4 | 0 | 200000 | 0 | There is a risk that inaccurate measurement of ecosystem outputs could impact identification of the NER plan and plan selection. To mitigation this risk, UACE could use a model created by the Audubon Society or develop new ecological models. Creation of new models is estimated to cost roughly $200,000. | 0 | 550 | 0 | There is a risk that inaccurate measurement of ecosystem outputs could impact identification of the NER plan and plan selection. To mitigation this risk, UACE could use a model created by the Audubon Society or develop new ecological models. Creation of new models is estimated to take roughly 18 months. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-13 19:48 | 0 | 5416 | Lindsay | Floyd | 299 | 299 | 0 | 0 | 0
8 | PLP-8 | 3831 | Imperial Streams and Salton Sea Ecosystem Restoration | 445445 | Emissive Seabed and Public Health Concerns | Site Conditions | 6 | As the footprint Salton Sea shrinks, the exposed seabed, which has concentrated salts and pollutants, is picked up during frequent dust storms. The seabed particulates then are spread to the surrounding communities, which contributes to reduced air quality and human health & safety concerns such as asthma and other respiratory diseases. With existing data, there are uncertainties around how much alternative plans will reduce dust emissions and how much of the air quality related concerns in the study area are attributed to the emissive seabed. | 3 | Likely | Likely (50% to 70%) | With existing data, it is very likely that dust emissions will not be accurately reflected in analysis of alternative plans. The Coachella Valley is prone to dust storms, and particulates are picked up from agriculture fields as well as from commuter and freight traffic emissions. The Sea is not the sole source of air pollutions, so it is unknown how much an ecosystem restoration project will improve local air quality conditions. |  |  | 13 | Planning - Plan Formulation | PLP | 3233 |  | 5 | Other | Inaccurate modeling of dust emissions could impact identification and selection of a comprehensive benefits plan. Addressing public health concerns will be considered in the other social effects benefit category when evaluating alternatives. | 5 | 2 | 0 | 200000 | 0 | This risk can be partially mitigated by modeling air quality. This could include measuring reductions in acres of exposed playa, measuring reductions of playa dust in the air, and augmenting understanding of the links between Sea dust emissions and public health in the area. Developing a dust emission/public health model is estimated to cost $200,000. | 0 | 550 | 0 | Developing a dust emission/public health model is estimated to take roughly 18 months. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-13 19:48 | 0 | 5416 | Lindsay | Floyd | 299 | 299 | 0 | 0 | 0
1 | PLE-1 | 3911 | Andalusia Island Complex | 505036 | Avian IBI Modeling | Info and Data Analysis | 1 | Model has not specifically been used as it is being applied for the WSC study. | 0 | Extremely Unlikely | Extremely Unlikely (0% to 5%) | My best professional judgement of the existing habitat conditions is that the WSC are missing the vertical habitat layers required of many migratory, resident, and wintering bird species. At a minimum, I anticipate significant differences between canopy nesting, canopy feeding, and non-native bird species populations between WSC and the reference reaches. |  |  | 16 | Planning - Environmental | PLE | 6927 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-05 19:51 | 0 | 6867 | Kayleigh | Thomas | 299 | 299 | 1 | 1 | 1
3 | PLE-3 | 3911 | Andalusia Island Complex | 505036 | Constrained Project Area | Site Conditions | 6 | The confined project area and H&H constraints may limit the aerial extent of habitat restoration alternatives. | 4 | Very Likely | Very Likely (70% to 90%) | Best professional judgement and scientific literature justify the likelihood rating. |  |  | 16 | Planning - Environmental | PLE | 6927 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 180 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-21 20:36 | 0 | 6867 | Kayleigh | Thomas | 299 | 299 | 1 | 1 | 0
2 | PLE-2 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Threatened and Endangered Species | Site Conditions | 6 | Existing and new T&E species are identified within the Recommended Plan. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | The Corps has experience managing impacts to existing T&E species in this area. Also there is no indications that resources agencies are preparing to list new T&E species or designate critical habitat that would impact the feasibility study. The PDT will use the USFWS IPAC system to monitor changes to the status of T&E species. |  |  | 16 | Planning - Environmental | PLE | 443 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 10000 | Previous experience and professional judgement | 0 | 0 | 180 | Previous experience and professional judgement | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-26 19:10 | 0 | 9033 | Chris | Dixon | 306 | 306 | 1 | 0 | 0
3 | PLC-3 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Significant Cultural Resources | Site Conditions | 6 | Significant cultural resources and/or historic properties determined eligible for, or listed on, the National Register for Historic Places (NRHP) are identified within the recommended plan. Specifically, they include abandoned shipwrecks within offshore borrows sites or along pipeline routes. | 3 | Likely | Likely (50% to 70%) | The offshore areas of Holden Beach are largely unsurveyed for cultural resources, but abandoned shipwrecks are recorded in the Lockwoods Folly Inlet and in nearby waters with similar bathymetry and maritime history. |  |  | 14 | Planning - Cultural Resources | PLC | 1742 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 300000 | Professional judgement and previous experience identifying abandoned shipwrecks | 0 | 0 | 180 | Professional judgement and previous experience identifying abandoned shipwrecks | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-07 17:59 | 0 | 9033 | Chris | Dixon | 306 | 306 | 1 | 0 | 0
4 | PRM-4 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Competing Priorities for PDT | Resource Availability | 5 | Competing priorities effect support of the Project Delivery Team. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | District personnel management practices, professional judgement and past experiences. |  |  | 17 | Project Management | PRM | 584 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 30000 | District personnel management practices, professional judgement and past experiences. | 0 | 0 | 150 | District personnel management practices, professional judgement and past experiences. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-07 18:05 | 0 | 9033 | Chris | Dixon | 306 | 306 | 1 | 0 | 0
5 | EGT-5 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Sufficient sand for initial construction and nourishment | Site Conditions | 6 | There is a lack of sufficient sand to support the recommended plan during initial construction and nourishment events. | 3 | Likely | Likely (50% to 70%) | The South Atlantic Coastal Study and previous offshore borings near Holden Beach. |  |  | 3 | Engineering - Geotechnical | EGT | 2352 |  | 1 | Asset Condition | The project will not be able to provide the anticipated level of risk reduction for the full 50 year period of performance. | 5 | 2 | 0 | 0 | 300000 | Previous contractor estimates | 0 | 0 | 180 | Previous contractor estimates. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-07 21:38 | 0 | 9033 | Chris | Dixon | 306 | 306 | 0 | 0 | 0
6 | EHH-6 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Impact of Ocean Isle Beach Terminal Groin | Info and Data Analysis | 1 | The immediate impacts from a non-Federal terminal groin at Ocean Isle Beach on bathymetry to nearby inlets. | 2 | Unlikely | Unlikely (30% to 50%) | Professional judgement |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 584 |  | 1 | Asset Condition | Effects evaluation of the adjacent inlets as potential sources of sand borrow. over the 50 year project life | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-07 18:13 | 0 | 9033 | Chris | Dixon | 299 | 299 | 0 | 1 | 1
7 | CNT-7 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Contractor availability | Contract Acquisition | 3 | The PDT is unable to award a contract for the geotechnical investigations | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Previous contract awards |  |  | 1 | Contracting | CNT | 2352 |  | 8 | Agency Strategy | The consequence of this risk is a failure to identify borrow sources, existing and subsurface conditions for the project within established project milestones. | 5 | 2 | 0 | 0 | 100000 | Previous contract awards. | 0 | 0 | 120 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-07 21:37 | 0 | 9033 | Chris | Dixon | 306 | 306 | 0 | 0 | 0
8 | EGT-8 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Shared use of inlet sand borrow sources | Stakeholder, Sponsor or Partners | 9 | Shared use of inlet sand borrow sources with other communities will create a volume short fall for the project. | 3 | Likely | Likely (50% to 70%) | Knowledge of existing, local nourishment projects |  |  | 3 | Engineering - Geotechnical | EGT | 2352 |  | 8 | Agency Strategy | The consequence of this risk will determine the nourishment cycle and plan for the project. | 5 | 2 | 0 | 0 | 50000 | Professional judgement | 0 | 0 | 180 | Professional judgement | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-07 21:28 | 0 | 9033 | Chris | Dixon | 306 | 306 | 0 | 0 | 0
9 | PLE-9 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | T&E species may move into recommended plan footprint | Site Conditions | 6 | New and/or existing threatened and endangered species are identified within the recommended plan. | 2 | Unlikely | Unlikely (30% to 50%) | USFWS IPAC system. The Corps also has experience managing impacts to existing T&E species in the region. |  |  | 16 | Planning - Environmental | PLE | 443 |  | 5 | Other | The consequence of this risk will force consultation and coordination with resource agencies and the public to avoid or mitigate impacts. Impacts to the performance of the project after construction are unclear. | 5 | 2 | 0 | 0 | 50000 | Previous experience consulting under the Endangered Species Act and other environmental laws. | 0 | 0 | 120 | Previous experience consulting under the Endangered Species Act and other environmental laws. | 2 | 4 | 4 | Inactive – Entered by Error | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-26 20:05 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
10 | PLE-10 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Erosion and land loss calculations are inaccurate | Info and Data Analysis | 1 | The assumptions within the Beach Fx model concerning erosion and land loss are incorrect. | 2 | Unlikely | Unlikely (30% to 50%) | Experience with the model |  |  | 15 | Planning - Economics | PLE | 2496 |  | 5 | Other | The consequence of this risk is a failure to accurately measure the future without and the future with project conditions. | 5 | 2 | 0 | 0 | 50000 | Professional experience with model | 0 | 0 | 90 | professional experience with the model | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 19:28 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
11 | PRM-11 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Type I Independent External Peer Review | Agency Policy and Process | 7 | An Independent External Project Review (IEPR) will effect study execution. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Previous experience. |  |  | 17 | Project Management | PRM | 584 |  | 5 | Other | The consequence of this risk will effect the study schedule and budget. | 5 | 2 | 0 | 0 | 120000 | Information from CSRM PCX | 0 | 0 | 120 | Information from CSRM-PCX | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 19:42 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
12 | EHH-12 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Inclusion of sea level rise data since 1992 | Info and Data Analysis | 1 | The study will not modify storm water levels in its models to include additional sea level rise data since 1992. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Professional judgement |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 584 |  | 5 | Other | The consequence of risk is new data related to sea level rise and storm water levels that will force modifications to the study models. | 5 | 2 | 0 | 0 | 60000 | Professional judgement | 0 | 0 | 120 | Professional judgement | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 19:51 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
13 | PRM-13 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | 3x3x3 Policy Waiver | Agency Policy and Process | 7 | The request for a 3x3x3 policy waiver on the study is denied. | 2 | Unlikely | Unlikely (30% to 50%) | Professional judgement |  |  | 17 | Project Management | PRM | 584 |  | 8 | Agency Strategy | The consequence of this risk will limit the study's examination of risk effecting the community and the solutions to reduce those risks. | 10 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-26 13:48 | 0 | 584 | Keith | Keeney | 306 | 299 | 0 | 1 | 1
14 | PLE-14 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | existing structural inventory | Info and Data Analysis | 1 | First-floor elevations and structural values within existing structural inventory are inaccurate. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Professional experience. |  |  | 15 | Planning - Economics | PLE | 5155 |  | 5 | Other | The consequence of this risk will be an inaccurate calculations of damages. | 5 | 2 | 0 | 0 | 50000 | Previous Experience | 0 | 0 | 90 | Previous experience | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 20:17 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
15 | PRM-15 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Shared sand borrow sources | Stakeholder, Sponsor or Partners | 9 | There is competition between communities on available sand borrow sources. | 2 | Unlikely | Unlikely (30% to 50%) | Professional judgement |  |  | 17 | Project Management | PRM | 584 |  | 5 | Other | The consequence will be more negotiation, analysis and planning with resource agencies to identify acceptable borrow sources. Mitigative planning. | 5 | 2 | 0 | 0 | 30000 | Professional judgement | 0 | 0 | 90 | professional judgement | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 20:28 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
16 | PRM-16 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Conflicts with other coastal storm projects | Stakeholder, Sponsor or Partners | 9 | The project conflicts with other coastal storm projects (local, state and Federal) in the region. | 2 | Unlikely | Unlikely (30% to 50%) | Professional judgement |  |  | 17 | Project Management | PRM | 584 |  | 8 | Agency Strategy | The consequence will be more negotiation, analysis and planning with resource agencies to identify acceptable borrow sources. Mitigative planning. | 5 | 2 | 0 | 0 | 30000 | Professional judgement | 0 | 0 | 90 | professional judgement. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-13 20:35 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
17 | PLE-17 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Complex environmental mitigation requires additional effort | Site Conditions | 6 | Complex environmental mitigation requires additional effort and documentation for the study. | 2 | Unlikely | Unlikely (30% to 50%) | Previous experience, existing Corps policy, knowledge of the study area. |  |  | 16 | Planning - Environmental | PLE | 443 |  | 6 | Compliance | The consequence of this risk will be greater documentation and coordination with resource agencies and the non-Federal sponsor for the study. Potentially expensive mitigation could be added to the overall construction of the project. | 5 | 2 | 0 | 0 | 100000 | Previous experience, existing Corps policy, knowledge of the study area. | 0 | 0 | 180 | Previous experience, existing Corps policy, knowledge of the study area. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-26 14:08 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
18 | PLC-18 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Nonstructural measures and Section 106 | Site Conditions | 6 | Nonstructural measures (e.g. floodproofing and elevation) to standing structures in the backbay may require a programmatic agreement to reach compliance with Section 106 of the National Historic Preservation Act. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Federal law and guidance, previous experience, and existing Corps policy |  |  | 14 | Planning - Cultural Resources | PLC | 584 |  | 5 | Other | The consequence of this risk will be greater coordination and documentation with consulting parties, Federally-recognized tribes, and the public leading to the preparation of a Programmatic agreement. | 5 | 2 | 0 | 0 | 50000 | Federal law and guidance, previous experience, and existing Corps policy. | 0 | 0 | 150 | Federal law and guidance, previous experience, and existing Corps policy. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-26 14:49 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
19 | EGT-19 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Artificial reef materials and sand borrow locations | Site Conditions | 6 | Artificial reef materials (e.g. rubber tires) near the project migrate into locations of proposed sand borrow. | 4 | Very Likely | Very Likely (70% to 90%) | Near-shore hydrographic surveys within 3 miles of the project. |  |  | 3 | Engineering - Geotechnical | EGT | 2352 |  | 8 | Agency Strategy | The consequence of this risk will be an inability to complete the study per Section 1001 requirements of Water Resources Reform and Development Act of 2014 (Public Law 113-121) . | 10 | 3 | 0 | 0 | 200000 | Previous contract awards for surveys | 0 | 0 | 180 | Previous contract awards for surveys. | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-26 15:03 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
20 | EGT-20 | 3913 | Brunswick County Beaches, Holden Beach Portion, General Re-evaluation Report | 481505 | Artificial reefs | Site Conditions | 6 | Artificial reef materials (e.g. rubber tires) are found migrating into proposed sand borrow locations for the project. | 3 | Likely | Likely (50% to 70%) | Artificial tires have Identified off-shore of Holden Beach during survey, but locations of sand borrow locations have not been determined. |  |  | 3 | Engineering - Geotechnical | EGT | 2352 |  | 4 | Operations | The consequence of this risk will be additional surveys and volumetric calculations to identify locations without these materials and the necessary quantities of sand borrow for the project. | 5 | 2 | 0 | 0 | 100000 | Previous contract at Wrightsville Beach | 0 | 0 | 180 | previous contract at Wrightsville Beach | 2 | 4 | 4 | Inactive – Entered by Error | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-06-28 19:50 | 0 | 584 | Keith | Keeney | 306 | 306 | 0 | 0 | 0
1 | EGT-1 | 3914 | Surf City Beach Construction PL 116-20 | 487223 | Finding sand in closer proximity to the project | Info and Data Analysis | 1 | Sand borrow for the recommended plan, a beach nourishment, are 5 to 6 miles from the project, increasing its cost and schedule. | 3 | Likely | Likely (50% to 70%) | The project was previously studied as part of a feasibility and authorized in 2010, but some data gaps existed in terms the quantity and quality of the sand identified during the study. |  |  | 3 | Engineering - Geotechnical | EGT | 2339 |  | 5 | Other | If the risk is realized, then the constructed project will require additional funds to provide the level of risk reduction for the 50-year project life. | 5 | 2 | 0 | 50000 | 100000 | Cost range is derived from previous contract awards | 0 | 45 | 90 | Schedule is derived from the previous contract awards. | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-06-12 15:41 | 0 | 9033 | Chris | Dixon | 302 | 302 | 0 | 0 | 0
2 | ECV-2 | 3914 | Surf City Beach Construction PL 116-20 | 487223 | Backbay flooding | Info and Data Analysis | 1 | Flooding in backbay of Surf City, NC will increase over the life of project. | 2 | Unlikely | Unlikely (30% to 50%) | The 2010 study of the project did not identify significant backbay flooding issues at Surf City. |  |  | 9 | Engineering - Civil | ECV | 584 |  | 1 | Asset Condition | If backbay flooding becomes an issue, then such could effect the risk reduction for the project and Surf City. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-06-07 21:53 | 0 | 9033 | Chris | Dixon | 299 | 299 | 0 | 1 | 1
3 | EHH-3 | 3914 | Surf City Beach Construction PL 116-20 | 487223 | Sea level rise | Info and Data Analysis | 1 | The impacts of sea level rise to the project are greater than anticipated. | 4 | Very Likely | Very Likely (70% to 90%) | Coastal Hazard System tool |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 584 |  | 1 | Asset Condition | If the risk is realized, then the project will need more sand and require changes to the nourishment interval to maintain a level of risk reduction on the project. | 5 | 2 | 50000 | 100000 | 200000 | Professional judgement. | 0 | 180 | 365 | Professional judgement. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-06-06 20:34 | 0 | 9033 | Chris | Dixon | 302 | 302 | 0 | 0 | 0
4 | LGL-4 | 3914 | Surf City Beach Construction PL 116-20 | 487223 | Anytime Dredging | Legal or Regulatory Actions | 10 | Cost and schedule risk if anytime dredging is not allowed. | 2 | Unlikely | Unlikely (30% to 50%) | Professional Judgement |  |  | 10 | Office of Counsel | LGL | 584 |  | 6 | Compliance | 'Professional judgement. | 10 | 3 | 500000 | 0 | 1000000 | 'Cost estimate for mobilization and demobilization. | 365 | 0 | 730 | 'Schedule estimate based on adherence to environmental windows. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-06-06 20:51 | 0 | 9033 | Chris | Dixon | 306 | 306 | 0 | 0 | 0
5 | CNT-5 | 3914 | Surf City Beach Construction PL 116-20 | 487223 | Construction contractor | Contract Acquisition | 3 | Identifying Nearby Contractor with adequate dredge hoppers to construct the project. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Professional judgement. |  |  | 1 | Contracting | CNT | 9013 |  | 8 | Agency Strategy | The risk would delay the schedule for construction of the project. | 5 | 2 | 0 | 0 | 20000 | Internal government cost estimate | 0 | 0 | 20 | Internal government cost estimate | 2 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-06-06 22:55 | 0 | 9033 | Chris | Dixon | 306 | 306 | 0 | 0 | 0
6 | EGT-6 | 3914 | Surf City Beach Construction PL 116-20 | 487223 | Encountering rock and/or cemented sands within borrow | Site Conditions | 6 | Rock and/or cemented sand could be encountered at anytime during construction (i.e. Initial and subsequent nourishment intervals), creating a reduction in production times and an increase cost of disposal. | 3 | Likely | Likely (50% to 70%) | Nearby CSRM projects and professional judgement. |  |  | 3 | Engineering - Geotechnical | EGT | 2339 |  | 5 | Other |  | 5 | 0 | 0 | 1000000 | 0 | Professional judge. still working on estimate. | 14 | 21 | 45 | Knowledge of rock boxes and their use. | 2 | 1 | 1 | Active | 6 | Construction | 20 | 20 | Construction Completion | 2023-06-06 20:42 | 0 | 9033 | Chris | Dixon | 299 | 302 | 1 | 0 | 0
7 | RLE-7 | 3914 | Surf City Beach Construction PL 116-20 | 487223 | Ownership and maintenance of lands related to the project | Legal or Regulatory Actions | 10 | The legal authority for Surf City to acquire and maintain the ownership of lands outside of their political boundaries. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Written authority and regulations. |  |  | 18 | Real Estate | RLE | 520 |  | 4 | Operations | Professional judgement. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 15 | Professional judgement. | 2 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-06-06 20:43 | 0 | 9033 | Chris | Dixon | 299 | 306 | 0 | 1 | 0
8 | EGT-8 | 3914 | Surf City Beach Construction PL 116-20 | 487223 | Likelihood of Encountering Unsuitable Material | Info and Data Analysis | 1 | Although subsurface investigations have yielded useful information and the District is actively pursuing vibracore contracts, given the characteristics of the underlying geology, it is likely that unsuitable material may be encountered at anytime in any borrow area. This could occur as fines, rock, or cemented sand. | 4 | Very Likely | Very Likely (70% to 90%) | Widespread variability of underlying geology and predominantly rocky offshore conditions, as well as log descriptions from various supporting investigations showing a wide range of sediment types and horizons. |  |  | 3 | Engineering - Geotechnical | EGT | 2339 |  | 5 | Other |  | 5 | 0 | 0 | 200000 | 500000 | Cost could be zero in the early phases of the project and increase in the outyears as sand volumes are depleted. Cost is based on the procurement of a vibracore contract or an increased hauling distance. | 0 | 30 | 90 | Estimate based on cost estimate comparisons and professional judgement. | 2 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-06-06 20:45 | 0 | 9033 | Chris | Dixon | 302 | 302 | 1 | 0 | 0
1 | PRM-1 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Inter-Agency Coordination | Communications | 2 | Adverse impact from complex project coordination between multiple interagency entities (VA, VAMC, VA CFM, VISN, USACE, SHPO). | 3 | Likely | Likely (50% to 70%) | Project will be coordinated between VA and USACE. Project Book hand over to USACE (expected 2023-2024). Historic & cultural resources work coordinated under a separate project that may have impact on the Major Project. Depending on the inclusion of Building 1 in NHPA consultation, the historic/cultural compliance effort could take several months. Mandatory approvals and decision events with USACE and VA senior leaders have been known to cause delays due to difficulty with scheduling. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 10000 | 100000 |  | 0 | 60 | 0 | Schedule. Most likely no impact, but allow max of 2 month schedule delay per year of execution. - Cost due to schedule: Assume delays are spread out, so include escalation for 50% of project cost. | 2 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 00:46 | 0 | 9033 | Chris | Dixon | 302 | 299 | 1 | 0 | 0
2 | PGM-2 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Design Schedule | Contract Performance | 4 | Any resulting delays will incur additional schedule and costs. Delay in design delays time to market. Depending on the inclusion of Building 1 in NHPA consultation, this historic/cultural compliance effort could take several months and require additional studies as part of the consultation efforts. | 1 | Very Unlikely | Very Unlikely (5% to 30%) |  |  |  | 22 | Programs Management | PGM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 17 | Design | 62 | 62 | Design Start | 2023-06-07 01:03 | 0 | 9033 | Chris | Dixon | 299 | 299 | 1 | 1 | 1
4 | PRM-4 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Growth in Design Scope | Contract Acquisition | 3 | SOW in Project Book is limited to pre-planning efforts focused on the Major Project buildings and infrastructure. Additional planning may have to be done by the AE of Record; influencing both design cost and schedule. Small cost to schedule risk. Limited SOW does not allow review of potential overall campus issues. The Project Book captures majority of project requirements. Does contain language, that the AE of Record will need to (define, design, analysis, determine...) Scope of Project Book excluded future usage of Building 1 and several smaller seismic projects on campus that require NHPA compliance. Risk could come from discovering unknown requirements, causing a delay in the schedule and increased costs. | 3 | Likely | Likely (50% to 70%) |  |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 12549897 | 24000000 | 37649692 | Almost certain to discover new requirements. Say overall 10% increase is most likely, 5-15% possible. | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-13 12:46 | 0 | 9033 | Chris | Dixon | 302 | 299 | 1 | 0 | 1
6 | PRM-6 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Design Phases | Agency Policy and Process | 7 | Project is expected to occur in multiple phases/buildings, requiring design, construction, contracting, and funding stream strict coordination to minimize gaps and holes in scope/funds. | 2 | Unlikely | Unlikely (30% to 50%) | Design approach will be influenced by Phased construction. Sequencing of work is critical and cannot be stretched out over a long period of time or design must be continuously updated. Phased construction and design inherently adds risks for oversights of the required phases. Design impacts are likely if contract is broken into phases. Impacts could be multiple mobilizations to the site, different contractors for different phases, etc. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 01:16 | 0 | 9033 | Chris | Dixon | 299 | 299 | 1 | 1 | 1
7 | PRM-7 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Scope Growth | Info and Data Analysis | 1 | Scope has a potential to grow through design development. | 2 | Unlikely | Unlikely (30% to 50%) | Scope Growth has the potential to increase cost. VA must ensure appropriate participation and buy-in during the design phase to minimize/control scope growth. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 01:26 | 0 | 9033 | Chris | Dixon | 299 | 299 | 1 | 1 | 1
8 | PRM-8 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Funding Sources | Info and Data Analysis | 1 | Funding availability for Major Project and for potential Asbestos and Hazardous Material abatement (not evaluated as part of Project Book SOW). | 3 | Likely | Likely (50% to 70%) | Hazardous Materials abatement (for buildings being demolished) budget is usually a different appropriation, is not a part of the Project Book SOW and not modeled in this cost summary. However timing (schedule), availability of funds (in-place at right time), and understanding of cost is critical. The VA will need to have this money available to complete any potential Hazardous material remediation or this may affect schedule. Review Risk Status for next meeting Budget approved for asbestos and hazardous materials (approx. $5M) * No anticipation for additional funds at this time * High likelihood/confirmation for asbestos and lead present * Need to have the scope written as value added if we are to proceed with destructive testing. * Contractor NEEDS to make all repairs for damages incurred by destructive testing. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 2000000 | 5000000 | Evidence for "Funding Sources" at medium cost risk | 2 | 120 | 240 | Evidence for "Funding Sources" at medium schedule risk | 3 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 16:45 | 0 | 9033 | Chris | Dixon | 302 | 302 | 1 | 0 | 0
9 | PRM-9 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | PFD changes | Info and Data Analysis | 1 | Program for Design developed and concurred by VAMC Roseburg as part of Project Book. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Final Project book to include PFD. Baseline Cost estimate assumes this to be included in Final Report. CRMP Documentation is submitted through VA for additional funding approval to reprogram project. Awaiting final decision via President Budget. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 16:26 | 0 | 9033 | Chris | Dixon | 299 | 299 | 1 | 1 | 1
10 | PRM-10 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | User Requested Changes | Info and Data Analysis | 1 | User requested changes on the project to increase quality/equipment and functionality after award. | 2 | Unlikely | Unlikely (30% to 50%) | Out of scope changes could result in increased cost and schedule delays. Early customer expectation management with the user groups will be critical to minimize impacts. Late change implications need to be clearly explained to the users. Initial engagement should begin at design start. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 16:28 | 0 | 9033 | Chris | Dixon | 299 | 299 | 1 | 1 | 1
11 | PRM-11 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Removal of Programs | Resource Availability | 5 | Risk to removing/reducing existing programs/department functions. Typically would not return. | 1 | Very Unlikely | Very Unlikely (5% to 30%) | Include review of PFD as part of initial design work to confirm space needs and uses for campus and the Major Project. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 16:29 | 0 | 9033 | Chris | Dixon | 299 | 299 | 1 | 1 | 1
12 | PRM-12 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Timely Response | Agency Policy and Process | 7 | Timely Response - Programming - Availability for VA leadership to make decisions in a timely manner. Reviewing and turning over submittal and RFIs to contractor as not to create a delay to the construction schedule. | 2 | Unlikely | Unlikely (30% to 50%) | Untimely responses potentially delay construction schedule placing the government at risk for payment of extended overhead. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 60 | 120 | Evidence for "Funding Sources" at medium schedule risk | 2 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 16:30 | 0 | 9033 | Chris | Dixon | 299 | 302 | 1 | 1 | 0
13 | PRM-13 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Swing Space | Info and Data Analysis | 1 | Phasing plan could require more or less swing space than anticipated | 2 | Unlikely | Unlikely (30% to 50%) | Team discussed that duration and type of impacts is likely to change but the cost is unlikely to change -- any change is likely to be negligible. If execution strategy changes to where more swing space is needed then likely escalation costs will decrease a similar amount due cost from schedule savings. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 16:32 | 0 | 9033 | Chris | Dixon | 299 | 299 | 1 | 1 | 1
14 | PRM-14 | 3915 | Seismically Upgrade, Reno B2, Replace B1 | 506120 | Occupied Buildings | Agency Policy and Process | 7 | Work in occupied buildings could impact mission or delay construction | 2 | Unlikely | Unlikely (30% to 50%) | Phasing plan is developed to avoid work in occupied spaces. Even if it does happen, this is acceptable. Medical center can work with and around construction. Estimate will be updated to reflect longer durations for activation times. No add'l impact, as long as that is completed. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-06-07 16:33 | 0 | 9033 | Chris | Dixon | 299 | 299 | 1 | 1 | 1

## SQL
Select distinct r.RISK_ID, concat(concat(d.ACRONYM, '-'), r.RISK_ID) as RISK_IDENTIFIER, r.PROJECT_ID, p.PROJECT_NAME, p.P2_LOOKUP, r.RISK_NAME, c.RISKCATEGORY, r.RISKCATEGORYID, r.RISK_STATEMENT, r.PROB_OCCURRENCE, CASE WHEN PROB_OCCURRENCE = 0 THEN 'Extremely Unlikely' WHEN PROB_OCCURRENCE = 1 THEN 'Very Unlikely' WHEN PROB_OCCURRENCE = 2 THEN 'Unlikely' WHEN PROB_OCCURRENCE = 3 THEN 'Likely' WHEN PROB_OCCURRENCE = 4 THEN 'Very Likely' WHEN PROB_OCCURRENCE = 5 THEN 'Extremely Likely' END AS LIKELIHOOD, CASE WHEN PROB_OCCURRENCE = 0 THEN 'Extremely Unlikely (0% to 5%)' WHEN PROB_OCCURRENCE = 1 THEN 'Very Unlikely (5% to 30%)' WHEN PROB_OCCURRENCE = 2 THEN 'Unlikely (30% to 50%)' WHEN PROB_OCCURRENCE = 3 THEN 'Likely (50% to 70%)' WHEN PROB_OCCURRENCE = 4 THEN 'Very Likely (70% to 90%)' WHEN PROB_OCCURRENCE = 5 THEN 'Extremely Likely (90% to 100%)' END AS LIKELIHOOD_DISC, r.PROB_OCCURRENCE_EVIDENCE, r.OCCURRENCECONFIDENCEID, o.CONFIDENCE, r.RISKOWNERDISCIPLINEID, d.DISCIPLINE, d.ACRONYM as DISCIPLINE_ACRONYM, r.RISKMANAGERID, m.RISKMANAGER, r.PERFORMANCEIMPACTTYPEID, p.PERFORMANCEIMPACT as PERFORMANCEIMPACTTYPE, r.PERFORMANCEIMPACT_DESC, r.PERFORMANCEIMPACT_IMPCT, r.PERFORMANCEIMPACT_RISK_RANKING, r.COST_IMPACT_LOWEST, r.COST_IMPACT_MOSTLIKELY, r.COST_IMPACT_HIGHEST, r.COST_IMPACT_EVIDENCE, r.SCHEDULE_IMPACT_LOWEST, r.SCHEDULE_IMPACT_MOSTLIKELY, r.SCHEDULE_IMPACT_HIGHEST, r.SCHEDULE_IMPACT_EVIDENCE, r.SCHEDULE_RISK_RANKING, r.RISKSTATUSID, S.ID, s.RISKSTATUS, r.PROJECTPHASEID, h.LIFECYCLEPHASENAME, r.PROJECTMILESTONEID, n.ID, n.MILESTONE, r.EDITDATE, r.LOCKSTATUS, r.USER_ID, u.FIRST_NAME, u.LAST_NAME, r.COST_IMPACT_DISTTYPE, r.SCHEDULE_IMPACT_DISTTYPE, r.NO_PERFORMANCE_IMPACT, r.NO_COST_IMPACT, r.NO_SCHEDULE_IMPACT from APP_ERR.RISK r left outer join APP_ERR.PROJECT_VIEW_NEW p on r.PROJECT_ID = p.PROJECT_ID join APP_ERR.RISKCATEGORY c on r.RISKCATEGORYID = c.id left outer join APP_ERR.OCCURRENCECONFIDENCE o on o.ID = r.OCCURRENCECONFIDENCEID left outer join APP_ERR.RISKOWNERDISCIPLINE d on d.id = r.RISKOWNERDISCIPLINEID left outer join APP_ERR.RISKMANAGER m on m.id = r.RISKMANAGERid left outer join APP_ERR.PERFORMANCEIMPACTCATEGORY p on r.PERFORMANCEIMPACTTYPEID = p.ID left outer join APP_ERR.RISKSTATUS s on s.id = r.RISKSTATUSID left outer join app_ERR.PROJECTPHASES h on h.PHASEID = r.PROJECTPHASEID left outer join app_err.PHASEMILESTONE n on n.id = r.PROJECTMILESTONEID left outer join app_err.TEAM_MEMBERS_LOOKUP u on u.USER_ID = r.USER_ID order by r.project_id, r.risk_id