## Export Worksheet
RISK_ID | PROJECT_ID | PROJECT_NAME | P2_LOOKUP | RISK_NAME | RISKCATEGORY | RISKCATEGORYID | RISK_STATEMENT | PROB_OCCURRENCE | PROB_OCCURRENCE_EVIDENCE | OCCURRENCECONFIDENCEID | CONFIDENCE | RISKOWNERDISCIPLINEID | DISCIPLINE | DISCIPLINE_ACRONYM | RISKMANAGERID | RISKMANAGER | PERFORMANCEIMPACTTYPEID | PERFORMANCEIMPACT | PERFORMANCEIMPACT_DESC | PERFORMANCEIMPACT_IMPCT | PERFORMANCEIMPACT_RISK_RANKING | COST_IMPACT_LOWEST | COST_IMPACT_MOSTLIKELY | COST_IMPACT_HIGHEST | COST_IMPACT_EVIDENCE | COST_RISK_RANKING | SCHEDULE_IMPACT_LOWEST | SCHEDULE_IMPACT_MOSTLIKELY | SCHEDULE_IMPACT_HIGHEST | SCHEDULE_IMPACT_EVIDENCE | SCHEDULE_RISK_RANKING | RISKSTATUSID | ID | RISKSTATUS | PROJECTPHASEID | LIFECYCLEPHASENAME | PROJECTMILESTONEID | ID_1 | MILESTONE | EDITDATE | LOCKSTATUS | USER_ID | FIRST_NAME | LAST_NAME | COST_IMPACT_DISTTYPE | SCHEDULE_IMPACT_DISTTYPE | NO_PERFORMANCE_IMPACT | NO_COST_IMPACT | NO_SCHEDULE_IMPACT
1 | 2307 | Miami-Dade Back Bay Coastal Storm Risk Management Feasibility Study, Miami-Dade County, Florida | 476677 | Florida Statute - Biscayne Bay Preserve | Legislative or Political | 8 | Florida Statute 258.397 Biscayne Bay Preserve - limits filling and dredging within Biscayne Bay. https://www.flsenate.gov/laws/statutes/2019/258.397 Coordinating agencies include Miami-Dade County Department of Environmental Resources Management and Florida Department of Environmental Protection. | 5 |  |  |  | 13 | Planning - Plan Formulation | PLP | 488 |  | 6 | Compliance | This will impact all measures in the Biscayne Bay including the 2021 Recommended Plan | 10 | 4 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | Environmental compliance will be impacted without a coordinated path forward. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-17 14:10 | 0 | 488 |  |  | 299 | 299 | 0 | 0 | 0
2 | 2307 | Miami-Dade Back Bay Coastal Storm Risk Management Feasibility Study, Miami-Dade County, Florida | 476677 | Coastal Barriers - Haulover Inlet | Info and Data Analysis | 1 | Environmental Compliance requires exact footprint of outer barrier location. That will be a challenge without modeling several different scenarios to determine the best location. Bridge Scour analysis is needed, sedimentation analysis is needed, and ADCIRC modeling refinement is needed to understand if out barrier lowers the water levels in the Back Bay. Cost and time may be a factor. | 4 | It is very likely that complications or non compliance will occur if the Inlet is not modeled. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 5170 |  | 6 | Compliance | If the ADCIRC ERDC modeling determines that the outer barrier is ineffective, then this may change the focus on where to provide structural measures. | -10 | 1 | 0 | 0 | 0 | cost has not been estimated at this time. The cost of a sector gate at this inlet could be prohibitive. | 1 | 0 | 0 | 0 | There will be a schedule impact because the ADCIRC analysis has to occur to decided if out barriers are needed. Timeframe has not been estimated to complete modeling. | 1 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 18:44 | 0 | 5170 |  |  | 299 | 299 | 0 | 0 | 0
2 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | BUDM/Placement Analysis | Info and Data Analysis | 1 | There is a wide range of anticipated dredged material volumes early in the study (from 5MCY to well over 20 MCY). The risk is ensuring there is sufficient capacity in identified placement sites to accommodate the volumes both for the initial construction and the 20-year O&M. Current Placement Area opportunities include Egmont (nearshore/beach/island restoration), 2D, 3D, ODMDS, viable dredge holes (4), island creation (for private use, bird habitat creation, and seagrass restoration), permitted Port site, Manatee County boat launch site. Team will conduct least cost analysis. Viable options that are not least cost will be pursued to see if there is a cost sharing partner to pay incremental difference. | 3 |  |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 15:01 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
4 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Subsurface Utilities | Site Conditions | 6 | EN recalls that TECO possibly has a gas line that intersects the proposed project area. EN mentioned that the subsurface utilities did not interfere with the previous plans to Widen Cut-B. To mitigate risk, it is necessary to obtain a map of all subsurface utilities. | 3 | EN recalls that TECO possibly has a gas line that intersects the proposed project area. EN mentioned that the subsurface utilities did not interfere with the previous plans to Widen Cut-B. Consequence if subsurface utilities do interfere: delay in study approval and/or increase cost. |  |  | 6 | Engineering - Structural Design | ESD | 2963 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-17 19:56 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
5 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Study Funding Delays | Agency Policy and Process | 7 | The PDT's available funding as of 1-JUN will likely only last the PDT through June. When SAJ requested additional funding in May, funding was denied and the MSC/HW indicated additional study funds may not be approved until a decision on the exception request is made | 3 | Likelihood is solely dependent on leadership/vertical team |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other | Funding needs must be met for the study to stay on schedule. | 10 | 3 | 0 | 0 | 0 |  | 1 | 0 | 120 | 0 | If funding is delayed, the schedule will be delayed. the TSP milestone will not be met | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 13:53 | 0 | -99 |  |  | 299 | 299 | 0 | 0 | 0
6 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Widening of Passing Lanes | Site Conditions | 6 | Widening for passing lanes would be conducted from the centerline of the channel rather than to one side only. Deepening of the channel would impact hardbottoms (HB) on both sides of the channel; however the difference of deepening impacts compared to the widening impacts to these HB are unknown. There is a risk of greatly increasing HB impacts from widening both sides of the channel over the impacts resulting from deepening alone. Additional HB surveys (in situ, qualitative, and quantitative) may be required to assess impacts if widening is determined to cause impacts over deepening alone. Additional mitigation may be required if impacts are greater | 3 | Hardbottom surveys are ongoing (As of MAY-202X). Impacts will be better understood when these surveys are complete in Fall 202X |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 2963 |  | 5 | Other | Mitigation is available through beneficial use of the rock dredged during construction | 5 | 2 | 0 | 0 | 0 | Additional HB surveys to evaluate impacts could be expensive and time-consuming, increasing cost. | 1 | 0 | 0 | 0 | Additional HB surveys to evaluate impacts could be expensive and time-consuming, delaying the study. | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-05-18 14:07 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
7 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Federal Funding | Agency Policy and Process | 7 | There will be a gap in Federal funding streams for the study after the AMM. NFS can accelerate their share of the funding. Three various efforts are in play during the spring (earmark, workplan, infrastructure bill) which could help in getting needed Federal funding. 15-FEB-22: Funding from IIJA was approved in early 2022 to fully fund the Federal portion of the study at $3M. Based on the $4.5M study budget, these federal funds will be sufficient to fund the study through the TSP (Spring 2023) | 1 | There are several avenues in play, subject to change |  |  | 17 | Project Management | PRM | 514 |  | 8 | Agency Strategy | Team would need to stop work if all funds exhausted. 1-APR-2022: There is sufficient time to plan ahead to maintain funding streams consistent with the authorized budget. The rating was downgraded from "major problem" to "minor problem", but is dependent upon receiving a decision to the exception request by 1-JUL to avoid schedule impacts. | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | There is a risk that if there is a gap in Federal funding for too long, NFS accelerated funds may be exhausted, causing a study delay and risk to 3-year schedule | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 14:36 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
8 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Cultural Resources Surveys | Info and Data Analysis | 1 | The team is currently not pursuing a Programmatic Agreement (PA), but to reduce risk will conduct needed surveys for placement areas during feasibility. Channel is generally already surveyed but there could be some additional surveys | 2 |  |  |  | 14 | Planning - Cultural Resources | PLC | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 | A wide array of placement areas is under consideration. All options may need to be analyzed if some are not screened out early, and may require additional funding | 1 | 0 | 0 | 0 | A wide array of placement areas is under consideration. All options may need to be analyzed if some are not screened out early, and may require additional time | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 14:48 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
9 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Environmental Surveys & Effects Analysis for Placement | Info and Data Analysis | 1 | If placement options are not decided upon with enough time, then must include all in NEPA analysis, including potential surveys, which would take more time, funding, and effort | 3 |  |  |  | 16 | Planning - Environmental | PLE | 8837 |  | 5 | Other | More time and funding needed to include all placement options in NEPA analysis | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 14:53 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
10 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Policy Exception for Additional Funding | Agency Policy and Process | 7 | Scope necessitates a need for a policy exception for an additional $1.5M to perform the needed analysis through the TSP. Exception request was submitted in early 2022. There is some risk and uncertainty as to whether a policy exception will be granted. | 3 | If a decision is not made by 1-JUL-2022, there would be significant schedule delays to realign scope of study to enable its completion in 3 years and under $3M. |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other | Port would lose the chance for Corps to do important analysis on reducing congestion (through passing lanes) and maneuverability (turning basins) | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 15:05 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
11 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Environmental Compliance - Hardbottom & Seagrass Surveys | Info and Data Analysis | 1 | Environmental compliance such as a BO could require more extensive seagrass/channel edge surveys. Multibeam and camera drops could be needed to provide additional information. Study will use side scan sonar to better understand extent of hardbottom along channel, to complete environmental compliance during feasibility for effects analysis. Study will use existing seagrass surveys to begin assumptions for effects analysis and could propose to complete final surveys in PED/prior to construction to refine placement locations to avoid seagrass or refine effects as needed. | 3 | Env surveys were conducted in ~2008 for Cuts A and B. Agencies likely have seagrass surveys that could be used for planning purposes and effects analysis. |  |  | 16 | Planning - Environmental | PLE | 8837 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 15:08 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
12 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | UMAM Impact Analysis | Info and Data Analysis | 1 | Team will use UMAM for impacts analysis, NMFS HCD is onboard. There could be risk if support changes | 1 | This was coordinated with NMFS HCD in an email on 10-DEC-2021, where NMFS HCD agreed with the path forward to use this model. |  |  | 16 | Planning - Environmental | PLE | 8837 |  | 5 | Other | Team would need to re-coordinate model for effects analysis | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 15:08 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
13 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Scope Selection | Agency Policy and Process | 7 | Team has evaluated scopes relative to key problems, for multiple parameters of time and funding, under 9 key risk drivers. This scope still has many challenges but the over risk to completing it in the funding/timeframe is medium. The team will proceed with scope 2 for the study analysis, per Port decision at meeting on 12/8/2021 (analysis of incremental deepening, incremental wideners for transitions, passing lanes and turning basins, as well as beneficial use). | 1 | Very low likelihood. Team has evaluated scope. |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-18 18:44 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
14 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Ship Simulation | Info and Data Analysis | 1 | Study will include ship simulation during feasibility study for passing lane and turning basin analysis for design and optimization of footprint. Ensure have adequate time and funding to include it. | 2 | Unlikely, ROM costs and timeframe has been included in the study scope and budget. |  |  | 6 | Engineering - Structural Design | ESD | 2963 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 18:11 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
15 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | EQ/OSE/RED Qualification Benefits Analysis | Agency Policy and Process | 7 | Risk that EQ/OSE/RED quantification benefits analysis is new, and many districts may be doing it differently, making it difficult to know what the standard process should be to meet policy requirements. Also, given the post-pandemic world many business and operations are changing and may change during or after the analysis. | 3 | Somewhat likely given new guidance without implementation guidance |  |  | 15 | Planning - Economics | PLE | 2265 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 18:33 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
16 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Design Vessel Selection | Info and Data Analysis | 1 | Ensure that the proper design vessel(s) are selected/explored when evaluating the potential scope of the study. Risk of a poor planning decision if study team doesn't holistically look at the vessels utilized at the neighboring ports such as Mobile, New Orleans, and Houston. | 2 | 1-MAR-22: Design Vessel was selected and PTB concurred with the appropriateness of its use. |  |  | 15 | Planning - Economics | PLE | 2265 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-18 18:47 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
17 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Deepening beyond 50 feet | Info and Data Analysis | 1 | Preliminary analysis shows that depths just off the outer entrance channel are ~50 feet. Potential deepening beyond that could cause a need to deepen beyond that, so ensure a gradual transition for vessels. This could have a large cost implication for the cost analysis pertaining to those alternatives. | 3 | This still needs to be understood and analyzed further by the team. |  |  | 6 | Engineering - Structural Design | ESD | 2963 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 19:04 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
18 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | H&H Modeling Needs | Info and Data Analysis | 1 | Numerical modeling of disposal site suitability (waves/sediment transport) as well as effects of disposal sites (flushing/circulation) may be needed later, to support env compliance. The need, extent, and type of numerical modeling has not yet been identified. When the need/extent/type of numerical modeling is identified, it could be later in the study process leading to schedule delays and cost increases. | 3 |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-05-18 19:10 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
19 | 3069 | Tampa Harbor Navigation Improvement Study | 499774 | Relocation of ATONS | Site Conditions | 6 | USCG ATONS will likely be affected from a TSP/recommended plan due to potential passing lanes. Relocations of ATONS must be coordinated with USCG and are also paid for Federally out of USCG. These take a lot of coordination and could be expensive. USCG needs time to vet and plan for these changes and costs. USCG may need more time or have funding constraints. | 3 | It is somewhat likely, but more unlikely if coordination begins early. |  |  | 13 | Planning - Plan Formulation | PLP | 514 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-18 19:14 | 0 | 4951 |  |  | 299 | 299 | 0 | 0 | 0
1 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Road not completed from Akutan Harbor to Akutan | Stakeholder, Sponsor or Partners | 9 | Road not completed from Akutan Harbor to Native Village of Akutan May not be able to utilize Akutan Harbor to transport goods/passengers in and out of Akutan Road was not required LSF for the Akutan Harbor Project | 2 | original likelihood: none Road was not required LSF for the Akutan Harbor Project Funding has been received to construct road and permit application with USACE updated 2023. Materials will be stockpiled during 2023, construction 2024. |  |  | 13 | Planning - Plan Formulation | PLP | 7887 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-03-14 19:29 | 0 | 7887 |  |  | 299 | 299 | 1 | 1 | 1
2 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Some economic benefit categories may be unknown | Info and Data Analysis | 1 | Some economic benefit categories may be unknown. On-site open discussion allows for other potential benefit categories and project impacts to come to light, without those discussion opportunities our data may be limited. May leave unknow benefits undocumented. | 3 | original likelihood: low On-site meetings planned in the near future |  |  | 15 | Planning - Economics | PLE | 5479 |  | 7 | Agency Reputational |  | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | andria, update?? | 1 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 19:31 | 0 | 7887 |  |  | 299 | 299 | 0 | 1 | 0
3 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Under/overestimating benefits | Info and Data Analysis | 1 | Only transportation cost savings and reduced delays were considered during FID May not account for all benefits Could lead to inaccurate documentation of benefits and inaccurate BCR | 2 | original likelihood: low Other benefits will be examined during feasibility |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 19:32 | 0 | 7887 |  |  | 299 | 299 | 0 | 1 | 1
4 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Use of pre-COVID transportation data | Info and Data Analysis | 1 | Decline in transportation since 2020 assumed to be solely due to COVID-19 pandemic. Pre-pandemic transportation levels are assumed to be more accurate for long-term transportation demand. Most recent data is not used. Fail to capture other causes in transportation decline. Fail to capture post-pandemic tranportation changes if transportation demand is not expected to return to pre-pandemic levels Potential to misidentify a transportation trend that could impact the economic analysis. Could lead to inaccurate analysis of future conditions | 4 | original likelihood: High Unknown if decline was due solely to COVID-19 and only way to verify is post-pandemic transportation levels which are not available |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:34 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
5 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | subsistence benefits | Site Conditions | 6 | Assumed knowledge of fishing/hunting areas and project would improve access to these areas. Fishing/hunting areas may not be completely known or the project may not improve access to the areas. Could lead to inaccurate documentation of OSE benefits Fishing/hunting areas may not be completely known or the project may not improve access to the areas Could lead to inaccurate documentation of OSE benefits | 1 | original likelihood: low Community meeting and reaching out to the Community POC on subsistence are planned for the near future and subsistence will be one of the topics discussed |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 19:35 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
6 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Negative Impacts | Info and Data Analysis | 1 | May have negative impacts that we are not identifying. Might miss some negative impacts from the projects. Could lead to inaccurate economic analysis | 1 | original likelihood risk: low Community meetings are planned in the near future. Meeting held in November. |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 19:36 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
7 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Project justification on NED benefits | Info and Data Analysis | 1 | It is assumed that the project would be able to be justified on NED benefits due to the intitial FID analysis, however, some costs and benefits have been identified since the FID which may lead to the need to justify the project based on OSE benefits. If the feasibility study does not identify an NED justified plan, pivoting to OSE justification will be more difficult and likely more time consuming due to data gathering and communication requirements. | 0 | original likelihood: Medium If the project cannot be justified on NED benefits, the team will need to pivot to OSE justification |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 17:59 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
8 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Underestimating costs | Info and Data Analysis | 1 | Costs for shuttle vessel, O&M for shuttle vessel and LSF were not included in the FID cost estimates. The absence of cost for vessel, OMRR&R and LSF could lead to inaccurate BCR | 2 | original likelihood: Low Could impact project cost |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 18:01 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
9 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Misappropriation of benefits | Info and Data Analysis | 1 | As shuttle transport would be a new activity, the transportation benefits may be treated as recreation benefits, not commercial benefits Could lead to misappropriation of benefits | 0 | original likelihood: not filled out. |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 18:02 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
10 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Shuttle vessel operating limitations | Info and Data Analysis | 1 | Based on vessel feasibility report, the shuttle vessel design would allow operation in conditions up to an 8 ft wave and a 20 knot wind, which may preclude operation for a substantial portion of time. If vessel operating limitations are not considered it could lead to overstating benefits Possibly lead to inaccurate economic analysis | 0 | Original likelihood: low Operational conditions will be examined during feasibility |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 18:05 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
11 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Aircraft operating limitations | Info and Data Analysis | 1 | Aircraft can only operate in conditions with windspeed of less than 15 knots. This may limit the flights in and out of Akutan airport. If aircraft operating limitations are not considered it could lead to overstating benefits | 0 | Original likelihood: low Operational conditions will be examined during feasibility |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 18:07 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
12 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Site selection will likely be a previously impacted area. | Info and Data Analysis | 1 | Historic properties are located all along the coast, the proposed project site has been previously impacted. Historic properties are located all along the coast, the proposed project site has been previously impacted. | 0 | original likelihood: low Cultural Resources coordination and analysis will occur during feasibility and PED |  |  | 14 | Planning - Cultural Resources | PLC | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 18:16 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
13 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Identify cultural resources at the site through existing doc | Site Conditions | 6 | Cultural resources can include aspects like sites used for traditional dancing, greeting places, worship, etc. May have positive economic benefits/negative impacts to cultural sites that have not been formally documented. Possible increase in project costs and negative impacts to cultural resources | 0 | original likelihood: low Cultural Resources coordination and analysis will occur during feasibility and PED |  |  | 14 | Planning - Cultural Resources | PLC | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:17 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
14 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | ESA/MMPA Policy Exception | Legal or Regulatory Actions | 10 | There may be a need to submit a policy exception request due to blasting requirements Project schedule could be delayed if policy waiver is not begun early in the process Possible delayed schedule if policy waiver is not obtained during feasibility, if needed. | 3 | original likelihood: low Determination of policy waiver is planned for early in the study to initiate a policy waiver, if required |  |  | 14 | Planning - Cultural Resources | PLC | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:19 | 0 | 7887 |  |  | 299 | 299 | 0 | 1 | 0
15 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Unknown nearshore bathymetry | Info and Data Analysis | 1 | Bathymetry cannot be collected in the nearshore zone due to the small tide range and safety concerns for operating a vessel in shallow waters near an apparent rocky shoreline. Bathymetry will be interpolated from deeper waters to the base of the shoreline where data can be collected by terrestrial methods. This lack of data produces uncertainties in breakwater and dredging quantities and produces more uncertainty of the character of bottom materials. If interpolation/assumptions are incorrect, it could lead to increased project cost and non-performace of the project | 0 | original likelihood: medium There will be some uncertainty regarding the interpolations |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:21 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
16 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Unknown nature of materials to be dredged | Info and Data Analysis | 1 | Aerial imagery shows a mix of rock outcrops and granular material along the coastline in the study area. It is not known how deep the granular material deposits are which would affect the efficiency of dredging operations. Dredging requirements for these materials are significantly different. Blasting may be required to remove the rocky materials. Mechanical methods would be needed to remove materials loosened by blasting. The assumption can be made that all materials will require blasting for removal. Blasting requirements may lead to increased project cost and need for ESA/MMPA policy exception | 0 | original likelihood: medium Dredging requirements will be analyzed during feasibility. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:23 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
17 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Availability of suitable stone to construct breakwaters at A | Info and Data Analysis | 1 | There may be an effort to try to assume rock can be mined locally or nearby to construct breakwaters at Akun. No known quarries are available on Akun or Akutan. Rock Sources at Dutch Harbor are not known to produce rock in sufficient quantity or quality for this project. The closest known active quarries are located at Cape Nome or Sand Point. Rock may have to be transported from Cape Nome or Sand Point for the project If a local source of rock is not available, it could increase project cost | 0 | original likelihood: low Rock sourcing will be examined during feasibility |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:24 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
18 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Wave conditions required for safe operation of ferry service | Info and Data Analysis | 1 | The team will need to decide on vessel dimensions and determine the sea conditions in which the vessel can transit the channel between Akun and Akutan. Assumption of design vessel characteristics should be vetted with community leaders or stakeholders such as APICDA to make a reasonable assumption of the characteristics of the design vessel. With any vessel assumption, there is a risk that the vessel that is eventually used for this purpose does not meet these assumptions and may not be able to operate in the conditions assumed in the study. If vessel cannot operate under assumed conditions, could lead to overstating benefits and underperformance of the project | 0 | original likelihood: low Wave conditions, operational conditions and vessel design will be examined during feasibilty |  |  | 13 | Planning - Plan Formulation | PLP | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 19:26 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
19 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Percent dredge needs blasting for cost estimates | Info and Data Analysis | 1 | If assumption is low, can result in increased costs as well as possible increase in environmental impacts Increase in study costs, increase in enviromental impacts, Increase in study time Under estimation of blasting requirements would result in schedule and budget overruns due to increased blasting, increase disposal, and possibility of the unanticipated need for an EIS | 0 | Geotechnical data can be utilized to accurately determine amount of blasting needed in the project Ensure data from geotechnical study incorporated into cost estimates and feasibility report as soon as it becomes available Geotech data preliminary data shows some discrepancies in the collected data. Awaiting determination of how these discrepancies will be resolved |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-16 15:46 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
20 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Delays could be incurred due to inclement weather | Site Conditions | 6 | If not accounted for via contingency, budget and schedule could be impacted. High winds and waves are not uncommon | 3 | Tolerate the risk |  |  | 13 | Planning - Plan Formulation | PLP | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-16 15:47 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
21 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Changes in storm/wave frequency could impact subsis/commerc | Site Conditions | 6 | If weather events occur, project costs and time could increase Climate change/sea level rise are ongoing global events Follow USACE guidance developed to account climate change related uncertainty | 0 |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 15:49 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
22 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Cultural resources | Site Conditions | 6 | would need to investigate, mitigate if occurs Cease construction, investigate, possibly mitigate If cultural resources are found, work would be stopped increasing time and costs associated with the project | 3 | Known cultural resources sites in project area |  |  | 14 | Planning - Cultural Resources | PLC | 3455 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:13 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
23 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Dredge material disposal | Site Conditions | 6 | What is the most appropriate method for dredge material disposal Without proper dredge disposal analysis, it could have impacts to cost and environment If dredge material is disposed improperly it could lead to higher project costs and environmental consequences | 1 | Disposal area coordinate points have be identified and no known HTRW in the project area |  |  | 16 | Planning - Environmental | PLE | 525 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:15 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
24 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | CERCLA/HTRW materials | Site Conditions | 6 | No known contamination in the project area If CERCLA/HTRW are discovered, it would increase disposal costs If HTRW were found, it could lead to higher project costs and environmental consequences | 1 | No known HTRW in the project area |  |  | 16 | Planning - Environmental | PLE | 525 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:16 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
25 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Additional geotechnical investigations in PED | Site Conditions | 6 | Exisiting geotechnical data used to estimate project quantities and methods If estimates were inaccurate, it could lead to an increase in project costs If geotechnical estimates were inaccurate, it could impact project costs and time | 0 | There is existing geotechnical data for much of the area, but not all of it |  |  | 3 | Engineering - Geotechnical | EGT | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-03-16 17:18 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
26 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Shoreline erosion | Site Conditions | 6 | Shoreline erosion may occur due to project implementation Nearshore wave and circulation patterns could be changed due to project implementation which may increase erosion If shoreline erosion occurred at a higher rate, O&M costs could be impacted | 1 | Modelling has taken into account longshore sedimentation rates and circulation patterns Beneficial use of dredge material and local gravel resources to mitigate erosion |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7887 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:23 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
27 | 3130 | Akutan Harbor Navigational Improvements, AK | 495160 | Trident moves out of Akutan | Stakeholder, Sponsor or Partners | 9 | Trident may move from Akutan to Dutch Harbor . Raw seafood tax pays AEB 2% and Akutan 1%. Loss of this revenue may result in inability to pay for LSF features | 3 | Trident subsidary LFS Inc awarded 75 year lease of Unalaska - Captains Bay tidelands and are building a dock. Trident has stated that the Akutan facility needs to be updated. |  |  | 15 | Planning - Economics | PLE | 5479 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-16 17:24 | 0 | 7887 |  |  | 299 | 299 | 0 | 0 | 0
1 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | EO 11988 Floodplain Management | Agency Policy and Process | 7 | EO 11988 states ":in order to avoid to the extent possible the long- and short-term adverse impacts associated with the occupancy and modifications of floodplains and to avoid direct or indirect support of floodplain development wherever there is a practicable alternative" Structural recommendations could be found non-compliant with EO 11988 due to inducing development in the Mossdale Tract area. | 3 | The previous study, the 2018 Interim Report, delayed recommendations for the Mossdale Tract area due to this issue, however the scope of the study includes a robust EO 11988 analysis combined with risk-informed planning to include a risk assessment and development of a Flood Plain Management Plan concurrent with the study. |  |  | 13 | Planning - Plan Formulation | PLP | 298 |  | 5 | Other | Not meeting compliance requirements with EO 11988 will lead to a negative Federal interest determination in regard to structural flood risk management in RD17 (Mossdale Tract). If this is the case, structural flood risk management measures will not move forward to PED and construction and the non-Federal sponsor's objectives of meeting SB 5 requirements will not be met. The outcome could result in a recommendation that does not meet the study objectives of the primary project purpose. | 10 | 3 | 0 | 300000 | 0 | $300,000 has been included in the scope of the study to mitigate this risk to the current level. | 2 | 0 | 0 | 0 | EO 11988 analysis is planned to be complete concurrent with TSP development. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-31 14:02 | 0 | 298 |  |  | 299 | 299 | 0 | 0 | 0
3 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Study Delays: Economic Modeling Software Updates | Info and Data Analysis | 1 | An update to HEC-FDA 1.4.3 is currently going through approval processes so that economic analysis will be migrated to TotalRisk 2.0. Delay in study completion due to incorporation of updated economic modeling software. | 2 | Plan to utilize TotalRisk with certification expected before TSP as coordinated with the vertical team. HEC-FDA will also be utilized to validate findings in the new modeling software. |  |  | 15 | Planning - Economics | PLE | 5615 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 15:19 | 0 | 7687 |  |  | 299 | 299 | 0 | 0 | 0
4 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Study Delays: Ecosystem Restoration Modeling | Info and Data Analysis | 1 | CE/ICA model runs could be delayed due to negotiation timelines and conflicting priorities with USFWS and NMFS and environmental data collection. USFWS may recommend models that are currently not certified for evaluation of ER features. This scenario would require close coordination and cooperation with the ECO-PCX and USFWS to ensure TSP milestone is not delayed. | 3 | Early coordination and communication with USFWS and NMFS will allow the team adequate time to ensure the required agency coordination and data collection is achieved. There is remaining risks that USFWS could require additional models to be certified for the purpose of determining mitigation requirements. |  |  | 16 | Planning - Environmental | PLE | 8753 |  | 5 | Other | There may be conflicting priorities and timelines with the coordination agencies in terms of negotiations and data collection. These model runs are imperative to alternative selection. | 10 | 3 | 0 | 150000 | 0 | CE/ICA model runs would be pushed back to summer/fall 2023. There may be conflicting priorities and timelines with the coordination agencies in terms of negotiations and data collection. Early coordination and communication will allow the team adequate time to ensure the required agency coordination and data collection is achieved. | 2 | 0 | 120 | 0 | CE/ICA model runs would be pushed back to summer/fall 2023. There may be conflicting priorities and timelines with the coordination agencies in terms of negotiations and data collection. These model runs are imperative to alternative selection. No delays are expected as the District plans to utilize existing HSI models that are certified or are anticipated to be certified ahead of the TSP milestone for NER analysis. There is remaining risks that USFWS could require additional models to be certified for the purpose of determining mitigation requirements. This scenario would require close coordination and cooperation with the ECO-PCX and USFWS to ensure TSP milestone is not delayed. | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 20:42 | 0 | 7687 |  |  | 299 | 299 | 0 | 0 | 0
5 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Study Delays: LifeSIM Modeling | Info and Data Analysis | 1 | Justification of OSE and compliance with the 5 January 2021 Policy Directive for Comprehensive Documentation of Benefits may not be met without modeling in Life SIM. Running FDA on the side to verify TotalRisk outputs. FDA may also provide an increased level of comfort for the review team, as it has been the standard model for estimating economic damages and NED benefits. | 2 | Moving towards using LifeSim and TotalRisk to model life loss and annualize economic damages. Also running FDA on the side to verify TotalRisk outputs. |  |  | 13 | Planning - Plan Formulation | PLP | 7687 |  | 5 | Other | Justification of OSE and compliance with the 5 January 2021 Policy Directive for Comprehensive Documentation of Benefits may not be met without modeling in Life SIM. Therefore the study team is planning to incorporate LifeSIM, TotalRisk, and FDA to model life loss, annualize economic damages, and compute project performance. Total Risk certification is expected in Quarter 3 FY23, in advance of the TSP milestone. The team will identify an appropriate level of life loss analysis needed to meet the goals and objectives of the study, but not exceed what is necessary. | 5 | 2 | 0 | 30000 | 0 | The cost difference is not significant and it mitigates potential risk down the road. It is also cost-efficient to do FDA now instead of doing it at the end of the study. | 2 | 0 | 30 | 0 | No schedule delays are expected. HEC-FDA is certified for use if TotalRisk does not get certified in time, or if we cannot get a one-time certification for this project. The study schedule could slip due to incorporating LifeSIM later in the feasibility phase. | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 20:53 | 0 | 7687 |  |  | 299 | 299 | 0 | 0 | 0
6 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Study Delays: Inclusion of Inland Climate Change Analysis | Info and Data Analysis | 1 | Potential delay in study completion and increase in study costs due to inclusion of inland climate change projections over the period of analysis. The State of California is concerned about potential significant increases in flows in the San Joaquin River due to inland climate change impacts over the planning horizon. Relying only upon the historical record for estimating future hydrologic and hydraulic conditions could underestimate the flood risk in the Mossdale Tract area. | 4 | Potential delay in study completion and increase in study costs due to inclusion of inland climate change projections over the period of analysis. There is a medium chance that the inclusion on an inland climate change analysis may significantly impact both schedule and budget. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8752 |  | 5 | Other | Inclusion of inland climate change projections over the period of analysis poses a Medium Risk to performance due to potential delay in study completion, increase in study costs, and impacts to schedule. The PDT is working with the Climate, Preparedness and Resiliency (CPR) Community of Practice (CoP) to determine the appropriate level of analysis to capture potential inland climate change impacts on selecting a recommended plan. Incorporation of inland climate change impacts will extend the study schedule and increase the budget. Not incorporating inland climate change impacts may not be acceptable to the local sponsors and could impact the level of flood risk management recommended for the Mossdale Tract area. The team is planning to conduct a hybrid approach to utilizing inland climate change for a sensitivity analysis, but not within the economic justification for the project. | 10 | 3 | 0 | 300000 | 0 | There is a medium chance that the inclusion on an inland climate change analysis may significantly impact both schedule and budget. A hybrid approach using DWR data for sensitivity analysis (evaluate change to EAD, AEP, CNP) to verify if the plan selection is sensitive to inland climate change. Economic analysis and study recommendation would NOT account for inland climate change impacts; Not included in economic justification. | 3 | 0 | 120 | 0 | There is a medium chance that the inclusion on an inland climate change analysis may significantly impact both schedule and budget. The PDT will prioritize determining the TSP and then conduct additional sensitivity analysis modeling. If a full in-depth analysis is required for plan selection, then study team will request an additional waiver for funding and time to support the completion of the in-depth analysis and incorporation into the project plan selection and economic justification. No study delays if finding confirms hybrid approach using DWR data for sensitivity analyses is not needed. | 3 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 20:19 | 0 | 7687 |  |  | 299 | 299 | 0 | 0 | 0
7 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Poor Planning Decision: Identifying Real Estate | Resource Availability | 5 | The District recognizes the challenge in locating mitigation sites due to limited available real estate within the Mossdale Tract area and the large amount of mitigation that could be required for potential structural measure recommendations of proposed FRM features; risk of inadequate resources to fulfill mitigation required for project implementation. | 4 | The District recognizes the challenge in locating mitigation sites due to limited available real estate within the Mossdale Tract area and the large amount of mitigation that could be required for potential structural measure recommendations. Concurrently with NNBF and ER refinements and alternative analysis, the District will develop potential mitigation locations contributing to the mitigation plan development for structural measures that could be recommended under this study effort. |  |  | 18 | Real Estate | RLE | 7687 |  | 5 | Other | Assumption: The team will know early on what land will and will not be available for acquisition. This will inform the recommended plan features and locations. Despite the teams efforts in conducting appropriate outreach to gage availability of land for mitigation purposes, if there are inadequate resources to fulfill mitigation requirements for project implementation, impacts to overall project would be a major problem. | 10 | 3 | 0 | 0 | 0 | Due to the risk of inadequate resources to fulfill mitigation required for project implementation, the team is conducting appropriate outreach to ensure they are aware of which land would and would not be available for mitigation purposes | 1 | 0 | 0 | 0 | The team will know early on what land will and will not be available for acquisition. This will inform the recommended plan features and locations. With NNBF and ER refinements and alternative analysis, the District will develop potential mitigation locations contributing to the mitigation plan development for structural measures that could be recommended under this study effort. This early recognition of the need for mitigation sites and early coordination could allow for completion of the study mitigation plan concurrently with the overall study schedule. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 18:06 | 0 | 7687 |  |  | 299 | 299 | 0 | 0 | 0
8 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Poor Planning Decision: Levee Design Approval | Agency Policy and Process | 7 | Selection of a plan that complies with USACE levee design guidance, including vegetation on levees. Opposition of the plan unless variances are received to reduce vegetation removal. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 7687 |  | 5 | Other | Unlikely performance impact since the PDT will be focused on selecting a plan that will comply with USACE levee design guidance, including vegetation on levees, or applying for variance during PED and Construction. The PDT will adopt the recommendations from the 2018 interim study to address vegetation on levees and assess the need for a variance during the development of detailed designs in the Pre-Construction Engineering and Design or Construction phases. The Recommended Plan will comply with USACE levee design guidance. | -5 | 1 | 0 | 0 | 0 | Additional mitigation costs to implement the project. Depending on the amount, the mitigation costs could impact the project BCR. Unlikely since the PDT will be focused on selecting a plan that will comply with USACE levee design guidance, including vegetation on levees, or applying for variance during PED and Construction. | 1 | 0 | 0 | 0 | Unlikely since the PDT will be focused on selecting a plan that will comply with USACE levee design guidance, including vegetation on levees, or applying for variance during PED and Construction. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 18:12 | 0 | 7687 |  |  | 299 | 299 | 0 | 0 | 0
9 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Analytical Error: Economics | Info and Data Analysis | 1 | Vertical team opposition to economic justification without HEC-FDA. Study delay in responding to review comments and incorporating HEC-FDA later in the study process. TotalRisk is new software anticipated to be certified in 2023 and therefore additional review comments are anticipated to be generated due to the use of new software. | 0 | Risk resolved - The study team plans to utilize both HEC-FDA and TotalRisk. |  |  | 15 | Planning - Economics | PLE | 5615 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 18:18 | 0 | 7687 |  |  | 299 | 299 | 1 | 1 | 1
10 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Analytical Error: Economic Justification | Agency Policy and Process | 7 | Vertical team opposition to economic justification without HEC-FDA. TotalRisk is new software anticipated to be certified in 2023 and therefore additional review comments are anticipated to be generated due to the use of new software. Study delay in responding to review comments and incorporating HEC-FDA later in the study process. | 0 | Risk resolved - The study team plans to utilize both HEC-FDA and TotalRisk. Unlikely since the PDT will be focused on selecting a plan that will comply with USACE levee design guidance, including vegetation on levees, or applying for variance during PED and Construction. |  |  | 15 | Planning - Economics | PLE | 5615 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 | Risk resolved - The study team plans to utilize both HEC-FDA and TotalRisk. | 0 | 0 | 0 | 0 |  | 0 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-06 18:26 | 0 | 7687 |  |  | 299 | 299 | 1 | 1 | 1
11 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Identification of suitable habitat mitigation sites | Site Conditions | 6 | Identifying habitat mitigation sites has been challenging due to limited opportunities for suitable mitigation sites in the region and the need for a potentially large amount of habitat mitigation. The risk is that not enough habitat mitigation sites would be identified which could stall resource agency support for the project and delay implementation. | 3 | Medium risk carried forward with recommended COA 3. Delay in study completion due to identification of suitable mitigation sites for impacts from proposed FRM project features. |  |  | 16 | Planning - Environmental | PLE | 8753 |  | 2 | Environmental | Minimal if any impact to schedule/cost/performance since a mitigation strategy is being implemented. | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 30 | 0 | The risk is that not enough habitat mitigation sites would be identified which could stall resource agency support for the project and delay implementation. | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-27 15:39 | 0 | 7687 |  |  | 299 | 299 | 0 | 0 | 0
12 | 3430 | LSJ Lathrop Manteca Feasibility Study | 503951 | Inland Hydrology | Info and Data Analysis | 1 | Inland Hydrology is expected to change over the life of this project. THe State of CA has done some analysis but it is not in alignment with the USACE guidance on this data process. The Sea Level and H&H COP do not currently have guidance for an acceptable method to account for inland hydrology change. Due to this the team is running a sensitivity analysis on the data, based on the information that the State has gathered to see if the proposed project will be resilient to future changes in inland hydrology. | 4 | We are already seeing changes impacts to the hydrology in the Central Valley due to climate change. With more extreme weather, atmospheric rivers, and changes in the elevation of the snowpack, we are expecting to have a significant increase in the amount of flow that enters the river system. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8752 |  | 1 | Asset Condition | If we missed the mark on inland climate change and flows are greater than expected then the risk to the project, community, environment, and agency reputation could be huge. We have been approved for an extension to mitigate to try and account for this but any change to policy could upgrade this to a major problem. | 5 | 2 | 200000 | 500000 | 2000000 | Depending on how it is eventually decided how to address inland climate change, this could add a significant cost if guidance is published prior to the completion of the project. The current guidance only requires a qualitative analysis, which is the lowest cost provided. The current plan of doing a sensitivity analysis to make sure the project will have future resilience is the most likely cost. If USACE guidance is developed prior to project completion, the project will have to redo all the hydrology, hydraulics, FDA analysis, risk, and likely alternative selection, which is what the highest value is accounting for. | 4 | 0 | 180 | 770 | Only going by guidance of qualitative analysis, results in no expected project delays. The most likely scenario of doing the sensitivity analysis adds an additional 6 months. If the USACE guidance is revised with a method to quantitatively analyze inland climate change, then that would add 2 years to the project schedule. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-05 21:40 | 0 | 8752 |  |  | 302 | 302 | 0 | 0 | 0
1 | 3511 | C&SF:Flood Resiliency (Section 216) Study, FL | 488589 | Wrong selection of plan | Info and Data Analysis | 1 | Multiple water resources projects within study boundary would potentially have interaction with the C&SF Flood Resiliency Study and could lead to have multiple Future Without Projects at some point of the planning process. This could potentially lead the team to select the wrong TSP. | 3 | There is a possibility for the team to select the wrong Plan |  |  | 13 | Planning - Plan Formulation | PLP | 6246 |  | 7 | Agency Reputational | If another round of alternatives is needed, might impact trust with the stakeholders | 10 | 3 | 200000 | 0 | 600000 | Approximate range of how much funding might be required to incorporate another round of alternatives in other studies | 4 | 30 | 0 | 90 | Approximate range of how much time might be required to incorporate another round of alternatives in other studies | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 18:10 | 0 | 6246 |  |  | 306 | 306 | 0 | 0 | 0
4 | 3531 | Lower Missouri Brunswick L-246 | 496631 | Construction of Federal or Local Projects | Site Conditions | 6 | Construction or alteration to levees, reservoirs, bridges, and other projects can contribute to altered hydraulics. For example, nonfed levee raises increase water surface elevations and are likely to raise stages more frequently, loading L246 and Brunswick more frequently. Not accounting for these future raises, construction projects, etc. means that changes in hydrology and hydraulics are not accounted for. | 2 | It is likely that the nonfed levees have been raised since the 2019 flood and were not captured in recent LiDAR surveys. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 5436 |  | 5 | Other | This risk is a minor problem and, if addressed, would provide improvement. If not addressed, all alternatives will still be compared to the same conditions. If addressed, then the selection of the recommended plan will be based of off the most up to date conditions. | 5 | 2 | 0 | 20000 | 0 | Including updated information related to nearby projects would require reanalysis of the hydraulic modeling effort. Potential cost depends on when the data comes available in the planning process and how much hydraulic reanalysis would have to occur. | 2 | 0 | 15 | 0 | Additional time would be required to update the hydraulic model with updated conditions. Additionally, the alternative models would need to be rerun. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-03 17:55 | 0 | 4830 |  |  | 299 | 299 | 0 | 0 | 0
5 | 3531 | Lower Missouri Brunswick L-246 | 496631 | Test Risk entered by developer | Agency Policy and Process | 7 | Test risk entered by developer Hardee Mahoney | 2 |  |  |  | 9 | Engineering - Civil | ECV | 8774 |  | 5 | Other |  | 5 | 0 | 0 | 500 | 0 |  | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-03 16:17 | 0 | 8774 |  |  | 299 | 299 | 1 | 0 | 1
1 | 3544 | Test A Project | 000000 | TEST risk 1 | Contract Acquisition | 3 | description | 2 |  |  |  | 21 | Construction - Project Engineer | EPE | 2331 |  | 8 | Agency Strategy |  | 5 | 2 | 5 | 0 | 15 |  | 2 | 5 | 0 | 15 |  | 2 | 7 | 7 | Inactive - Decision Made | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-30 15:46 | 0 | 138 |  |  | 306 | 306 | 0 | 0 | 0
2 | 3544 | Test A Project | 000000 | Test Risk 2 | Legal or Regulatory Actions | 10 |  | 1 |  |  |  | 11 | Operations | OPS | 8653 |  | 6 | Compliance |  | 5 | 2 | 1 | 0 | 100000 |  | 2 | 0 | 33 | 0 |  | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-01-19 22:19 | 0 | 8653 |  |  | 306 | 299 | 0 | 0 | 0
3 | 3544 | Test A Project | 000000 | 11 | Legal or Regulatory Actions | 10 |  | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 8653 |  | 5 | Other | 11 | 5 | 2 | 11 | 11 | 12 | 1 | 2 | 1 | 2 | 3 |  | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-01-19 22:25 | 0 | 8653 |  |  | 299 | 302 | 0 | 0 | 0
4 | 3544 | Test A Project | 000000 | Test 002 | Contract Performance | 4 | Short desc | 3 |  |  |  | 7 | Engineering - Electrical | EEL | 8653 |  | 1 | Asset Condition |  | 5 | 2 | 400000 | 0 | 950000 | None | 2 | 0 | 20 | 0 |  | 2 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-01-24 13:49 | 0 | 8775 |  |  | 306 | 299 | 0 | 0 | 0
5 | 3544 | Test A Project | 000000 | Risk Test 0854 | Stakeholder, Sponsor or Partners | 9 |  | 0 |  |  |  | 14 | Planning - Cultural Resources | PLC | 8653 |  | 6 | Compliance |  | 5 | 2 | 500000 | 800000 | 800000 |  | 2 | 0 | 100 | 0 |  | 2 | 7 | 7 | Inactive - Decision Made | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-03-23 19:36 | 0 | 138 |  |  | 306 | 299 | 0 | 0 | 0
6 | 3544 | Test A Project | 000000 | Test 24 Jan 2023 0909 | Agency Policy and Process | 7 | aen;vinaiovnain afan eif'ju39 urh98yyu[[- j'co | 1 | 4 u[94d[9yu09t2j[9g=0-]v |  |  | 14 | Planning - Cultural Resources | PLC | 1 | William Blake | 3 | Human Health and Safety |  | 5 | 2 | 0 | 50 | 0 |  | 2 | 0 | 800 | 0 |  | 4 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-01-24 14:11 | 0 | 138 |  |  | 299 | 299 | 0 | 0 | 0
7 | 3544 | Test A Project | 000000 | risk a | Contract Performance | 4 | writing description here | 2 |  |  |  | 11 | Operations | OPS | 8653 |  | 6 | Compliance |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 350 | 0 | writing evidence here | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-01-31 19:42 | 0 | 138 |  |  | 299 | 299 | 0 | 0 | 0
8 | 3544 | Test A Project | 000000 | Test Save Measure | Site Conditions | 6 | Test Save Measure | 2 |  |  |  | 12 | Other | OTH | 8653 |  | 5 | Other |  | 5 | 2 | 0 | 100000 | 0 |  | 2 | 20 | 0 | 60 |  | 2 | 1 | 1 | Active | 6 | Construction | 17 | 17 | Notice to Proceed | 2023-02-13 17:30 | 0 | 8775 |  |  | 299 | 306 | 0 | 0 | 0
9 | 3544 | Test A Project | 000000 | abc | Legal or Regulatory Actions | 10 |  | 2 |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 486 |  | 5 | Other |  | 5 | 2 | 0 | 50 | 0 |  | 2 | 0 | 5 | 0 |  | 2 | 1 | 1 | Active | 6 | Construction | 18 | 18 | Construction Start Date | 2023-02-27 15:41 | 0 | 138 |  |  | 299 | 299 | 0 | 0 | 0
10 | 3544 | Test A Project | 000000 | 3/6 Test | Legal or Regulatory Actions | 10 |  | 1 |  |  |  | 24 | Safety | SAF | 486 |  | 5 | Other |  | 10 | 2 | 0 | 100000 | 0 |  | 2 | 0 | 100 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-07 14:59 | 0 | 8775 |  |  | 299 | 299 | 0 | 0 | 0
11 | 3544 | Test A Project | 000000 | ABC TEST risk | Communications | 2 | description | 3 |  |  |  | 20 | Public Affairs | COM | 8653 |  | 5 | Other |  | 10 | 3 | 0 | 5000 | 0 |  | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 18 | 18 | Construction Start Date | 2023-03-20 14:26 | 0 | 138 |  |  | 299 | 299 | 0 | 0 | 1
12 | 3544 | Test A Project | 000000 | test risk | Info and Data Analysis | 1 | description | 3 |  |  |  | 7 | Engineering - Electrical | EEL | 138 |  | 3 | Human Health and Safety |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 50 | 0 |  | 2 | 1 | 1 | Active | 6 | Construction | 18 | 18 | Construction Start Date | 2023-04-17 14:39 | 0 | 138 |  |  | 299 | 299 | 0 | 0 | 0
13 | 3544 | Test A Project | 000000 | short desription | Communications | 2 |  | 2 |  |  |  | 7 | Engineering - Electrical | EEL | 1 | William Blake | 2 | Environmental |  | 5 | 2 | 0 | 5000 | 0 |  | 2 | 0 | 5 | 15 |  | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 8 | 8 | Design Start | 2023-03-30 15:41 | 0 | 138 |  |  | 299 | 302 | 0 | 0 | 0
14 | 3544 | Test A Project | 000000 | ABC | Contract Performance | 4 | afeae | 2 | add later |  |  | 15 | Planning - Economics | PLE | 2687 |  | 2 | Environmental |  | 10 | 3 | 0 | 0 | 50 | gsrr | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 17 | 17 | Notice to Proceed | 2023-04-17 13:44 | 0 | 138 |  |  | 306 | 299 | 0 | 0 | 1
15 | 3544 | Test A Project | 000000 | Limited geotechnical investigation, limited data | Info and Data Analysis | 1 | Different site conditions that could lead to increased costs, schedule, poor performance of infrastructure being built | 3 | large levees over large geographical areas likely have different site conditions |  |  | 3 | Engineering - Geotechnical | EGT | 1944 |  | 4 | Operations |  | 10 | 3 | 0 | 500000 | 0 |  | 4 | 0 | 180 | 0 |  | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-04-17 14:38 | 0 | 138 |  |  | 299 | 299 | 0 | 0 | 0
16 | 3544 | Test A Project | 000000 | Test risk | Stakeholder, Sponsor or Partners | 9 | description | 3 |  |  |  | 17 | Project Management | PRM | 2687 |  | 5 | Other |  | 5 | 2 | 5000 | 7500 | 10000 |  | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-05-19 14:28 | 0 | 138 |  |  | 302 | 302 | 0 | 0 | 1
1 | 3545 |  |  | Shoreline placement of Rindge Dam impounded sediment mostly | Communications | 2 | Although the July 2016 field surveys did not identify surfgrass subtidally east of the pier, they could not be certain of that determination for the area less than 10-feet MLLW since the survey vessel could not obtain video in the shallow depths. Subsequently, the sponsor, through visual surveys during low tide, confirmed surfgrass presence in small patches in a boulder field immediately downcoast of the Malibu Pier placement site. | 5 | Proximity immediately downcoast of placement location |  |  | 8 | Engineering - Architectural and Interior | EAI | 2331 |  | 5 | Other |  | 5 | 2 | 0 | 5000 | 0 | 1. Halts shoreline placement of mostly sands. 2. Requires reformulation of placement strategy. 3. May require out of kind mitigation, including artificial reef construction with kelp planting. | 2 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-01-24 14:11 | 0 | 2331 |  |  | 299 | 299 | 0 | 0 | 0
1 | 3552 |  |  | Poor Planning Decision | Communications | 2 | Identify and rank study priorities. Develop study objectives based on these priorities. | 2 | Alternatives have been formulated to specifically address the highest study priorities. |  |  | 14 | Planning - Cultural Resources | PLC | 2331 |  | 5 | Other | If study priorities are not accurately identified, the recommended plan may not address the most severe biological needs of the system. | 10 | 3 | 0 | 5000 | 0 | Study priorities are misidentified or ranked improperly. | 2 | 50 | 0 | 100 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-01-24 13:23 | 0 | 2331 |  |  | 299 | 306 | 0 | 0 | 0
3 | 3552 |  |  | Commodity growth rate projections and fleet forecast needed | Info and Data Analysis | 1 | If future commodity or fleet projections are changed after modeling effort is complete, large schedule delays will occur because portion of modeling will need to be redone | 3 | The commodity growths rates drive the number of TEUs coming to the local ports, therefore, the number of vessels. Any change to the forecast would cause additional analysis and model runs. |  |  | 9 | Engineering - Civil | ECV | 2331 |  | 5 | Other | Vertical team acceptance of Commodity Growth rate projections & future fleet forecast Make no updates in the future. Conduct Sensitivity Analysis at this point on the Commodity growth rates. | 10 | 3 | 0 | 5000 | 0 |  | 2 | 0 | 50 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-01-24 13:56 | 0 | 2331 |  |  | 299 | 299 | 0 | 0 | 0
1 | 3554 |  |  | Climate change are uncertain and could construction | Info and Data Analysis | 1 | description | 4 |  |  |  | 21 | Construction - Project Engineer | EPE | 8692 |  | 7 | Agency Reputational |  | 5 | 2 | 0 | 50000 | 0 |  | 2 | 100 | 200 | 200 |  | 4 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-01-25 20:35 | 0 | 138 |  |  | 299 | 306 | 0 | 0 | 0
1 | 3555 | St. Augustine Back Bay CSRM | 479265 | 3x3x3 Scope, Schedule, and Budget | Agency Policy and Process | 7 | Due to the scope, and size and complexity of the study area, there is a risk to the study schedule and budget, and study may not reach a Chief's Report within 3-years of signing of the FCSA. | 5 |  |  |  | 13 | Planning - Plan Formulation | PLP | 4614 |  | 8 | Agency Strategy | Project will not be 3x3 compliant | 10 | 4 | 0 | 3000000 | 0 |  | 4 | 0 | 1095 | 1095 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-26 16:07 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
2 | 3555 | St. Augustine Back Bay CSRM | 479265 | Cultural Resources Surveys | Info and Data Analysis | 1 | Cultural resources surveys will be needed depending on location and potential measures, | 2 |  |  |  | 14 | Planning - Cultural Resources | PLC | 8781 |  | 5 | Other | If surveys are not completed, project design would have to be changed to mitigate potential impacts to existing cultural resources, resulting in increased budget and time delays | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-14 15:32 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
3 | 3555 | St. Augustine Back Bay CSRM | 479265 | Environmental Surveys - Wetlands | Info and Data Analysis | 1 | Development of mitigation plan dependent on surveys to determine absence/presence and condition of existing wetlands. Survey spatial extent is dependent on TSP footprint. | 4 | Existing knowledge of wetland presence within the study area |  |  | 16 | Planning - Environmental | PLE | 7848 |  | 5 | Other | Potential impacts to environmental resources, changes to project design would be needed to mitigate impacts, resulting in increased budget and time delays | 5 | 2 | 0 | 0 | 0 | This item is included in the study budget | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-04 19:49 | 0 | 4614 |  |  | 299 | 299 | 0 | 1 | 1
4 | 3555 | St. Augustine Back Bay CSRM | 479265 | Future Development | Site Conditions | 6 | Assume all redevelopment is up to new standards | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 390 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 15:42 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
5 | 3555 | St. Augustine Back Bay CSRM | 479265 | Existing Local Measures | Site Conditions | 6 | Degradation of existing seawalls | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 390 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 15:43 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
6 | 3555 | St. Augustine Back Bay CSRM | 479265 | Real Estate Requirements | Stakeholder, Sponsor or Partners | 9 | Public participation and acceptance of required standard estates. The number of stakeholders and property owners in the study area footprint is significant. Some private lands will likely be required for the project. Any real estate that can't be acquired without going to court could negatively impact the acquisition schedule. | 3 |  |  |  | 18 | Real Estate | RLE | 8817 |  | 5 | Other |  | 10 | 3 | 0 | 1 | 0 |  | 4 | 0 | 126 | 253 |  | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-04-26 16:05 | 0 | 4614 |  |  | 299 | 306 | 0 | 0 | 0
7 | 3555 | St. Augustine Back Bay CSRM | 479265 | Inlet surge barrier alternative modeling | Info and Data Analysis | 1 | May need additional/high fidelity modeling for design of inlet closure alternatives | 2 | PDT can make well-informed assumptions on how inlet closure alternatives will perform based on existing models, subject to concurrence from vertical team |  |  | 12 | Other | OTH | 390 |  | 5 | Other | Utilizing the high fidelity models would provide minor improvement to understanding of inlet closure alternatives | -5 | 1 | 50000 | 0 | 100000 |  | 4 | 0 | 365 | 365 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-26 15:50 | 0 | 4614 |  |  | 306 | 299 | 0 | 0 | 0
8 | 3555 | St. Augustine Back Bay CSRM | 479265 | Non-NED recommendation | Stakeholder, Sponsor or Partners | 9 | Tentatively Selected Plan identified is not the NED plan | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 390 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-20 19:44 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
9 | 3555 | St. Augustine Back Bay CSRM | 479265 | Changes in Engineering Modeling Scope | Info and Data Analysis | 1 | The schedule and budget have been created prior to the Initial Flood Driver Screening for the study area results. These results will inform the path forward for addressing compound flood hazards (surge, rainfall, riverine with tides and SLC) or a more simplistic approach addressing surge with tides and SLC. The scope and budget have been created assuming the most complex modeling scenario. | 3 |  |  |  | 9 | Engineering - Civil | ECV | 8814 |  | 5 | Other | The non-Federal sponsor has voiced concern regarding flood risk from rainfall and riverine sources. The team should work with the non-Federal sponsor for buy in of the surge with tide and SLC approach for cohesion moving forward. | 5 | 2 | -100000 | -50000 | 0 | This reduction in the modeling scope would reduced the schedule and budget of the study. | 1 | -255 | 0 | 0 | This reduction in the modeling scope would reduced the schedule and budget of the study. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-23 12:26 | 0 | 8814 |  |  | 306 | 306 | 0 | 0 | 0
11 | 3555 | St. Augustine Back Bay CSRM | 479265 | Update to WRDA 2022 Implementation Guidance | Info and Data Analysis | 1 | The publication of WRDA 2022 implementation guidance could cause the study to change the engineering and economic modeling approach. "WRDA 2022 S8106 would allow for study scopes to expand in two ways: (1) expand coastal storm and inland flood feasibility studies to incorporate other flood risk (e.g., due to erosion, tides, rainfall, subsidence, groundwater emergence), and (2) expand feasibility studies to include water supply, water conservation, and measures to reduce water resource impacts of extreme weather events, including drought." https://www.usace.army.mil/Missions/Civil-Works/Project-Planning/Legislative-Links/WRDA-2022/ | 3 |  |  |  | 13 | Planning - Plan Formulation | PLP | 390 |  | 5 | Other |  | 10 | 3 | 0 | 0 | 500000 | Publication of implementation guidance could effect engineering and economic modeling, scope, schedule, and budget. | 4 | 0 | 0 | 365 | Publication of implementation guidance could effect engineering and economic modeling, scope, schedule, and budget. | 3 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-26 16:08 | 0 | 8814 |  |  | 306 | 306 | 0 | 0 | 0
12 | 3555 | St. Augustine Back Bay CSRM | 479265 | Risk Reduction and Economic Benefits Beyond Study Area | Info and Data Analysis | 1 | Due to the nature of the City of St. Augustine municipal boundary and the surrounding water bodies, it is likely that risk reduction and economic benefits will occur outside of the study area (dependent on PSE). | 4 |  |  |  | 15 | Planning - Economics | PLE | 162 |  | 5 | Other | It will be imperative to the study to understand the total benefits to the the study area and surrounding areas to accurately capture a BCR. This may also include using best engineering judgement to determine benefit extends (PSE of a surge barrier for example) without high fidelity modeling. | -10 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-23 13:11 | 0 | 8814 |  |  | 299 | 299 | 0 | 1 | 1
13 | 3555 | St. Augustine Back Bay CSRM | 479265 | CBRA Compliance | Agency Policy and Process | 7 | The USFWS may not consider several alternatives to be compliant with the Coastal Barrier Resource Act (CBRA). There are two CBRA system units within the study area. | 3 |  |  |  | 16 | Planning - Environmental | PLE | 390 |  | 8 | Agency Strategy |  | 10 | 3 | 50000 | 100000 | 150000 |  | 4 | 90 | 180 | 270 |  | 3 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-20 12:38 | 0 | 390 |  |  | 302 | 302 | 0 | 0 | 0
14 | 3555 | St. Augustine Back Bay CSRM | 479265 | PDT Workload & Turnover | Resource Availability | 5 | PDT workload on other projects and turnover of key PDT members over the course of the study could impact schedule and budget. | 3 |  |  |  | 17 | Project Management | PRM | 8994 |  | 5 | Other |  | 5 | 2 | 50000 | 100000 | 150000 |  | 4 | 90 | 180 | 365 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-20 12:42 | 0 | 390 |  |  | 302 | 302 | 0 | 0 | 0
15 | 3555 | St. Augustine Back Bay CSRM | 479265 | Interior Drainage | Info and Data Analysis | 1 | Uncertainty of impacts of alternatives to interior drainage systems, and adjustments that may be necessary to incorporate | 0 |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8814 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-04-26 15:20 | 0 | 4614 |  |  | 299 | 299 | 0 | 0 | 0
16 | 3555 | St. Augustine Back Bay CSRM | 479265 | Possibility of having no NED justified plan | Agency Policy and Process | 7 | If alternative accounts' benefits are not apparent team recommendation will be study termination. | 1 |  |  |  | 15 | Planning - Economics | PLE | 162 |  | 8 | Agency Strategy |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-26 19:45 | 0 | 162 |  |  | 299 | 299 | 0 | 1 | 1
17 | 3555 | St. Augustine Back Bay CSRM | 479265 | Identification of economic study area. | Info and Data Analysis | 1 | Structures not included in the inventory could incur damage. | 2 | If a structure should be included in the inventory, the damage to the structure should not be significant. |  |  | 15 | Planning - Economics | PLE | 162 |  | 8 | Agency Strategy | If additional structures not in the inventory would incur damage, the damage would likely be insignificant. | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-26 19:57 | 0 | 162 |  |  | 299 | 299 | 0 | 0 | 0
4 | 3572 | City of Boston Coastal Storm Risk |  | Inaccurate Floodplain for Formulation and Economic Analysis | Info and Data Analysis | 1 | NACCS uses save points throughout Boston Harbor and interpolates those data points across the terrain showing a 1D result of where the water ends up and incorporates SLC at the first year and the last year in the G2CRM planning model. Will the model provide accurate depiction of the floodplain extents and flood pathway entry point for formulation and economic analysis? | 3 | Without specific refinement, and updating the storm suite, it is likely that the model will not accurately reflect extra-tropical events, nor will it have the refined mesh to depict an accurate floodplain over a 100-year planning horizon. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 5 | Other | An inaccurate floodplain could result in reformulation; significant redesign; post-authorization in the future. | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-24 14:18 | 0 | 4490 |  |  | 299 | 299 | 0 | 1 | 1
5 | 3572 | City of Boston Coastal Storm Risk |  | ECONOMIC DAMAGES IN THE FUTURE WITHOUT PROJECT CONDITION | Info and Data Analysis | 1 |  | 3 |  |  |  | 15 | Planning - Economics | PLE | 2495 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-29 15:03 | 0 | 4490 |  |  | 299 | 299 | 0 | 1 | 1
6 | 3572 | City of Boston Coastal Storm Risk |  | Climate Change Impacts to Floodplain | Info and Data Analysis | 1 | In a dense urban environment with significant tide swings (+9 feet) differences between water surface elevations and floodplains within each curve are significant. Over a 50-year period of economic analysis and a 100-year planning horizon, the impacts of SLC in the study area are also significantly different. The impacts can influence comprehensive benefits analysis; critical resource impacts; as well as impacts to natural resources. | 4 | There is a significant difference in preliminary curves at the low/intermediate/ and High SLC scenarios. It is likely that the formulation will change depending on the accuracy of the FWOP floodplain at both the 50-year and 100-year horizons. 50-year for quantitative analysis and 100-year for qualitative analysis. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 3 | Human Health and Safety | Depending on the model setup conditions and input criteria, the floodplains could understate the risk while still being policy compliant. | 10 | 4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 18:52 | 0 | 4490 |  |  | 299 | 299 | 0 | 1 | 1
7 | 3572 | City of Boston Coastal Storm Risk |  | Programmatic Agreement (Sec. 106) | Legal or Regulatory Actions | 10 | Depending on the alternatives selected, the entire study area is full of historic properties and potential archeological artifacts as well as National Historic Landmarks and significant historic and cultural landscapes. Historic, architectural and archaeological assessments and surveys will likely be required as the study progresses. If areas such as the Naval Shipyard and historic wharfs are identified for significant construction, significant surveys, i.e. in-water surveys may be required prior to the PA being signed. Offshore work would also require remote sensing archaeological surveys depending upon the location and the proposed alternative. | 2 | There is a study cost increase risk if in-water surveys are required prior to executing the PA. Additionally, historic properties assessments and archaeological surveys, both on shore or in water, may be required for specific alternatives identified leading to the TSP. Depending the upon the significance of the historic property or landscape, this could result in additional costs and possible scope modifications either during the FS or PED. |  |  | 16 | Planning - Environmental | PLE | 4490 |  | 5 | Other | If invasive or detailed surveys become required to complete a PA on the Study it will create potential cost and schedule delays. | 10 | 3 | 0 | 300000 | 0 | An initial historic and archaeological assessment of the project study area will be required during the FS to identify historic properties. This assessment will help inform development of the Section 106 PA which will need to be coordinated and executed once the TSP is identified and by the end of the FS. | 2 | 0 | 180 | 0 | If in-water surveys would require AE Contracting and remote sensing equipment. | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-01-30 16:59 | 0 | 4490 |  |  | 299 | 299 | 0 | 0 | 0
8 | 3572 | City of Boston Coastal Storm Risk |  | Acquisition of Real Estate | Stakeholder, Sponsor or Partners | 9 | The number of stakeholders and property owners in the study area footprint is significant. Many areas that will require structural measures are not publicly owned by the City of Boston. Other areas may be identified for managed retreat or buyout as the recommended plan. They are either private or under the control of a different public entity. In order to construct or implement, there may be a significant real estate undertaking; any real estate that can't be acquired could impact the effectiveness of the plan, potentially causing a redesign. | 3 | A redesign post authorization will potentially impact the authorized project, the cost, or the environmental impacts. |  |  | 18 | Real Estate | RLE | 4490 |  | 5 | Other |  | 5 | 2 | 0 | 500000 | 0 | If a redesign is necessary due to real estate acquisition issues it will require both Engineering and NEPA work. | 4 | 0 | 270 | 0 | To develop an EDR and potentially a Supplemental NEPA Document post authorization. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 15 | 15 | BCOES Certification | 2023-01-31 16:46 | 0 | 4490 |  |  | 299 | 299 | 0 | 0 | 0
10 | 3572 | City of Boston Coastal Storm Risk |  | Plan Formulation to SLC Curves | Info and Data Analysis | 1 | USACE CSRM Studies incorporate sea level change into formulation. Policy directs formulation to USACE Curves, the high, intermediate and low scenarios. Teams traditionally formulate to all three curves, or they formulate to the intermediate curve and run sensitivity on the other two. Formulating to the low curve in a study area such as Boston could significantly understate risk; formulating to the high curve could overstate risk and remove opportunities for softer, adaptable solutions. | 4 | Formulating for SLC is not an exact science and it is driven by the conditions of the study area, outputs of the model, as well as critical thresholds. Without risk management, it is very likely the team will formulate to the intermediate curve, because it's often been confused as the accepted practice and risk would be understated in the study area. |  |  | 13 | Planning - Plan Formulation | PLP | 4490 |  | 6 | Compliance | If the study team, inlcuding the sponsor, recommends a plan based on the High SLC scenario, but the PL&C team recommends the Intermediate SLC scenario based on uncertainty it could be a major problem. The result could be either reformulation, or a need for an LPP/NED exception to go with the High SLC scenario. | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 60 | 180 | It is likely there will be some discussion with the ATR and PL&C Team as to which curve is proper, why, and what is driving the decision. When considering the number and level of reviews, it is anticipated and built into the study schedule for 60 days. | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-01 19:07 | 0 | 4490 |  |  | 299 | 302 | 0 | 1 | 0
12 | 3572 | City of Boston Coastal Storm Risk |  | Coastal Model Development Delays | Info and Data Analysis | 1 | Delays associated with development numerical coastal models. Regardless of NACCS or MC-FRM, there are significant changes necessary to develop an accurate existing and future without project model. Delays to coastal modeling could cascade and affect Economics and Cost. | 4 | The study area is very complex and there are several projects and actions by others that need to be developed for the numerical modeling. As large as the study area, it is likely that there will be challenges in developing the FWOP picture. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 5 | Other | There could be delays in releasing the draft report. | 5 | 2 | 0 | 25000 | 0 | If there are issues, the study team will likely need to bring in assistance. | 2 | 0 | 60 | 120 | If there are delays it will likely impact economics and cost disciplines and prolong the schedule. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-23 19:55 | 0 | 4490 |  |  | 299 | 302 | 0 | 0 | 0
13 | 3572 | City of Boston Coastal Storm Risk |  | Incremental Funding | Resource Availability | 5 | Incremental funding of the study will impact schedule and resource availability. The study funding stream indicates a federal need of $750K in FY23 and FY24, followed by $500K in FY25. Any delay or denial of this funding will result in a schedule delay commensurate with the reduced funding. | 5 | The study is being funded through Workplan and Presidents Budget requests. These requests are outside the sphere of influence for CENAE. If there is a delay or shortfall in any of these funding streams, the schedule will be impacted. The FY'23 Workplan request is $500K; currently there is zero money allocated to the Study. The FY'24 PBUD is $550K, which is $200K less than requested. Based on this shortfall, the study is one full year of federal funding behind schedule and will impact schedule by one year. |  |  | 22 | Programs Management | PGM | 4490 |  | 7 | Agency Reputational | The study is already scheduled for five years, in a City that recognizes an immediate need for intervention. Adding another year due to funding shortfalls will have a domino effect on PED and Construction schedules. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 365 | 365 | One year will be added to the schedule based on the funding stream shortfalls. Depending as to where in the study funding stream shortfalls are made up, it will impact the overall study delay. | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 18:16 | 0 | 4490 |  |  | 299 | 306 | 0 | 1 | 0
14 | 3572 | City of Boston Coastal Storm Risk |  | Impacts due to Logan International Airport | Legal or Regulatory Actions | 10 | Logan International Airport and its airspace and flyways are in the study area. Based on needed elevation for structural solutions, flyway, runway end safety zones, and obstruction clearance rules may be impacted. | 3 | Without risk management and cooperating with the FAA, it is likely that an NNBF planned for Belle Isle Marsh, or Wood Isle Marsh would impact study completion. |  |  | 16 | Planning - Environmental | PLE | 4490 |  | 6 | Compliance |  | 10 | 3 | 0 | 5000 | 15000 | The FAA could require additional bird hazard studies or other studies to demonstrate the performance impacts on Logan International Airport. | 2 | 0 | 30 | 180 | Significant bird studies or surveys could cost a lot of money. However, there is extensive information and studies available for the areas in question. | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-01 19:21 | 0 | 4490 |  |  | 302 | 302 | 0 | 0 | 0
15 | 3572 | City of Boston Coastal Storm Risk |  | Roadways as non-project segments | Agency Policy and Process | 7 | There are several elevated roadways that serve as non-project segment barriers. These segments are not designed or constructed to serve that purpose. If USACE formulates around these segments, they could become risk items later in a risk analysis. | 4 | Without risk management, it is likely that the study team will formulate without consideration of the non-project segments and only formulate to tie in closure structures for the underpasses of these segments. |  |  | 12 | Other | OTH | 3630 |  | 6 | Compliance | If it is determined that closure structures are not compliant or too great of a risk, reformulation could be necessary. Reformulation could also increase the study budget due to NEPA impacts and engineering survey needs depending on the recommendation. | 10 | 3 | 0 | 10000 | 50000 | The greatest impact of this risk is reformulation where it is determined that the risk is too great for a simple closure structure tied into an existing non-project segment. The more likely impact is additional study and analysis to ensure tie in is structurally sound and does not exacerbate risk. | 2 | 0 | 0 | 45 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 19:35 | 0 | 4490 |  |  | 302 | 306 | 0 | 0 | 0
16 | 3572 | City of Boston Coastal Storm Risk |  | Life Safety Risk of the Alternatives | Agency Policy and Process | 7 | Life safety risk of the alternatives must be evaluated per the Comprehensive Benefits Memo as part of the Net Benefits Plan. The ability of the alternatives to impacts life safety risk and the team's ability to describe that impact through the results of consequences modeling will be evaluated by OWPR. | 4 | Life Safety analysis in the study phase can be qualitative or semi-quantitative depending on the degree of risk determined by the PDT. Without risk management and involvement of risk cadre, it is very likely that a qualitative assessment would be completed. That assessment would be evaluated by OWPR and determined whether it is compliant and satisfactory or requires additional work. |  |  | 12 | Other | OTH | 4490 |  | 6 | Compliance | If sufficient life safety analysis can't be demonstrated, it may require reformulation. | 10 | 4 | 0 | 50000 | 0 | If it is determined that Life Safety is not sufficient, could require additional analysis, or potentially reformulation. This has Planning, NEPA, and Engineering impacts. | 2 | 0 | 120 | 0 |  | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 19:52 | 0 | 4490 |  |  | 299 | 299 | 0 | 0 | 0
17 | 3572 | City of Boston Coastal Storm Risk |  | Nonstructural Real Estate Costs | Agency Policy and Process | 7 | USACE policy for nonstructural measures is in development and there is no standard estate and no determination whether elevation/floodproofing requires an interest in real estate. | 4 | There will likely be some building adaptation or other nonstructural measures to buildings in the study area. The Enterprise is still developing costs, requirements, and policy. Even when first published, it will likely still have impacts on formulation. |  |  | 13 | Planning - Plan Formulation | PLP | 4490 |  | 6 | Compliance | Policy could increase nonstructural LERRS and change the benefits so significantly that it changes the TSP and require reformulation. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 150 | It is likely that the impact will be somewhere between 0 and 5 months while the team works to understand and incorporate nonstructural LERRS. If nonstructural measures are not used, it is zero impact. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-27 18:02 | 0 | 4490 |  |  | 299 | 306 | 0 | 1 | 0
18 | 3572 | City of Boston Coastal Storm Risk |  | Utilities in the Project Area | Site Conditions | 6 | Failure to identify utiities potentially affected by proposed structural solution may impact schedule, cost, and, design. | 3 | Dense urban environment, mapping utilities, private and public is not always accurate, or done at all. |  |  | 12 | Other | OTH | 3630 |  | 6 | Compliance | Cost impacts of relocating utilities could extend beyond the Chief's discretionary authority and require a Post Authorization Change. | 10 | 3 | 0 | 150000 | 500000 | If utilities are discovered that impact constructability, or implementation, it could increase costs significantly. | 4 | 0 | 180 | 720 | A significant redesign or need to execute surveys/borings could significantly impact schedule. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 11 | 11 | Complete Real Estate Acquisition | 2023-03-01 20:18 | 0 | 4490 |  |  | 302 | 302 | 0 | 0 | 0
19 | 3572 | City of Boston Coastal Storm Risk |  | SLC impacting Geology and Geotech | Site Conditions | 6 | Sea level rise leads to higher groundwater elevations in areas of fill in the City of Boston. The areas of fill are currently susceptible to liquefaction and liquefaction susceptibility is exacerbated by rising sea level. | 3 | Liquefaction of coastal areas of fill leads to lateral spreading and settlement of overlying coastal protection levees and structures. |  |  | 3 | Engineering - Geotechnical | EGT | 3630 |  | 5 | Other |  | 10 | 0 | 0 | 1300000 | 30000000 | The impact of the analysis in PED could change the foundation recommendations of the features authorized in the Feasibility Study. It is likely that the Feasibility Study analysis will paint an accurate picture and only the cost of borings will be necessary in PED to confirm. However, if there is a significant change in conditions, it could significantly increase the cost of the feature's foundation. It could also change the NEPA impacts. | 4 | 0 | 180 | 720 | Schedule impacts could range from 6 months to 2 years in PED depending on how different the conditions are from what is determined in Feasibility. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 10 | 10 | Concept Design Phase (35%) | 2023-03-01 20:33 | 0 | 4490 |  |  | 302 | 302 | 1 | 0 | 0
20 | 3572 | City of Boston Coastal Storm Risk |  | Materially differing site condition | Site Conditions | 6 | Site characterization for potential subsurface construction will not be conducted until PED phase. | 3 | Construction costs could increase significantly depending on unanticipated foundation conditions on shore or off shore. |  |  | 3 | Engineering - Geotechnical | EGT | 3630 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 120 | Depending on the alternatives in the Final Array, the Engineering team may need longer to gather enough data for the risk informed design process. Additionally, the qualitative risk assessment and the CSRA will need to account for the uncertainty of subsurface conditions. If not, the risk of insufficient construction costs may be realized. | 2 | 1 | 1 | Active | 4 | Planning | 5 | 5 | Senior Leaders Briefing | 2023-03-01 20:42 | 0 | 4490 |  |  | 299 | 306 | 1 | 1 | 0
21 | 3572 | City of Boston Coastal Storm Risk |  | Determining a proposed action impacts EFH or ESA Resources | Site Conditions | 6 | Identification of EFH resources at any site late in the feasibility study process would add time to the schedule and increase study cost. | 4 | Without risk management it is very likely that we will identify either waterside construction or actual in-water work that could impact EFH. If it is waterside construction that is identified as part of the Feasibility Level design, post-ADM, it could have significant impacts on completing the NEPA document. |  |  | 16 | Planning - Environmental | PLE | 4490 |  | 6 | Compliance |  | 5 | 2 | 0 | 100000 | 250000 | If baseline surveys or additional investigation is necessary post ADM, it will impact cost and schedule, depending as to where in the study area it is. If it requires mitigation, then it will require planning and modeling on top of the potential surveys. | 2 | 0 | 60 | 180 | If surveys and mitigation planning is necessary it will take much longer. However, the likelihood is, information will be on hand and it is a matter of mitigation planning only. | 2 | 1 | 1 | Active | 4 | Planning | 5 | 5 | Senior Leaders Briefing | 2023-03-01 21:50 | 0 | 4490 |  |  | 302 | 302 | 0 | 0 | 0
22 | 3572 | City of Boston Coastal Storm Risk |  | Recommending features that cut off access to water | Stakeholder, Sponsor or Partners | 9 | Building of structures could reduce access to water's edge and associated recreational opportunities that those areas provide. | 4 | Without risk management and comprehensive benefits planning it is very likely that NED planning will point to hardening shoreline and blocking access to the water as part of risk management. |  |  | 16 | Planning - Environmental | PLE | 4490 |  | 7 | Agency Reputational |  | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 180 | 720 | The worst-case scenario is an unwilling sponsor and a terminated study. The more likely scenario is going out for public review after TSP and getting significant push-back requiring some reformulation. Reformulation will likely require a second release for NEPA. | 4 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-01 21:48 | 0 | 4490 |  |  | 299 | 302 | 0 | 1 | 0
23 | 3572 | City of Boston Coastal Storm Risk |  | HTRW material at any project site | Stakeholder, Sponsor or Partners | 9 | Identification of HTRW during PED investigation will impact Sponsor's ability to turn over LERRDS and could impact schedule and budget | 4 | There are contaminated areas in the study area, specifically in the upper Neponset River and along Chelsea Creek. There are no Superfund sites in the direct area where the study is looking. |  |  | 12 | Other | OTH | 4490 |  | 5 | Other |  | 10 | 4 | 0 | 0 | 0 |  | 0 | 0 | 365 | 1440 | If HTRW is discovered that requires Sponsor remediation, it could take anywhere from 1-year to indefinitely. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 11 | 11 | Complete Real Estate Acquisition | 2023-03-01 21:56 | 0 | 4490 |  |  | 299 | 302 | 0 | 1 | 0
24 | 3572 | City of Boston Coastal Storm Risk |  | City of Boston Leading Public Involvement | Communications | 2 | This is an opportunity. The Sponsor scheduled $250K WIK dedicated to Public Involvement and Outreach. | 5 | The city has 7-years of working on Climate Ready Boston which is the foundation for the Corps Study. They have the relationships, they understand the language barriers and interpretive needs and they know the hot-button issues in each neighborhood. |  |  | 13 | Planning - Plan Formulation | PLP | 4490 |  | 7 | Agency Reputational |  | -10 | 1 | 0 | -250000 | 0 |  | 1 | -180 | -30 | 0 | Their experience will be a significant time savings both in actual outreach, but also in responding to inquiries about who and what we didn't do for outreach. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-01 22:02 | 0 | 4490 |  |  | 299 | 302 | 0 | 0 | 0
25 | 3572 | City of Boston Coastal Storm Risk |  | ERDC Refinement of the CHS Model specific to Boston CSRM | Info and Data Analysis | 1 | Scheduling a Modeling Validation Period will ensure that the study team has the correct FWOP picture and approach to make risk informed planning decisions. | 5 | CHS and G2CRM will provide a policy compliant product; however, does it provide the necessary data to give the study team the necessary information to make the correct decisions? This period will compare two separate coastal modeling approaches and two economic models to ensure that the right strategy and models are selected. The models will use existing data from a complex neighborhood to validate. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 4 | Operations |  | -10 | 1 | -250000 | 150000 | 350000 | Without the refinement period, the study will likely move forward and develop a policy compliant product. However, in PED when more detail and an SQRA/SAR are necessary, it could be determined that the feasibility modeling was incorrect. Based on experience, the effort to correct this is about $500k. This triangulation shows that the study could break even at $350K for the effort or realize up to a $250K savings. | 2 | -270 | -270 | 270 | The opportunity for schedule savings is not linear. If rework in the study later on is required, it would likely take 9 months based on experience. However, the 6-month refinement period to update CHS for the specific study is free time because it was already going to be used by the team to identify inputs to the existing and FWOP condition. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-23 20:00 | 0 | 4490 |  |  | 302 | 299 | 0 | 0 | 0
26 | 3572 | City of Boston Coastal Storm Risk |  | Comprehensive Benefits Strategy and EJ | Agency Policy and Process | 7 | Comp Benefits (Jan '21 Memo) and EJ Outreach/inclusion (Jan '23 IG) are two planning areas of consideration that could impact plan selection. | 4 | The City of Boston is overwhelmingly EJ by definition of the CEJST (1.0). Reasons include linguistic isolation, traffic density and volume, and workforce development related vulnerabilities. Additionally, there are several intangible risks, impacts, and benefits that need to be considered in Boston that fall under the Comprehensive Benefits Strategy. |  |  | 15 | Planning - Economics | PLE | 2495 |  | 7 | Agency Reputational |  | 5 | 2 | 0 | 0 | 200000 | Without risk management, the impacts of incomplete comprehensive benefits analysis could be reformulation. The impacts of incomplete EJ Outreach is a non policy compliant NEPA Document that require rework and a second release. | 2 | 30 | 0 | 180 | If rework is necessary and a second release is necessary, the impact could be as great as 6 months. | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-01 22:26 | 0 | 4490 |  |  | 306 | 306 | 0 | 0 | 0
27 | 3572 | City of Boston Coastal Storm Risk |  | Resource Availability to Support CHS Model Refinement | Resource Availability | 5 | Partnering with ERDC for refining CHS creates a risk due to timing. We are making the request for support at the end of the FY 2nd Quarter when Workload is at its peak for resources. If ERDC can't support the scope and refinement of the CHS model, it could delay the ability to accurately model the existing and future without project conditions. | 4 | It is very likely that ERDC's workload for 3rd and 4th Quarter FY23 is already planned out and full. NAE is requesting to add additional requirements to the ERDC staff to support refinement of CHS. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3630 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 25000 | If ERDC's capacity is already reached and OT is necessary to meet the needs of the District, there could be an additional cost beyond burdened labor rates. | 2 | 0 | 0 | 30 | The Team factored full workload when developing the schedule for the ERDC work. 30 days would likely be as a result of already scheduled leave of absence, or an issue with the model itself. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-29 15:03 | 0 | 4490 |  |  | 306 | 306 | 0 | 0 | 0
28 | 3572 | City of Boston Coastal Storm Risk |  | Economic Model Development | Info and Data Analysis | 1 | G2CRM is the preferred model in conjunction with CHS for economic analysis of Coastal Studies. The risk is under or overestimating damages in the future without project conditions which could impact formulation and alternative selection. G2CRM does not in itself incorporate SLC or wave runup, it is a post processing exercise for year one and year 50 to identify the impacts of SLC. | 3 | Without risk identification and risk management, it is likely that the study would underestimate damages in a FWOP due to SLC and wave runup. |  |  | 15 | Planning - Economics | PLE | 2495 |  | 6 | Compliance | It is a minor problem that would require additional formulation. As long as the issue is identified prior to TSP and release of the draft report, there would only be minor problems associated with reformulation. | 5 | 2 | 0 | 0 | 150000 | On the highest end, the estimate includes reformulation and re-running the economic model. | 2 | 0 | 0 | 90 | This error would potentially impact the alternative identified as the TSP. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-29 14:53 | 0 | 4490 |  |  | 306 | 306 | 0 | 0 | 0
1 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Underseepage - Borings not adequate to capture Piping Risk A | Site Conditions | 6 | Borings not adequate to capture areas where underseepage/piping failure risk areas not captured. Underestimating the size and number of seepage berms and/or relief wells in feasibility that have to be added in final design. This leads to underestimating construction and real estate costs in feasibility. | 2 | If we capture an adequate sampling of soils across the site we are like to get size and number of required relief wells correct. In final design it will be likely that locations shift. |  |  | 3 | Engineering - Geotechnical | EGT | 4051 |  | 6 | Compliance | The number and size of seepage berms will be captured in final design | 5 | 2 | 0 | 150000 | 0 | Large. Number of relief wells is underestimated they are $150,000.00 per relief wells with collector. Seepage berms require real estate and material and are typically 200 feet or so from levee and typically extend multiple stations. Past construction and current trends used to estimate. | 4 | 0 | 180 | 0 | If seepage berms are underestimated they will require that Sponsor aquire additional real estate for construction. Minor. Final design will have more borings and number and size of relief wells and underseepage berms will be captured in final. | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-04-11 03:09 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
2 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Underestimate Levee Settlement | Info and Data Analysis | 1 | Inadequate borings are collected to get good feasibility design estimate of settlement. This leads to need to increase height of levees during final design. | 2 | We plan to capture adequate data to determine magnitude or risk in design |  |  | 3 | Engineering - Geotechnical | EGT | 8248 |  | 5 | Other | It will be captured in final design | 5 | 2 | 0 | 50000 | 0 | The footprint of the levee would change requiring additional real estate. Construction costs would increase due to increase in levee height. We plan to collect enough borings to capture magnitude of settlement and needed levee height. | 4 | 0 | 180 | 0 | Past experience indicates that acquiring real estate can be very time consuming and can lead to delays. Typically it is controlled by sponsor and occurs at their desired schedule. This occurred on St. Joseph levee project where sponsor was not super eager to move project along. | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 10 | 10 | Concept Design Phase (35%) | 2023-04-14 18:23 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
3 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Foundation Soil Strength underestimated | Info and Data Analysis | 1 | Not enough borings to get good estimate of soil strength, leading to understimating levee footprint and underestimating foundation size of any floodwalls that are designed. | 2 | We plan to capture adequate subsurface data to get good estimate of foundation soil strength |  |  | 3 | Engineering - Geotechnical | EGT | 8248 |  | 5 | Other | We will capture foundation soil strenght in more detail in final design. | 5 | 2 | 0 | 75000 | 0 | Additional Real estate would be required for levee and shallow foundations of floodwalls. Would require deeper deep foundations of any pile supported floodwalls. | 4 | 0 | 365 | 0 | Sponsor will need to acquire additional real estate and additional subsurface data collected | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-04-14 18:28 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
4 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Utilize FY23 LOMO System River Model | Info and Data Analysis | 1 | Utilize LOMO System Plan HEC-RAS with minimum updates | 2 | The system plan model will not include level of detail required to fully analyze the scope of the project. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8248 |  | 7 | Agency Reputational | The scope of the full LOMO RAS model is not directly aligned with the spin-off study scopes. | 5 | 2 | 0 | 50000 | 0 | Model additional site detail including bridge structure, adjustments to calibrate to Jefferson City USGS gage, and tributaries. | 2 | 0 | 180 | 0 | Delays H&H analysis until Oct. 2023. Reliance on another project schedule. | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 18:32 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
5 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Accurate modeling of FWOP condition | Site Conditions | 6 | Accurately modeling of FWOP conditions. | 2 | Hitachi indicated desire to move out if they have another flood. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 4051 |  | 5 | Other | Future impacts typically discounted back to present value. | 5 | 2 | 0 | 10000 | 0 | Provide additional analysis/rework FWOP conditions | 2 | 0 | 30 | 0 | Rework/additional analysis time | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 18:37 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
6 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Unwilling sellers | Stakeholder, Sponsor or Partners | 9 | Multiple unwilling sellers have declined offers from the Non Federal Sponsor. | 3 | There are 3 property owners already stated unwilling to sell. Further more there is business property owner unwilling to sell at fair market value. |  |  | 18 | Real Estate | RLE | 8248 |  | 5 | Other |  | 5 | 2 | 0 | 50000 | 0 |  | 4 | 0 | 180 | 0 |  | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 11 | 11 | Complete Real Estate Acquisition | 2023-04-14 18:40 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
7 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Jurisdictional wetlands impacts to alternatives | Site Conditions | 6 | Previous wetland delineations have identified jurisdictional wetlands throughout the study area. The risk of wetland impacts are heightened. | 3 | Previous wetland delineations have identified wetlands throughout the study area. |  |  | 16 | Planning - Environmental | PLE | 5621 |  | 5 | Other | Wetland impacts can be minimized and mitigated. | 5 | 2 | 0 | 10000 | 0 | Fieldwork is necessary to confirm locations of wetlands within the study area. Additional work may be needed to modify alternatives to avoid/minimize wetland impacts. | 2 | 0 | 30 | 0 | Time needed for fieldwork to confirm locations of wetlands within the study area. Additional time may be needed to modify alternatives to avoid/minimize wetland impacts. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-14 18:42 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
8 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | System Plan developing CAR- spin-off time frame may need gre | Agency Policy and Process | 7 | Coordination pursuant to FWCA is required. Ongoing FWCA coordination under the Lower Missouri River System Plan study may be able provide some input from USFWS to the Jefferson City study in the form of planning aid letters and a coordination act report. However, it is unclear if this coordination act report will be available soon enough to be utilized for the Jefferson City study. | 3 | Current estimates for USFWS FWCA input for the Lower Missouri River System Plan study indicate that planning aid letters will be finalized in time for the Jefferson City study to utilize them, but the coordination act report might not be. |  |  | 16 | Planning - Environmental | PLE | 8248 |  | 7 | Agency Reputational | Given that FWCA coordination with USFWS is already underway for the Lower Missouri River System Plan study, additional coordination for the Jefferson City spinoff study is unlikely to be substantial. | 5 | 2 | 0 | 50000 | 0 | USFWS may determine that the planning aid letters produced for the System Plan study, in combination with a planning aid letter specific to the Jefferson City study, may be sufficient. However, a study-specific coordination act report has not yet been ruled out. | 4 | 0 | 30 | 0 | Time may be needed to negotiate FWCA scope. Once negotiated, much of the work performed by USFWS can be done in parallel to USACE's work on the feasibility study. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-14 18:45 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
9 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Federally listed bats roosting in project area | Site Conditions | 6 | An initial site visit confirmed the presence of trees that likely serve as adequate summer roosting by multiple species of federally listed bats. It is possible that these species are present in the study area during the summer roosting season. | 3 | Site visit confirmed the presence of adequate habitat. |  |  | 16 | Planning - Environmental | PLE | 8248 |  | 7 | Agency Reputational | Informal Section 7 consultation is likely to only result in a seasonal tree clearing restriction. | 5 | 2 | 0 | 1000 | 0 | Informal consultation for potential bat impacts is very likely necessary for alternatives that remove trees. If the proposed action does not remove trees, Section 7 consultation would not be necessary for a "no effect" determination. | 2 | 0 | 14 | 0 | If no tree clearing is proposed, then it is likely that no Section 7 consultation for these bat species would be required. However, if tree clearing is proposed then USFWS may need one or two weeks to complete informal consultation for these species. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-14 18:47 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
10 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Floodway Impact | Legal or Regulatory Actions | 10 | Inadequate determination of floodway and floodplain impacts when analyzing alternatives. | 2 | USACE procedures and documentation practices will include analysis of impacts with selection of alternatives. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8248 |  | 5 | Other | Not fully analyzing would deviate from standard USACE practices. | 5 | 2 | 0 | 40000 | 0 | Costs associated with analysis and documentation of upstream and downstream impacts. Expand model to fully encompass affected profile. | 2 | 0 | 30 | 0 | Analysis incorporated into standard USACE practices. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 18:58 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
11 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Survey | Site Conditions | 6 | Accuracy of survey impacts H&H and civil design and risk that additional survey data is needed (field or bathymetric). | 3 | Accuracy/availability of as-built information for features including bridges and existing infrastructure/utilities. |  |  | 9 | Engineering - Civil | ECV | 8248 |  | 5 | Other | Assumptions could be made based on aerial imagery, site visits, available LiDAR. | 5 | 2 | 0 | 20000 | 0 | Cost of survey crew and data processing | 2 | 0 | 30 | 0 | Time necessary for survey and data processing and updating original assumptions | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 19:00 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
12 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Sole beneficiary | Agency Policy and Process | 7 | Policy dictates that a sole beneficiary analysis is required; project risk that 25% of benefits could go to one landowner; sensitive policy area that requires VT coordination per exhibit G6 in Planning Guidance Notebook ER 1105-200. | 3 | small floodplain with two principal landowners |  |  | 15 | Planning - Economics | PLE | 3052 |  | 6 | Compliance | Sole beneficiary would jeopardize federal interest determination. | 10 | 3 | 0 | 10000 | 0 | Time and money doing required vertical team coordination | 2 | 0 | 30 | 0 | Time and money doing required vertical team coordination | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-14 19:01 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
13 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Borrow location changes to somewhere where there aren't exis | Site Conditions | 6 | Determine if soils are satisfactory material, enough quantity to construct project. Would need additional borings in order to complete. | 3 | Past experience |  |  | 3 | Engineering - Geotechnical | EGT | 8248 |  | 5 | Other | The need for more borings would be a minor problem in the planning phase but could become a major problem if not discovered until the PED phase. | 5 | 2 | 0 | 100000 | 0 | Additional borings and analysis | 2 | 0 | 180 | 0 | Time to coordinate borings, rights of entry, and other logistics. | 3 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-28 23:16 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
14 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Borrow location is incorrectly identified or inadequate amou | Site Conditions | 6 | Additional siting and borings would be needed. | 3 | Past experience |  |  | 3 | Engineering - Geotechnical | EGT | 4051 |  | 5 | Other | Past experience, critical piece to move ahead to constructible project. | 10 | 3 | 0 | 100000 | 0 | additional borings and analysis would need to be performed | 4 | 0 | 180 | 0 | Additional days for borings, analysis, right of entry, and other logistics | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-04-28 23:18 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
15 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Stakeholder would like to use a Locally Preferred Plan to co | Stakeholder, Sponsor or Partners | 9 | Use of Locally Preferred Plan could be a higher cost than the smaller Levee footprint. Also, if this is being used as a reason to mitigate the issue of non-willing sellers, | 3 | Discussion with sponsors throughout project, prior experience |  |  | 17 | Project Management | PRM | 4051 |  | 7 | Agency Reputational | There is a high risk that the sponsor will not want to move forward with the plan that isn't the LPP. | 10 | 3 | 0 | 19999 | 0 | Labor costs to work additional waivers, VT discussions, sponsor coordination, evaluation, etc. | 2 | 0 | 90 | 0 | Time in schedule to work additional waivers, VT discussions, sponsor coordination, evaluation, etc. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-28 23:25 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
16 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Jeff City Airport | Site Conditions | 6 | Presence of local airport may limit our ability to propose borrow areas and wetland creation for mitigation near the airport, as these things may attract birds and increase collision risk. | 3 | The airport is located approximately in the middle of study area, so any borrow sites or wetland mitigation sites would have a high likelihood of being located near the airport. |  |  | 16 | Planning - Environmental | PLE | 5621 |  | 2 | Environmental | Early coordination with FAA and airport personnel should USACE to identify constraints for borrow area locations (if needed) and wetland mitigation area (if needed). Corps currently anticipates that constraints can be satisfied by locating these areas at an adequate distance to the airport. | 5 | 2 | 0 | 50000 | 0 | Coordination will be necessary between the Corps, Federal Aviation Administration, and airport personnel to discuss the potential for increased collision hazards near the airport. It is possible that borrow sites and wetland mitigation sites may need to be located further away from the airport, which could potentially raise real estate costs. | 2 | 0 | 30 | 0 | Coordination with FAA and airport personnel will be required to fully document the constraints may be placed on project designs due to the presence of the airport. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-28 23:28 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
17 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Unidentified Utilities | Site Conditions | 6 | Relocation of utilities would be required | 3 | PDT experience with recent levee projects |  |  | 9 | Engineering - Civil | ECV | 4051 |  | 5 | Other | Solutions have been found in past projects | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 90 | 0 | Utility owners are required to perform the relocation, could impact schedule if not found until construction or requires additional design. | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-04-28 23:38 | 0 | 4051 |  |  | 299 | 299 | 0 | 1 | 0
18 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Cumulative effects isn't as extensive as needed | Agency Policy and Process | 7 | The Prior Study at L-142 ruled that the cumulative effects wasn't as extensive as needed. The team will need to ensure that the cumulative effects at analyzed far enough upstream and downstream of the project study, | 2 | Risk is unlikely since the team has learned from previous study. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 4051 |  | 5 | Other | Performing this analysis will be a minor improvement to the previous study and ensure that this study continues to move forward. | -5 | 1 | 0 | 10000 | 0 | H&H will make sure modeled alternatives are modeled far enough upstream and downstream and entered into the system model. | 2 | 0 | 30 | 0 | Additional modeling and reviews. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 18:52 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
19 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | First floor elevations | Site Conditions | 6 | First floor elevation is uncertain and single biggest driver of damages and benefits in riverine FRM. Economist need to be in the field and make survey in order to get first floor elevations | 3 | Viewing elevations from maps is often inaccurate. The purpose of the field survey is to ensure that we have accurate first floor elevations to prevent this from happening. |  |  | 15 | Planning - Economics | PLE | 3052 |  | 5 | Other | Damages and benefits will be incorrect - either high or low and the BC ratio will be incorrect as well. | 10 | 3 | 0 | 6000 | 0 | Additional field visit for two personnel and updating maps as needed. | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 18:58 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 1
20 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Qualified Personnel | Resource Availability | 5 | Many experienced PDT members have left the District or have moved onto more senior level positions. Many resources are also overresourced. | 3 | Many staff lack experience on Planning studies and resources are stretched thin. |  |  | 17 | Project Management | PRM | 4051 |  | 5 | Other | Monthly LIRs with resource providers on all LoMo projects and reporting of any resource concerns and missed milestones. | 5 | 2 | 0 | 20000 | 0 | Bringing PDT members up to speed, mentoring newer PDT members, | 2 | 0 | 60 | 0 | Additional time for training, learning policies, limited staff to add multiple PDT members of same discipline | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-01 19:05 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
21 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Evaluate previously authorized project | Legal or Regulatory Actions | 10 | Per guidance, any previously authorized project must be evaluated during the planning phase as one of the alternatives. | 4 | There is a previously authorized project so it must be evaluated. |  |  | 15 | Planning - Economics | PLE | 3052 |  | 5 | Other | Evaluation should be fairly straight forward. | 5 | 2 | 0 | 12000 | 0 | Labor for additional evaluation | 2 | 0 | 10 | 0 | Additional time for evaluation | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 19:14 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
22 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Stakeholder concerns with Right Bank | Communications | 2 | The study location is on the left bank of the river. However, stakeholders are concerned with Wears Creek and interior flooding on the right bank. Additional communication effort will be needed to emphasize the project area. | 4 | Stakeholder concerns about addressing flooding on Wears Creek have already been brought up on the site visit. |  |  | 12 | Other | OTH | 8248 |  | 5 | Other | Continued communication of the study area | 5 | 2 | 0 | 6000 | 0 | Additional labor and outreach | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 19:19 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 1
23 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Policy Waiver to NED plan selection | Agency Policy and Process | 7 | It is currently not determined if the NED plan will be justified. | 2 |  |  |  | 15 | Planning - Economics | PLE | 3052 |  | 5 | Other | Justification can be difficult. | 10 | 2 | 0 | 10000 | 0 | Additional labor for waiver | 2 | 0 | 60 | 0 | additional time for waiver | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-01 19:24 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
24 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | PL84-99 eligibility of secondary levee | Agency Policy and Process | 7 | The current Capital View levee would become a secondary levee if a new levee is constructed behind it, threatening its eligibility in the PL 84-99 program. | 3 | ER 500-1-1, page 5-6, para 5-3, a secondary levee is ineligible unless it protects human life. |  |  | 3 | Engineering - Geotechnical | EGT | 8248 |  | 5 | Other | Capital View levee getting kicked out of the PL84-99 program in order to build a second levee is a show stopper for the stakeholders. | 10 | 3 | 0 | 20000 | 0 | Additional labor working through policy | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-01 19:37 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 1
25 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Changes in design criteria | Agency Policy and Process | 7 | Ever changing policies and design criteria impacting the study progress after scoping is complete. | 3 | Guidance and policy is always changing. |  |  | 17 | Project Management | PRM | 4051 |  | 5 | Other | Varies depending on the guidance/policy/criteria update and impacts to the study | 5 | 2 | 0 | 50000 | 0 | Varies depending on the guidance/policy/criteria update and impacts to the study | 2 | 0 | 180 | 0 | Varies depending on the guidance/policy/criteria update and impacts to the study | 3 | 1 | 1 | Active | 4 | Planning | 6 | 6 | Chief’s Report/Director’s Report | 2023-05-01 19:42 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
26 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | Cultural surveys | Site Conditions | 6 | Cultural surveys will not be performed during feasibility phase | 3 | Possibility of finding something during cultural surveys during PED |  |  | 14 | Planning - Cultural Resources | PLC | 8248 |  | 5 | Other | Depending on what is found from the survey, impacts on the project alignment could be significant. | 10 | 3 | 0 | 100000 | 0 | Cost of surveys and/or additional redesign if something is found during PED | 4 | 0 | 180 | 0 | Additional days for redesign | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-05-01 19:45 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
27 | 3574 | Lower Missouri River Jefferson City L-142 | 496630 | New Utilities | Site Conditions | 6 | New utilities or changes to existing utilities between Feasibility and PED | 2 | The team is obtaining all known utility surveys in the area. The area is not well developed therefore additional utilities will not be as likely. |  |  | 9 | Engineering - Civil | ECV | 4051 |  | 5 | Other | This is a frequent occurrence during many project design phases | 5 | 2 | 0 | 10000 | 0 | additional redesign | 4 | 0 | 60 | 0 | additional redesign | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 10 | 10 | Concept Design Phase (35%) | 2023-05-01 19:48 | 0 | 4051 |  |  | 299 | 299 | 0 | 0 | 0
1 | 3576 | Owyhee | 479131 | Inadequate water for all year round habitat | Site Conditions | 6 | Irrigation demands and arid conditions limit water availability for aquatic habitat restoration. | 5 |  |  |  | 16 | Planning - Environmental | PLE | 2594 |  | 2 | Environmental | will not be able to maximize benefits | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-02-02 17:33 | 0 | 2919 |  |  | 299 | 299 | 0 | 1 | 1
1 | 3593 | Lower Mississippi River Comprehensive Management Study |  | MR&T may not operate as well as believed | Info and Data Analysis | 1 | Outcome Risk: MR&T may not operate as well as we believe. Consequence: Modeling and design outcomes may be inaccurate. | 3 | 1/4 diversion features are now obsolete due to existing conditions varying from modeled conditions |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 4 | Operations |  | 10 | 3 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 19:50 | 1 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
2 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Budget limitations | Resource Availability | 5 | Risk: Study budget cannot support the full authorized scope of Lower Mississippi River reevaluation. This could lead to Study Risk (Analytical error, study delays, study cost increase, poor planning decision) Consequence: There could be analytical error, poor planning decisions made if a limited budget does not allow sufficient modeling for the area of influence. Asking for additional funds to pursue the full relevant system could add study delays and study cost increase. | 4 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 8 | Agency Strategy |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:23 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
3 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Budget Limitations | Contract Performance | 4 | Risk: Study budget cannot support the full authorized scope of Lower Mississippi River reevaluation, resulting in Outcome Risk (hazard risk and project performance risk). Consequence: If budget limitations reduce the PDT's ability to adequately model or evaluate the comprehensive system, constructed features may not adequately address the problems, may not resolve the intended "adverse outcomes" from existing structures, and may add unexpected risks to system. For example, an insufficient analysis on a system-wide sediment budget may result in future unanticipated instabilities. | 3 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 4 | Operations |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-02-24 20:28 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
4 | 3593 | Lower Mississippi River Comprehensive Management Study |  | External partner and community engagement | Communications | 2 | Risk: Delayed external partner and community engagement could delay momentum. Identifying the full scope of stakeholders will take some time. This could result in Schedule delays. Consequence: Schedule delays could arise if poor or delayed communication results in non consensus or friction points. | 2 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 60 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:31 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
5 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Architecture of Sub-PDTs | Agency Policy and Process | 7 | Due to the size of this mega study, the Governance structure will need multiple sub-PDTs. The PDTs may be divided by Problem area, geographically, or by Mission Area. Different risks may accompany each method for dividing the sub-PDTs. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:39 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
6 | 3593 | Lower Mississippi River Comprehensive Management Study |  | System-wide sub-PDT | Agency Policy and Process | 7 | The Governance structure will likely include a technical sub-PDT body responsible for maintaining consistency on a system-wide scale (ie for H&H modeling, Ecosystem Restoration modeling, lessons learned, legal, etc.) Different risks may accompany the Governance structure depending on what functions the system-wide sub-PDT body includes or excludes. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:43 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
7 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Impact Area Unknown | Info and Data Analysis | 1 | Impact area of study is yet unknown. Impact area is influenced by study area, which has yet to be clearly defined. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:46 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
8 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Study Area Undefined | Info and Data Analysis | 1 | The left and right bounds of the study area have yet to be defined. This contributes some uncertainty to the problems, opportunities, and influence area. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:49 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
9 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Modifying Mississippi River System | Contract Performance | 4 | Despite best modeling efforts, the impacts of modifying the hydraulic and hydrologic functions of the Lower MS River cannot be known until after construction is complete. Discrepancies between the modeled system and actual system could pose operational risks and hazards, and could also add uncertainties to maintenance needs. | 3 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other | Altering the hydraulics and hydrology of the Lower MS River could have major positive or negative consequences, with a variety of negative outcomes including environmental impacts and legal challenges. | 10 | 3 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 20:55 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
10 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Operations modification or override | Contract Performance | 4 | There is currently uncertainty surrounding if the PDT will evaluate modifying operations of the LMR or if current operations will be overridden to overhaul the existing system. Modifying or overriding the current LMR operations each has its own risks. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:06 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
11 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Period of Analysis | Info and Data Analysis | 1 | The period of analysis has not yet been defined. Selecting a 50-year, 100-year, or 200-year period of analysis each have their own risks. Longer periods of analysis may provide for a greater longevity of solutions based on estimated risks. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:10 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
12 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Competiting interests among States or Districts | Stakeholder, Sponsor or Partners | 9 | Competing interests among States and Districts could complicate definition of problems and opportunities, resulting in a delayed study timeline | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:12 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
13 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Exclusion of New Madrid seismic zone from analysis | Info and Data Analysis | 1 | Inclusions and exclusions of problems considered for analysis will impact the level of risk adopted. A future earthquake in the New Madrid seismic zone may be excluded from the problems identified due to study budget limitations; in this case the risk will need to be assessed. The earthquake has a low likelihood within the period of analysis but high consequence. | 1 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:26 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
14 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Coincident event | Info and Data Analysis | 1 | The current system cannot handle a coincident event of storm surge combined with river high water. There are outcome risks including hazard risks and project performance risks if the coincident is not adequately considered. Inclusions and exclusions of problems considered for analysis will impact the level of risk adopted in this study. | 4 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 10 | 4 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:31 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
15 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Reversing adverse outcomes from existing construction | Legal or Regulatory Actions | 10 | Adverse outcomes from previous existing construction may not be able to be overcome with the new proposed projects. This may result in stakeholder disappointment or even exacerbated adverse effects with legal implications. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-02-24 21:35 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
16 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Schedule delay | Agency Policy and Process | 7 | Risk: Risk of 9 months lost time and decreased efforts that can be invested in the study if the study start date is based on the Implementation Guidance, which specified a study start date upon receipt of funds (May 2022 date) instead of at an originally anticipated October 2023 FCSA signing. This could result in study delays, outcome risk, poor planning decision Consequence: Regional system may not be considered thoroughly enough to "reverse" adverse effects from existing efforts, and may cause new adverse effects. Miscalculating risks and consequences across the whole Lower Mississippi River system could result in new adverse impacts. Evidence: Mega studies typically require 5years. Coastal Texas Study, the largest mega study to date, required 120 active PDT members for only one state (Texas) . The study already had a 2-year Master Plan that preceded the study start and still took 5 years. If LMR Comp only has 4 years total due to lost time, the need to serve 6 states across multiple districts with diverging interests, 4 years does not seem realistic to create a meaningful re-working of the entire Lower Mississippi River system. This opportunity to reenvision the river will likely only once in a lifetime, so it is crucial to have sufficient time for meaningful work. Risk Management: To reduce risk, P0 team will coordinate further. P0 Team will seek an Exemption to IG to identify a start date of right now, a start date at a future FCSA date, start date of when P0 PDT timeline ends, or have a Memorandum of Understanding (MOU) | 5 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:38 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
17 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Counsel concerns with IG | Legal or Regulatory Actions | 10 | Counsel has concerns with the way IG is written. Date that 5-year schedule begins. IG says study begins "upon receipt of funds". Sorting out the start date could cause schedule delays. Not delaying the schedule could result in delayed milestones. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:40 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
18 | 3593 | Lower Mississippi River Comprehensive Management Study |  | FCSA inclusion unknown | Agency Policy and Process | 7 | Because the study is 100% Federally-funded, an FCSA may not be executed. The FCSA signing typically starts the 5-year timeline for a study. The IG states that the 5-year schedule begins upon receipt of funds. Too little working time negatively impacts capabilities within study effort. With a once -in-a-generation opportunity to reenvision the LMR, there is a risk of insufficient analysis if enough time is not granted to this effort. Risk Reduction: Prepare Exemption packet. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:47 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
19 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Study area yet to be defined | Stakeholder, Sponsor or Partners | 9 | The left and right limits of the study area have yet to be defined. Changing limits may not be acceptable to existing partners on past studies. Stakeholders are impacted by left and right bounds. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:50 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
20 | 3593 | Lower Mississippi River Comprehensive Management Study |  | New policies may add analysis time | Legal or Regulatory Actions | 10 | New policies, such as new Environmental Justice and Drought policies, may add study analysis time or legal challenges. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-02-24 21:52 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
21 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Project construction impacts on operation | Contract Performance | 4 | It is critical to maintain smooth operation of the Mississippi River during project construction, as the river operation impacts the food supply security of the world. If there are construction delays or operational challenges, there are larger economic and global security risks that may result. | 0 |  |  |  | 13 | Planning - Plan Formulation | PLP | 6361 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-02-24 21:55 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
22 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Duration betw Alternatives Milestone to TSP | Resource Availability | 5 | Evaluation of multiple Alternatives across business lines and across different geographic areas could stretch out the timeline. Modeling needs will not be known until we have a list of Alternatives. | 4 |  |  |  | 13 | Planning - Plan Formulation | PLP | 346 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-17 19:37 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
23 | 3593 | Lower Mississippi River Comprehensive Management Study |  | Duration between ADM and Final Report | Resource Availability | 5 | Design considerations for Feasibility Design Phase could be significant (Mitigation Planning/ Navigation Impacts/ FRM Impact/ Existing Operations Impact). Schedule highly dependent on TSP and scope of Public/Legal/Policy Comments. | 4 |  |  |  | 13 | Planning - Plan Formulation | PLP | 346 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 5 | 5 | Senior Leaders Briefing | 2023-04-17 19:38 | 0 | 6361 |  |  | 299 | 299 | 0 | 0 | 0
2 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | Insufficient sand to support the recommended plan | Info and Data Analysis | 1 | The recommended plan for the GRR, a beach nourishment, lacks sufficient sand for the 50 year project life. | 2 | The project was previously studied as part of a feasibility and authorized in 2010, but some data gaps existed in terms the quantity and quality of the sand identified during the study. This general re-evaluation will address these gaps. |  |  | 3 | Engineering - Geotechnical | EGT | 2339 |  | 1 | Asset Condition | If the risk is realized, then the constructed project will not provide the level of risk reduction for Surf City, NC and require additional resources (funds, investigations, etc.) to identify the necessary sand. | 5 | 2 | 0 | 50000 | 100000 | Cost range is derived from the contract of additional vibracore samples during the re-evaluation, and varies based on the number samples taken. | 2 | 0 | 45 | 90 | Schedule is derived from the contract of additional vibracore samples during the re-evaluation, and varies based on the number samples taken. | 2 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-05-22 19:02 | 0 | 584 |  |  | 302 | 302 | 0 | 0 | 0
3 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | Backbay flooding | Info and Data Analysis | 1 | Flooding in backbay of Surf City, NC will increase over the life of project. | 2 | The 2010 study of the project did not identify significant backbay flooding issues at Surf City. |  |  | 9 | Engineering - Civil | ECV | 584 |  | 1 | Asset Condition | If backbay flooding becomes an issue, then such could effect the risk reduction for the project and Surf City. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-03-24 19:31 | 0 | 584 |  |  | 299 | 299 | 0 | 1 | 1
4 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | Sea level rise | Info and Data Analysis | 1 | The impacts of sea level rise to the project are greater than anticipated. | 4 | Coastal Hazard System tool |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 584 |  | 1 | Asset Condition | If the risk is realized, then the project will need more sand and require changes to the nourishment interval to maintain a level of risk reduction on the project. | 5 | 2 | 50000 | 100000 | 200000 | Professional judgement. | 4 | 60 | 180 | 365 | Professional judgement. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-05-10 16:58 | 0 | 584 |  |  | 302 | 302 | 0 | 0 | 0
5 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | Anytime Dredging | Legal or Regulatory Actions | 10 | Cost and schedule risk if anytime dredging is not allowed. | 2 | Professional Judgement |  |  | 10 | Office of Counsel | LGL | 584 |  | 6 | Compliance | 'Professional judgement. | 10 | 2 | 500000 | 0 | 1000000 | 'Cost estimate for mobilization and demobilization. | 4 | 365 | 0 | 730 | 'Schedule estimate based on adherence to environmental windows. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-05-10 16:52 | 0 | 138 |  |  | 306 | 306 | 0 | 0 | 0
6 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | Construction contractor | Contract Acquisition | 3 | Identifying Nearby Contractor with adequate dredge hoppers to construct the project. | 1 | Professional judgement. |  |  | 1 | Contracting | CNT | 9013 |  | 8 | Agency Strategy | The risk would delay the schedule for construction of the project. | 5 | 2 | 0 | 0 | 20000 | Internal government cost estimate | 2 | 0 | 0 | 20 | Internal government cost estimate | 2 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-05-10 16:55 | 0 | 584 |  |  | 306 | 306 | 0 | 0 | 0
7 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | Encountering rock and/or cemented sands within borrow | Site Conditions | 6 | Rock and/or cemented sand could be encountered at anytime during construction (i.e. Initial and subsequent nourishment intervals), creating a reduction in production times and an increase cost of disposal. | 3 | Nearby CSRM projects and professional judgement. |  |  | 3 | Engineering - Geotechnical | EGT | 2339 |  | 5 | Other |  | 5 | 0 | 0 | 1000000 | 0 | Professional judge. still working on estimate. | 2 | 14 | 21 | 45 | Knowledge of rock boxes and their use. | 2 | 1 | 1 | Active | 6 | Construction | 20 | 20 | Construction Completion | 2023-05-10 17:01 | 0 | 584 |  |  | 299 | 302 | 1 | 0 | 0
8 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | Ownership and maintenance of lands related to the project | Legal or Regulatory Actions | 10 | The legal authority for Surf City to acquire and maintain the ownership of lands outside of their political boundaries. | 1 | Written authority and regulations. |  |  | 18 | Real Estate | RLE | 520 |  | 4 | Operations | Professional judgement. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 15 | Professional judgement. | 2 | 7 | 7 | Inactive - Decision Made | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-04-17 18:51 | 0 | 584 |  |  | 306 | 306 | 0 | 1 | 0
9 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | Likelihood of Encountering Unsuitable Material | Info and Data Analysis | 1 | Although subsurface investigations have yielded useful information and the District is actively pursuing vibracore contracts, given the characteristics of the underlying geology, it is likely that unsuitable material may be encountered at anytime in any borrow area. This could occur as fines, rock, or cemented sand. | 4 | Widespread variability of underlying geology and predominantly rocky offshore conditions, as well as log descriptions from various supporting investigations showing a wide range of sediment types and horizons. |  |  | 3 | Engineering - Geotechnical | EGT | 2339 |  | 5 | Other |  | 5 | 0 | 0 | 200000 | 500000 | Cost could be zero in the early phases of the project and increase in the outyears as sand volumes are depleted. Cost is based on the procurement of a vibracore contract or an increased hauling distance. | 2 | 0 | 30 | 90 | Estimate based on cost estimate comparisons and professional judgement. | 2 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-05-09 14:06 | 0 | 9053 |  |  | 302 | 302 | 1 | 0 | 0
10 | 3611 | Surf City Beach Construction PL 116-20 | 487223 | ERASE THIS RISK - test | Contract Performance | 4 | test | 2 |  |  |  | 16 | Planning - Environmental | PLE | 138 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 7 | Operations and Maintenance | 23 | 23 | Q2 | 2023-05-22 19:00 | 0 | 138 |  |  | 299 | 299 | 1 | 1 | 1
2 | 3631 | RumaylanDetention Facility | 509717 | Bond Waiver | Contract Acquisition | 3 | Bonds provide a guarantee that a contractor will fulfill all of their obligations under a construction contract. Without bonds, and if KTR defaults, there is no surety to take over contract to completion; there is no financial compensation to the owner in case a contractor fails to complete the contract. | 5 | There are no banks in Syria. There is no way to bond. |  |  | 1 | Contracting | CNT | 8912 |  | 5 | Other |  | 10 | 4 | 0 | 34717281 | 0 |  | 4 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 24 |  | 41 | 41 | Contract Required Complete | 2023-02-26 22:55 | 0 | 8912 |  |  | 299 | 299 | 0 | 0 | 1
1 | 3652 | DE Inland Bay/Bay Coast | 402963 | Acquisition | Stakeholder, Sponsor or Partners | 9 | The acquisition of houses that are not suitable to be raised may need to be acquired. | 2 |  |  |  | 18 | Real Estate | RLE | 863 |  | 5 | Other | The unexpected acquisition of houses could be a major impact to performance given the additional time, effort, and cost added if acquisition is needed. | 10 | 3 | 0 | 0 | 1000000 | Estimated cost at $1 million until we have additional real estate information. | 4 | 0 | 365 | 1095 | 3 years assumed for the longest time to acquire a home. Will be updated if more info is obtained. | 3 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-04-25 12:38 | 0 | 8780 |  |  | 306 | 302 | 0 | 0 | 0
2 | 3652 | DE Inland Bay/Bay Coast | 402963 | Study Cost ($2 Million) | Agency Policy and Process | 7 | The total study budget is $2 million with no ability for non-federal sponsor contributions. With a smaller budget, the PDT will need to formulate on lessons learned and will potentially not be able to formulate to the highest standard. | 5 | This will significantly impact the project since the FCSA is signed and based on communication with the non-federal sponsor. |  |  | 12 | Other | OTH | 3290 |  | 8 | Agency Strategy | This risk constrains the geographic scope and the examination of alternatives. It also constrains the level of detail able to be explored and there are no opportunities for adding additional members of the PDT for expertise. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-04-25 12:50 | 0 | 8780 |  |  | 299 | 299 | 0 | 1 | 0
3 | 3652 | DE Inland Bay/Bay Coast | 402963 | CBRA Compliance | Agency Policy and Process | 7 | USFWS may not accept several alternatives, and there are multiple CBRA units in our study area. | 4 | It is very likely that the USFWS will not allow certain alternatives to move forward. |  |  | 16 | Planning - Environmental | PLE | 863 |  | 5 | Other | The PDT will likely make decisions to avoid CBRA Areas which may impact the performance of the alternatives. | 5 | 2 | 0 | 5000 | 25000 | If we try to circumvent the compliance, the PDT could spend additional money with no positive result. | 2 | 0 | 25 | 150 | If we try to circumvent the compliance, the PDT could spend additional time with no positive result. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-12 14:43 | 0 | 8780 |  |  | 302 | 302 | 0 | 0 | 0
4 | 3652 | DE Inland Bay/Bay Coast | 402963 | Real Estate Requirements | Stakeholder, Sponsor or Partners | 9 | Public participation and acceptance of required standard estates. The number of stakeholders and property owners in the study area is significant. Some private lands may be required for the project. Any real estate that cannot be acquired without court processes may negatively impact the acquisition schedule. | 3 |  |  |  | 18 | Real Estate | RLE | 863 |  | 5 | Other |  | 5 | 2 | 0 | 10000 | 150000 |  | 4 | 0 | 160 | 720 |  | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 11 | 11 | Complete Real Estate Acquisition | 2023-05-12 14:48 | 0 | 863 |  |  | 302 | 302 | 0 | 0 | 0
5 | 3652 | DE Inland Bay/Bay Coast | 402963 | Inlet Surge Barriers | Info and Data Analysis | 1 | May need additional/high fidelity modeling for design of inlet alternatives | 2 | Inlet barrier alternatives have significant constraints on feasibility, including CBRA, estimated cost derived from similar studies, real estate risk, and environmental impact. H&H is one risk component of overall high risk alternative. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 863 |  | 5 | Other |  | 5 | 2 | 50000 | 75000 | 500000 | If Inlet barrier alternatives are moved forward past the AMM, based on modeling that would be needed, the internal cost could be up to 500000 | 3 | 0 | 365 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-12 15:00 | 0 | 863 |  |  | 302 | 299 | 0 | 0 | 0
6 | 3652 | DE Inland Bay/Bay Coast | 402963 | Study Area | Stakeholder, Sponsor or Partners | 9 | Study authorization allows for study area of entire coast of Delaware. NFS focus for coastal storm risk is on Inland Bays. NFS has related that multiple studies are ongoing in Wilmington Area for flood risk management. NAP has recently completed the Dredged Material Utilization study, which has been authorized in WRDA 2020 and amended in WRDA 2022. This would provide coastal storm risk reduction for communities on Delaware Bay Coast. Inland Bays area has had very little attention for back-bay flood risk reduction. Study risk is including additional areas beyond the Inland Bays post-AMM. | 4 | Early planning decision made in concert with NFS and relayed and agreed to by NFS leadership. |  |  | 13 | Planning - Plan Formulation | PLP | 863 |  | 5 | Other | If larger study area is carried through, project could run out of funding and be terminated. | 10 | 3 | 75000 | 0 | 200000 | Additional EN modeling and economic modeling and data collection. If inclusion of DE Bay coast and residual risk of DMU communities, cost would be lower. If inclusion of Wilmington Area, cost would be high. | 4 | 90 | 0 | 365 | If inclusion of DE Bay coast and residual risk of DMU communities, time would be lower. If inclusion of Wilmington Area, time would be high. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-05-12 15:03 | 0 | 863 |  |  | 306 | 306 | 0 | 0 | 0
7 | 3652 | DE Inland Bay/Bay Coast | 402963 | PDT Workload and Turnover | Resource Availability | 5 | PDT workload on other projects and turnover of key PDT members over the course of the study could impact schedule and budget. | 4 | PDT members have already begun to turnover during first study phase. |  |  | 17 | Project Management | PRM | 3290 |  | 5 | Other | Impact to schedule and budget. | 5 | 2 | 50000 | 100000 | 150000 |  | 3 | 90 | 180 | 360 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-04-28 14:20 | 0 | 863 |  |  | 302 | 302 | 0 | 0 | 0
8 | 3652 | DE Inland Bay/Bay Coast | 402963 | Interior Drainage | Info and Data Analysis | 1 | Uncertainty of impacts of alternatives to interior drainage systems, and adjustments that may be necessary to incorporate. | 2 |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 863 |  | 5 | Other |  | 5 | 2 | 0 | 15000 | 50000 |  | 4 | 0 | 25 | 250 |  | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 10 | 10 | Concept Design Phase (35%) | 2023-05-12 15:05 | 0 | 863 |  |  | 302 | 302 | 0 | 0 | 0
9 | 3652 | DE Inland Bay/Bay Coast | 402963 | Identification of economic study area | Info and Data Analysis | 1 | Structures not included in structure inventory could incur damage. | 2 | Using combined NSI and sponsor data for study area. May miss structures incurring damage outside of study area. |  |  | 15 | Planning - Economics | PLE | 863 |  | 5 | Other |  | 5 | 2 | 0 | 5000 | 50000 |  | 2 | 0 | 5 | 25 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-12 15:18 | 0 | 863 |  |  | 302 | 302 | 0 | 0 | 0
10 | 3652 | DE Inland Bay/Bay Coast | 402963 | Structure Characteristics | Info and Data Analysis | 1 | NSI and local structure data may not accurately characterize the structure characteristics such as type of structure, first floor elevation, etc. Many structures have been elevated in the study area and this condition may not be captured in data. | 3 |  |  |  | 15 | Planning - Economics | PLE | 863 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-28 14:39 | 0 | 863 |  |  | 299 | 299 | 0 | 0 | 0
11 | 3652 | DE Inland Bay/Bay Coast | 402963 | Sea Level Change Impacts to the Floodplain | Info and Data Analysis | 1 | There is a significant difference in preliminary curves at the low/intermediate/ and High SLC scenarios. It is possible that the formulation will change depending on the accuracy of the FWOP floodplain at both the 50-year and 100-year horizons. 50-year for quantitative analysis and 100-year for qualitative analysis. | 3 | Given the current projections of sea level rise, this risk is likely to impact the plans and implementation of design over time. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 863 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-12 15:19 | 0 | 8780 |  |  | 299 | 299 | 0 | 1 | 1
12 | 3652 | DE Inland Bay/Bay Coast | 402963 | Utilities in the Project Area | Site Conditions | 6 | Failure to identify utilities affected by proposed structural solutions may impact schedule, cost, and design. | 1 |  |  |  | 12 | Other | OTH | 3290 |  | 6 | Compliance |  | 5 | 2 | 0 | 100000 | 500000 | Dense urban environment, mapping utilities, private and public is not always accurate, or done at all. If utilities are discovered that impact constructability, or implementation, it could increase costs significantly. | 4 | 0 | 180 | 500 |  | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 9 | 9 | Project Definition Phase (15%) | 2023-05-01 12:23 | 0 | 8780 |  |  | 302 | 302 | 0 | 0 | 0
13 | 3652 | DE Inland Bay/Bay Coast | 402963 | Materially different site conditions | Site Conditions | 6 | Site characterization for potential subsurface construction will not be conducted until the PED Phase. Construction costs could increase significantly depending on subsurface conditions and unanticipated foundation conditions on or off-shore. | 2 |  |  |  | 3 | Engineering - Geotechnical | EGT | 3290 |  | 5 | Other |  | 5 | 2 | 0 | 50000 | 500000 |  | 4 | 0 | 50 | 299 | Depending on the alternatives in the Final Array, the Engineering team may need longer to gather enough data for the risk informed design process. Additionally, the qualitative risk assessment and the CSRA will need to account for the uncertainty of subsurface conditions. If not, the risk of insufficient construction costs may be realized. | 3 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-05-01 12:29 | 0 | 8780 |  |  | 302 | 302 | 0 | 0 | 0
14 | 3652 | DE Inland Bay/Bay Coast | 402963 | Recommending Features that Cut off access to water | Stakeholder, Sponsor or Partners | 9 | Building of structures could reduce access to the water's edge or to existing docks that would impact the recreational use of the areas. Without risk management and comprehensive benefits planning it is likely that NED planning will point to hardening shoreline and blocking access to the water as part of risk management. | 2 |  |  |  | 20 | Public Affairs | COM | 3290 |  | 7 | Agency Reputational | The worst-case scenario is an unwilling sponsor and a terminated study. The more likely scenario is going out for public review after TSP and getting significant push-back requiring some reformulation. Reformulation will likely require a second release for NEPA. | 5 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-01 12:34 | 0 | 8780 |  |  | 299 | 299 | 0 | 1 | 1
15 | 3652 | DE Inland Bay/Bay Coast | 402963 | Sea Level Change Model Assumption | Info and Data Analysis | 1 | Actual sea level elevation change could be greater than existing forecast models' range and resulting plans may be under-engineered. | 2 | Due to increased recent storms nationwide and given the range of possible sea level rise scenarios, there remains a chance that true mean sea level rise will fall outside of model expectations. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 863 |  | 8 | Agency Strategy |  | 5 | 2 | 0 | 5000 | 100000 | Cost varies depending on the assumed risk incorporated in the construction phase, but cost will likely be unrealized until additional data increases accuracy of current models. If sea level rise is higher in real time than what was modeled, then the rate and volume of sand erosion could be much higher. That would necessitate more frequent and or larger volumes of sand replenishment. If sea level rise is lower than what was modeled, then we may be over engineering a solution and less material/frequent nourishment would be needed. | 2 | 0 | 0 | 250 | If the team is directed to conduct additional modeling under a different sea level change scenario it would lengthen the impact analysis and evaluation phase, this could postpone dates to reach TSP. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-12 15:07 | 0 | 8780 |  |  | 302 | 306 | 0 | 0 | 0
17 | 3652 | DE Inland Bay/Bay Coast | 402963 | Availability of Compatible Sediment Material | Site Conditions | 6 | Beach Nourishment and NNBF options such as marsh or wetland restoration may be ineffective or unjustifiable due to cost if not enough compatible sediment material is available. A realization of the risk might be that finding additional or alternative material for use would require additional time and would likely be much more costly than using materials found close to the site. | 4 | The risk is currently very likely since there are not any beneficial reuse areas identified that are not already in use for Beach Restoration. |  |  | 3 | Engineering - Geotechnical | EGT | 3290 |  | 5 | Other |  | 5 | 2 | 0 | 100000 | 200000 |  | 4 | 0 | 365 | 0 |  | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 8 | 8 | Design Start | 2023-05-01 18:11 | 0 | 8780 |  |  | 302 | 299 | 0 | 0 | 0
19 | 3652 | DE Inland Bay/Bay Coast | 402963 | HTRW On the Project Sites | Legal or Regulatory Actions | 10 | There are two Superfund sites within the study area. Both are located in Millsboro, one at 199 Mitchell Street and one at 225 W Dupont Boulevard. One of the alternative includes small barriers on tributaries that are adjacent to the Superfund Site located at 199 Mitchell Street. | 2 | Given current conditions, the Alternative to put small barriers on a few tributaries in Millsboro may be directly next to or impacted by a Superfund site. |  |  | 16 | Planning - Environmental | PLE | 863 |  | 6 | Compliance | If we were to determine that the barrier for Alternative 3 at the tributary needs to cross the Superfund site at Mitchell avenue, it would impact the performance of the protection given and might cause more issues in that area. | 5 | 2 | 0 | 2000 | 20000 |  | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-12 15:23 | 0 | 8780 |  |  | 302 | 299 | 0 | 0 | 1
20 | 3652 | DE Inland Bay/Bay Coast | 402963 | EA Timeline | Agency Policy and Process | 7 | Risk that if decision to draft an EA is made early on in the process, the EA timeline of 1 year will go into effect but EA would not be able to be completed within 1 year, following the feasibility study timeline. A waiver for time requirements on an EA would need to be requested. | 3 | Likely if decision is made to draft EA. |  |  | 16 | Planning - Environmental | PLE | 5627 |  | 5 | Other |  | 5 | 0 | 1000 | 0 | 5000 | Funds would be needed to prepare and coordinate EA timeline waiver submittal and processing. | 2 | 10 | 0 | 30 | Time needed to prepare and submit EA timeline waiver. | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-05-02 15:23 | 0 | 5627 |  |  | 306 | 306 | 1 | 0 | 0
21 | 3652 | DE Inland Bay/Bay Coast | 402963 | Preparation of an EIS | Resource Availability | 5 | If significant impacts are anticipated and an EIS is to be prepared, additional funds and time would be needed for the preparation (when compared to an EA). Additional funding needed for an EIS may impact overall limited feasibility study budget of $2 million. | 2 | May occur if measures anticipated to have significant impacts move forward. |  |  | 16 | Planning - Environmental | PLE | 5627 |  | 5 | Other |  | 5 | 0 | 100000 | 150000 | 200000 |  | 2 | 365 | 0 | 730 | Time limit of two years to complete an EIS per new NEPA rules. | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-05-02 15:39 | 0 | 5627 |  |  | 302 | 306 | 1 | 0 | 0
1 | 3653 | 2024 Dredging Project, Military Ocean Terminal Concord (MOTCO), CA. |  | Overlapping projects with the boat ramp, dredging and levee | Site Conditions | 6 | Unexpected additional environmental compliance coordination and review required for the Boat Ramp project at MOTCO. | 2 |  |  |  | 17 | Project Management | PRM | 4571 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 9 | Design | 32 | 32 | Receive Concept (30%) | 2023-03-14 20:11 | 0 | 4571 |  |  | 299 | 299 | 0 | 0 | 0
1 | 3654 | Keystone Dam – Wedge (495646) |  | Review Risk (level of review) | Agency Policy and Process | 7 | Our current schedule assumes that we would not have any significant changes to the analysis or TSP that would require us to go back through ATR or QCC. If we did need to revisit the ATR or QCC, the October 2023 DSOG would not be feasible. The current path is that we are only refining the previously identified TSP. Anything outside of this would trigger re-formulation and would keep us from presenting our TSP to the DSOG in October. | 2 |  |  |  | 13 | Planning - Plan Formulation | PLP | 28 |  | 5 | Other |  | 5 | 0 | 0 | 200000 | 0 | Accounts reformulation, DQC, ATR and QCC. | 4 | 0 | 365 | 0 | It would be a one year total schedule slip. It would take 6 months to get back to DSOG with a TSP, but we would miss the 1 June approval date deadline. | 4 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-13 19:51 | 0 | 28 |  |  | 299 | 299 | 1 | 0 | 0
2 | 3654 | Keystone Dam – Wedge (495646) |  | NEPA Related Schedule Risks | Agency Policy and Process | 7 | We currently assume the NEPA document will not need significant refinement after DSOG and will be ready for public review within 2-3 weeks after DSOG. If the DSOG significantly changes the TSP and substantial re-coordination or revisions to the NEPA document are required we will need to add time into the schedule. Depending on the magnitude of changes, this may affect our ability to secure a 1 June approval for the DSMR. | 1 |  |  |  | 16 | Planning - Environmental | PLE | 28 |  | 6 | Compliance | Could be major depending on the magnitude of changes. | 5 | 2 | 0 | 25000 | 0 |  | 4 | 0 | 60 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-13 19:58 | 0 | 28 |  |  | 299 | 299 | 0 | 0 | 0
3 | 3654 | Keystone Dam – Wedge (495646) |  | Contract for Risk Assessment Work | Contract Acquisition | 3 | It was recommended to the PDT that they contract with an external structural expert to support the team in the reevaluation of two structural failure modes. The onboarding process for this external resource has been lengthy and has delayed the ECRA update. This affects not only the ECRA but the re-evaluation of RMPs and puts the schedule at risk. | 5 | The schedule has already been impacted. It is now a matter of the magnitude of that impact. |  |  | 17 | Project Management | PRM | 28 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 90 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-13 20:07 | 0 | 28 |  |  | 299 | 299 | 1 | 1 | 0
4 | 3654 | Keystone Dam – Wedge (495646) |  | Sufficiency of the Refined ECRA | Agency Policy and Process | 7 | We are assuming that the updated ECRA will be accepted by the July DSOG. If it is not, there will be budget and schedule impacts to account for further refinement. | 1 |  |  |  | 17 | Project Management | PRM | 28 |  | 5 | Other |  | 5 | 0 | 0 | 75000 | 0 |  | 4 | 0 | 90 | 0 |  | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-13 20:31 | 0 | 28 |  |  | 299 | 299 | 1 | 0 | 0
5 | 3654 | Keystone Dam – Wedge (495646) |  | DSOG Refinements to TSP | Agency Policy and Process | 7 | There is a risk that DSOG may or may not endorse all of the measures in the TSP. Refinements to the TSP could be costly and time consuming, putting the schedule at risk. | 1 |  |  |  | 13 | Planning - Plan Formulation | PLP | 28 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 | Cost impact is unknown. | 1 | 0 | 0 | 0 | Schedule impact is unknown. | 1 | 1 | 1 | Active | 4 | Planning | 4 | 4 | Agency Decision | 2023-03-13 20:31 | 0 | 28 |  |  | 299 | 299 | 1 | 0 | 0
6 | 3654 | Keystone Dam – Wedge (495646) |  | Reevaluation of Hydrology Based on Policy Changes | Agency Policy and Process | 7 | The way the agency evaluates risk associated with the Probable Maximum Flood changed during development of the DSMS. The PDT will perform an evaluation using this new methodology. The results have the potential to impact the identified TSP, potentially requiring a larger dam raise than what has been previously evaluated. | 4 | The degree of change is currently unknown. The PDT will re-evaluate the new proposed top of dam and evaluate risk under the new PMF condition. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 28 |  | 5 | Other |  | 5 | 0 | 0 | 50000 | 0 |  | 4 | 0 | 30 | 0 | This assumes this analysis does not impact plan formulation. (ie. the dam cannot be raised high enough) | 2 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-13 20:27 | 0 | 28 |  |  | 299 | 299 | 1 | 0 | 0
1 | 3671 | New Project |  | Big Scary Risk | Site Conditions | 6 | Sink Holes everywhere | 5 | Geotechnic surveys |  |  | 3 | Engineering - Geotechnical | EGT | 6867 |  | 2 | Environmental | doesn't work to keep out carp | 10 | 4 | 10000 | 10000 | 500000 | So much evidence | 2 | 1 | 100 | 365 |  | 4 | 1 | 1 | Active | 6 | Construction | 21 | 21 | Project Acceptance | 2023-05-18 20:26 | 0 | 6867 |  |  | 299 | 306 | 0 | 0 | 0
2 | 3671 | New Project |  | Other RIsk | Contract Performance | 4 |  | 2 |  |  |  | 9 | Engineering - Civil | ECV | 6847 |  | 5 | Other |  | 5 | 0 | 0 | 50000 | 0 |  | 2 | 0 | 150 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-20 19:59 | 0 | 6867 |  |  | 299 | 299 | 1 | 0 | 0
6 | 3677 | Capstone |  | Hurricane Model Uncertainty | Info and Data Analysis | 1 | Understanding of hurricane frequency and magnitude, model selected, influence from sea level rise, impacts from climate change, are a risk to the project. Impacts to the plan selection and design. | 3 | There is uncertainty inherent in any model. We are certain about the range of uncertainty of the selected hurricane model based on the model documentation. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7329 |  | 8 | Agency Strategy |  | 5 | 2 | 0 | 0 | 80000 | If existing model is acceptable, no additional cost to project. If new model is needed, development of new model is anticipated to cost $80,000. | 2 | 30 | 60 | 363 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:35 | 0 | 7329 |  |  | 306 | 302 | 0 | 0 | 0
9 | 3677 | Capstone |  | Historic properties in a historic district | Site Conditions | 6 | There are X number of historic districts, x number of historic properties. We need to be able to identify the properties that will be effected by flooding or are below X elevation. The source/database of identification of the properties may not be complete. | 5 | Not all historic properties are within the database. We do know that there are a significant number of historic properties but where they are located within the flooding area that was identified is unknown. |  |  | 14 | Planning - Cultural Resources | PLC | 8953 |  | 6 | Compliance | SHPO coordination can effect the project outcome and identification of TSP | 10 | 4 | 0 | 500000 | 0 | You would need additional surveys to identify areas to minimize data gaps. | 4 | 0 | 180 | 0 | Gathering additional data does take time and could impact construction going forward. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 14:21 | 0 | 8952 |  |  | 299 | 299 | 0 | 0 | 0
13 | 3677 | Capstone |  | 200-year level of protection requested by non-fed sponsor | Info and Data Analysis | 1 | The Non-Federal Sponsor's objective is to achieve a 200-year interval level of protection for urban and urbanizing areas. The uncertainty is regarding the level of accuracy with 200-year modeling and projections, and how to analyze that, how it effects economics, and therefore the overall future justification of the project and proposed TSP. | 4 | Team expertise and prior project experience |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 8934 |  | 8 | Agency Strategy | Will influence alternatives development and TSP outcome | 10 | 4 | 50000 | 100000 | 250000 | Assumptions based on team expertise, assumptions of study area, and prior experience | 3 | 0 | 60 | 0 |  | 4 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:27 | 0 | 8934 |  |  | 302 | 299 | 0 | 0 | 0
14 | 3677 | Capstone |  | Model Accuracy | Info and Data Analysis | 1 | Model uses H&H data that is older than 10 years | 1 | Water surface elevations have not significantly changed in the last few years. The water surface elevation data should still be applicable. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 5627 |  | 5 | Other |  | -5 | 0 | 0 | 0 | 100000 | On the low end if the model needs minimal updates, the cost would be minimal. If model needs to be updated the costs might be up to 100K. | 2 | 30 | 0 | 90 | If updates are needed to model, 3 months are needed. | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:23 | 0 | 5627 |  |  | 306 | 306 | 1 | 0 | 0
15 | 3677 | Capstone |  | Effects of Sea Level Rise on Project Design | Site Conditions | 6 | Sea level rise may exceed water levels in everglades that we are basing designs on | 4 | We may choose a sea level curve model result to design to that differs from future actual sea level rise conditions/elevations |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7650 |  | 2 | Environmental | if sea level rise projections do not accurately capture the future sea level rise and storm surge risk, the project may not perform as projected | 10 | 4 | 500000 | 800000 | 1500000 | Cost comparison of measures needed based on low, med, high sea level rise | 4 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:24 | 0 | 7650 |  |  | 302 | 299 | 0 | 0 | 1
16 | 3677 | Capstone |  | Unknown Historical Shipwrecks | Site Conditions | 6 | There is a potential for cultural resources to impact further widening or deepening of the channel, specifically a historical (pirate) shipwreck in the area of the dredging. | 1 | The channel has been established for a substantial amount of time, so most cultural resources have probably been discovered prior to any dredging the may occur. Risk will increase if the channel is widened or a new channel is established. |  |  | 14 | Planning - Cultural Resources | PLC | 7308 |  | 2 | Environmental | The assumption is the discovered cultural resources would be a relatively small archaeological site, which would not substantial impact the overall project goal. | 5 | 2 | 0 | 1000000 | 0 | If cultural resources are discovered, there would have to be an excavation and recovery of the resources. | 4 | 0 | 730 | 0 | If cultural resources are discovered, the schedule would be pushed back by 2 years due to excavation and hurricane season. | 4 | 1 | 1 | Active | 5 | Pre-Construction Engineering and Design (PED) | 7 | 7 | Survey and Geotech Characterization | 2023-03-14 14:26 | 0 | 7308 |  |  | 299 | 299 | 0 | 0 | 0
18 | 3677 | Capstone |  | Hurricane Model Uncertainty | Info and Data Analysis | 1 | Hurricane Frequency, Hurricane intensity, Model Selection, Hurricane influence from sea level rise, Hurricane variability from the gulf stream -Knowing the full extent of the hazard will determine our selection | 3 | Historic model validation, some spaghetti model lines are right sometimes and other times they are wrong |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7707 |  | 8 | Agency Strategy | Model Section will impact all csrm studies and decision making | 10 | 3 | 80000 | 0 | 3000000 | If existing model is successful, we assume the run costs would be $80k. If model is unsuccessful, estimated cost of new model is $3M | 4 | 30 | 120 | 363 | Lot of unknowns | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 14:30 | 0 | 7893 |  |  | 306 | 302 | 0 | 0 | 0
19 | 3677 | Capstone |  | Hurricane model uncertainty | Info and Data Analysis | 1 | Uncertainty involved with forecasting the timing, frequency, and intensity of hurricane events. Secondary info uncertainty is related to hurricane related storm surge and sea level rise with regard to changing conditions in the future under climate change. The risk is directly associated with designing to a specific level of frequency and intensity, but with future conditions changing under climate change, the design may turn out being inadequate with inaccurate predictions. | 3 | Model accuracy is never 100%. Even the most current models are subject to changing environmental conditions. Model outputs should provide uncertainty likelihood in their results. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 7329 |  | 3 | Human Health and Safety | Model selection has the potential to impact the project greatly. | 10 | 3 | 80000 | 0 | 3000000 | Model cost $80,000 to runs as is, if the need arises to create a new model with future climate changes incorporated the price could inflate to 3 mil. | 4 | 30 | 120 | 363 | Model run as is could be within 30-120 days. If new model needs created it could push schedule significantly. | 4 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-14 14:30 | 0 | 7707 |  |  | 306 | 302 | 0 | 0 | 0
20 | 3677 | Capstone |  | Potential to negatively impact water rights in project area | Stakeholder, Sponsor or Partners | 9 | Existing water rights by farmers or others may be negatively impacted by project features aiming to reduce flood risk. For example, if a reservoir is selected it may impact downstream water uses. Or new levees could damage irrigation rights. | 2 |  |  |  | 21 | Construction - Project Engineer | EPE | 5210 |  | 5 | Other |  | 5 | 0 | 0 | 20000 | 0 |  | 2 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-03-14 14:18 | 0 | 5210 |  |  | 299 | 299 | 1 | 0 | 1
25 | 3677 | Capstone |  | Utilizing existing outdated H&H model | Info and Data Analysis | 1 |  | 1 | unlikely because water levels have not changed above the threshold needed to create a new model. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 731 |  | 5 | Other |  | -5 | 1 | 100000 | 200000 | 750000 |  | 2 | 0 | 0 | 90 |  | 2 | 1 | 1 | Active | 4 | Planning | 2 | 2 | Alternatives | 2023-03-14 14:28 | 0 | 8007 |  |  | 306 | 306 | 0 | 0 | 0
2 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Sea Level Rise Model Assumption | Info and Data Analysis | 1 | Actual sea level elevation change could be greater than existing forecast models' range and resulting plans may be under-engineered. | 2 | Due to increased recent storms nationwide and given the range of possible sea level rise scenarios, there remains a fair chance of true mean sea level rise falling outside of model expectations. #Note: Need additional feedback on this |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3850 |  | 8 | Agency Strategy | Risk that proposed, recommended plan, would be insufficient or overconstructed to solve the erosion problem. | 10 | 3 | 0 | 0 | 1 | Cost varies depending on the assumed risk incorporated in the construction phase, but cost will likely be unrealized until additional data increases accuracy of current models. If sea level rise is higher in real time than what was modeled, then the rate and volume of sand erosion could be much higher. That would necessitate more frequent and or larger volumes of sand replenishment. If sea level rise is lower than what was modeled, then we may be over engineering a solution and less material/frequent nourishment would be needed. #Need further feedback to access risk cost | 4 | 0 | 0 | 0 | If the team is directed to conduct additional modeling under a different sea level change scenario it would lengthen the impact analysis and evaluation phase, this would postpone dates to reach TSP. #Need further feedback to access schedule impact | 1 | 1 | 1 | Active | 7 | Operations and Maintenance | 22 | 22 | Q1 | 2023-03-22 22:24 | 0 | 8413 |  |  | 306 | 299 | 0 | 0 | 0
4 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Economic & Hydraulic Model Approval | Agency Policy and Process | 7 | Economic and hydraulic models are assumed to be approved for single use within the time constraints of the study. Deviation from our assumed times will increase duration of project and cost. | 1 | Based on our previous communication with CSRM-PCX, we have reason to believe that the approval of the model is unlikely to be rejected or delayed. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3850 |  | 6 | Compliance | Rejecting a model would result in setbacks for the project and increased costs, as using alternative models may require additional coordination and a learning curve. | 5 | 2 | 0 | 0 | 0 | Model approval delays would prolong the analysis phase of the project and increase cost while approval is pending. Model rejection would require alternative analysis methodology, significantly increasing labor costs. | 1 | 0 | 0 | 0 | Either a delay or rejection of our models will result in schedule setbacks until we either receive approval, or under worst case scenario, find alternative methodology if required to do so. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-23 22:26 | 0 | 8413 |  |  | 299 | 299 | 0 | 0 | 0
5 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Assume Availability of Compatible Sediment Material | Site Conditions | 6 | Beach nourishment may be ineffective with incompatible sediment material currently available. A realization of said risk would require additional time to seek out alternative sediment sources, likely a time draining and costly process. | 2 | The site has been nourished prior with available sediment, so it is likely that the available sediment is compatible. # Need more feedback - on amount of sediment available and if it will be sufficient. While prior efforts for nourishment have been done, I believe the scale of our project would be larger and so the amount of sediment needed may not be met. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3850 |  | 5 | Other | Seeking out alternative sediment sources and determining an appropriate method of deliver would be time consuming and therefore increase labor cost for the planning phase. | 10 | 3 | 0 | 0 | 0 | Additional time to find alternative sediment and conduct further analysis to ensure it meets project requirements will increase labor costs, in addition to planning the sediment alternative delivery method. The total project cost would increase, as alternative sediment sources will be more expensive. | 1 | 0 | 0 | 0 | Finding alternative sediment will take time, alongside any further analysis required to ensure meets NEPA compliance and required sediment composition. Additionally, the sediment will need to be delivered, and the delivery method will also need additional time. | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-24 22:16 | 0 | 8413 |  |  | 299 | 299 | 0 | 0 | 0
6 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Dredge Vehicle Availability | Site Conditions | 6 | Assuming that there is a hydraulic cutterhead dredge, a vessel used to mix dredged sediment to ensure it is uniform. If the alternative hopper type dredge vessel was used, it could result in an incompatible sediment borrow material rendering the nourishment ineffective. We would need to source an appropriate dredge vehicle elsewhere. | 1 | Given that this area has previously been nourished regularly, appropriate equipment is expected to have been used and should still be available. #Need feedback on communications with Oceanside or relevant agency on vehicle availability. |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 3850 |  | 5 | Other | Risk may have small impacts on cost for the planning phase in terms of labor time. #Are there any other potential impacts? | 5 | 2 | 0 | 0 | 0 | Missing the appropriate dredge vessel could increase cost through additional labor cost due to time invested locate an appropriate vessel. | 1 | 0 | 0 | 0 | Locating an appropriate vessel, and could take time depending on proximity to providers. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-03-24 22:49 | 0 | 8413 |  |  | 299 | 299 | 0 | 0 | 0
7 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Project Implementation Impact on Threatened Species | Site Conditions | 6 | Assuming that timing and duration of project implementation will avoid and/or minimize impacts to endangered and threatened species in the project area. | 1 | Endangered and threatened species in the area could be placed at unintended risk, potentially violating one of our acts ("endangered species") and increase costs if remediation is necessary. The project is fairly narrow in scope and much of the work (dredging) has been ongoing before, leading to the assumption that project will cause large not external damage. |  |  | 16 | Planning - Environmental | PLE | 953 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 4 | 4 | Inactive – Entered by Error | 6 | Construction | 16 | 16 | Construction Contract Award | 2023-04-03 16:27 | 0 | 8413 |  |  | 299 | 299 | 0 | 0 | 0
8 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Planning Budget Limitation | Agency Policy and Process | 7 | The budget allocated was based on the 2016 labor rates, and so the current funding is out of step with current needs. Due to limited budget, planners time commitment will be limited on project to approximately 25% of weekly available hours, below the suggested amount. | 5 | Prior planning experience suggests a higher time preferred than budget allows; additional funding is unlikely, and we will need to adjust accordingly. |  |  | 13 | Planning - Plan Formulation | PLP | 995 |  | 5 | Other | With limited planning time availability, the report will need to have significantly higher involvement from other team members. | 10 | 4 | 0 | 0 | 0 | No cost change as there are no additional funds available. | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 4 | Planning | 1 | 1 | Project Initiation | 2023-03-27 22:39 | 0 | 8413 |  |  | 299 | 299 | 0 | 0 | 0
9 | 3691 | San Diego County Shoreline - Oceanside, CA, Mitigation Study | 104714 | Project Implementation Impact on Threatened Species | Site Conditions | 6 | Assumption that timing and duration of project implementation will avoid and/or minimize impacts to endangered and threatened species in the project area. | 1 | Endangered and threatened species in the area could be placed at unintended risk, potentially violating Endangered Species Act and increase costs if remediation is necessary. The project is narrow in scope and much of the work (dredging) has been ongoing before, leading to the view that the project will have a controlled and limited impact. It would require a very unlikely introduction of |  |  | 16 | Planning - Environmental | PLE | 953 |  | 5 | Other | Under the unlikely scenario of schedule setbacks, depending on the scale of the issue team may have issues with budget a limited budget if significant labor needs to be invested to mitigate negative externalities. | 5 | 2 | 0 | 0 | 0 | The introduction of new unaccounted for threatened species or unanticipated expansion of project scope during the planning phase would increase time and labor for the teams to plan and mitigate around concerns. | 1 | 0 | 0 | 0 | The introduction of new unaccounted for threatened species or unanticipated expansion of project scope during the planning phase would increase time and introduce schedule setbacks depending on the scale of the problem. | 1 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-03 17:15 | 0 | 8413 |  |  | 299 | 299 | 0 | 0 | 0
1 | 3771 | Atka Navigation Improvements |  | Designation of dredged material placement site | Site Conditions | 6 | Designation of a dredged material placement site will be required as part of this feasibility study. Not enough is understood at this to verify the appropriate management of the dredged material or the amount of blasting that will likely be required to provide safe navigation. | 2 | Coordination with regulatory agencies has already begun and will be managed as the project progresses and more data is available. |  |  | 16 | Planning - Environmental | PLE | 6223 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 4 | Planning | 3 | 3 | Tentatively Selected Plan | 2023-04-11 23:45 | 0 | 6223 |  |  | 299 | 299 | 0 | 0 | 1
1 | 3772 | Bluestone DSA |  | Existing Concrete Harder than Expected | Site Conditions | 6 | Concrete has a higher than expected compressive strength which could result in hihger demo costs. (Expected non issue, check with sandy) Concrete demolition has begun in the stilling basin (Weir, Apron) while demoing the concrete in the primary apron it is possible to find concrete with higher strengths and making the demoing harder. This will most likely be in a localized area in a monolith. No strength provided to the contractor in design documents. Could be inferred based on bearing plate design 3000psi. (wearing items faster than expected, method of construction slower than gov expected, without issue though. FY23 UPDATE: Currently just over 50% excavation/demo. Let side existing Apron, baffles, existing cofferdam remain to be demo'd | 2 |  |  |  | 21 | Construction - Project Engineer | EPE | 8955 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 | Marginal | 1 | 0 | 0 | 0 | Marginal | 1 | 1 | 1 | Active | 6 | Construction | 19 | 19 | Commissioning of Systems | 2023-04-12 18:58 | 0 | 8955 |  |  | 299 | 299 | 0 | 0 | 0
2 | 3772 | Bluestone DSA |  | Open Anchor Holes During Event Leads to Slab Replacement | Site Conditions | 6 | Open anchor holes exposed during a spill even could lead to slab replacement. If this were to occur there is possible dam failure. Risk to apron if hole are left open. If this occurs and a monolith is jacked it could result in replacement of slab. Similar to an "Act of God" event if the open anchor holes were exposed to spillway flow there is a potential for dam failure. (Do not model) FY23 Update No update. Left for tracking purpose. Not modeled | 1 |  |  |  | 21 | Construction - Project Engineer | EPE | 8955 |  | 5 | Other |  | 10 | 2 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 6 | Construction | 20 | 20 | Construction Completion | 2023-04-13 12:19 | 0 | 8955 |  |  | 299 | 299 | 0 | 0 | 0
3 | 3772 | Bluestone DSA |  | Project Close-Out Duration | Communications | 2 | The estimated duration of project close-out could vary. | 4 |  |  |  | 17 | Project Management | PRM | 8955 |  | 5 | Other |  | 5 | 2 | 0 | 0 | 0 |  | 0 | 180 | 180 | 365 |  | 4 | 1 | 1 | Active | 6 | Construction | 20 | 20 | Construction Completion | 2023-04-13 12:22 | 0 | 8955 |  |  | 299 | 306 | 0 | 1 | 0
1 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Inter-Agency Coordination | Communications | 2 | Adverse impact from complex project coordination between multiple interagency entities (VA, VAMC, VA CFM, VISN, USACE, SHPO). | 3 | Project will be coordinated between VA and USACE. Project Book hand over to USACE (expected 2023-2024). Historic & cultural resources work coordinated under a separate project that may have impact on the Major Project. Depending on the inclusion of Building 1 in NHPA consultation, the historic/cultural compliance effort could take several months. Mandatory approvals and decision events with USACE and VA senior leaders have been known to cause delays due to difficulty with scheduling. |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 10000 | 100000 |  | 2 | 0 | 60 | 0 | Schedule. Most likely no impact, but allow max of 2 month schedule delay per year of execution. - Cost due to schedule: Assume delays are spread out, so include escalation for 50% of project cost. | 2 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-04-27 21:24 | 0 | 9032 |  |  | 302 | 299 | 1 | 0 | 0
2 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Design Schedule | Contract Performance | 4 | Any resulting delays will incur additional schedule and costs. Delay in design delays time to market. Depending on the inclusion of Building 1 in NHPA consultation, this historic/cultural compliance effort could take several months and require additional studies as part of the consultation efforts. | 1 |  |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 17 | Design | 62 | 62 | Design Start | 2023-05-01 16:55 | 0 | 9032 |  |  | 299 | 299 | 1 | 1 | 1
3 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Growth in Design Scope | Contract Acquisition | 3 | SOW in Project Book is limited to pre-planning efforts focused on the Major Project buildings and infrastructure. Additional planning may have to be done by the AE of Record; influencing both design cost and schedule. Small cost to schedule risk. Limited SOW does not allow review of potential overall campus issues. The Project Book captures majority of project requirements. Does contain language, that the AE of Record will need to (define, design, analysis, determine...) Scope of Project Book excluded future usage of Building 1 and several smaller seismic projects on campus that require NHPA compliance. Risk could come from discovering unknown requirements, causing a delay in the schedule and increased costs. | 3 |  |  |  | 17 | Project Management | PRM | 9032 |  | 5 | Other |  | 5 | 0 | 12549897 | 24000000 | 37649692 | Almost certain to discover new requirements. Say overall 10% increase is most likely, 5-15% possible. | 4 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 16 | Planning | 61 | 61 | Planning | 2023-05-01 17:01 | 0 | 9032 |  |  | 302 | 299 | 1 | 0 | 1
4 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Design Phases | Agency Policy and Process | 7 | Project is expected to occur in multiple phases/buildings, requiring design, construction, contracting, and funding stream strict coordination to minimize gaps and holes in scope/funds. | 2 | Design approach will be influenced by Phased construction. Sequencing of work is critical and cannot be stretched out over a long period of time or design must be continuously updated. Phased construction and design inherently adds risks for oversights of the required phases. Design impacts are likely if contract is broken into phases. Impacts could be multiple mobilizations to the site, different contractors for different phases, etc. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-16 12:32 | 0 | 8774 |  |  | 299 | 299 | 1 | 1 | 1
5 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Scope Growth | Info and Data Analysis | 1 | Scope has a potential to grow through design development. | 2 | Scope Growth has the potential to increase cost. VA must ensure appropriate participation and buy-in during the design phase to minimize/control scope growth. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-05 | 0 | 8774 |  |  | 299 | 299 | 1 | 1 | 1
6 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Funding Sources | Info and Data Analysis | 1 | Funding availability for Major Project and for potential Asbestos and Hazardous Material abatement (not evaluated as part of Project Book SOW). | 3 | Hazardous Materials abatement (for buildings being demolished) budget is usually a different appropriation, is not a part of the Project Book SOW and not modeled in this cost summary. However timing (schedule), availability of funds (in-place at right time), and understanding of cost is critical. The VA will need to have this money available to complete any potential Hazardous material remediation or this may affect schedule. Review Risk Status for next meeting Budget approved for asbestos and hazardous materials (approx. $5M) * No anticipation for additional funds at this time * High likelihood/confirmation for asbestos and lead present * Need to have the scope written as value added if we are to proceed with destructive testing. * Contractor NEEDS to make all repairs for damages incurred by destructive testing. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 2000000 | 5000000 | Evidence for "Funding Sources" at medium cost risk | 2 | 2 | 120 | 240 | Evidence for "Funding Sources" at medium schedule risk | 2 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-05 | 0 | 8774 |  |  | 302 | 302 | 1 | 0 | 0
7 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | PFD changes | Info and Data Analysis | 1 | Program for Design developed and concurred by VAMC Roseburg as part of Project Book. | 1 | Final Project book to include PFD. Baseline Cost estimate assumes this to be included in Final Report. CRMP Documentation is submitted through VA for additional funding approval to reprogram project. Awaiting final decision via President Budget. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-05 | 0 | 8774 |  |  | 299 | 299 | 1 | 1 | 1
8 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | User Requested Changes | Info and Data Analysis | 1 | User requested changes on the project to increase quality/equipment and functionality after award. | 2 | Out of scope changes could result in increased cost and schedule delays. Early customer expectation management with the user groups will be critical to minimize impacts. Late change implications need to be clearly explained to the users. Initial engagement should begin at design start. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-05 | 0 | 8774 |  |  | 299 | 299 | 1 | 1 | 1
9 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Removal of Programs | Resource Availability | 5 | Risk to removing/reducing existing programs/department functions. Typically would not return. | 1 | Include review of PFD as part of initial design work to confirm space needs and uses for campus and the Major Project. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-05 | 0 | 8774 |  |  | 299 | 299 | 1 | 1 | 1
10 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Timely Response | Agency Policy and Process | 7 | Timely Response - Programming - Availability for VA leadership to make decisions in a timely manner. Reviewing and turning over submittal and RFIs to contractor as not to create a delay to the construction schedule. | 2 | Untimely responses potentially delay construction schedule placing the government at risk for payment of extended overhead. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 60 | 120 | Evidence for "Funding Sources" at medium schedule risk | 2 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-05 | 0 | 8774 |  |  | 299 | 302 | 1 | 1 | 0
11 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Swing Space | Info and Data Analysis | 1 | Phasing plan could require more or less swing space than anticipated | 2 | Team discussed that duration and type of impacts is likely to change but the cost is unlikely to change -- any change is likely to be negligible. If execution strategy changes to where more swing space is needed then likely escalation costs will decrease a similar amount due cost from schedule savings. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-05 | 0 | 8774 |  |  | 299 | 299 | 1 | 1 | 1
12 | 3792 | SEISMICALLY UPGRADE, RENO B2, REPLACE B1 | 506120 | Occupied Buildings | Agency Policy and Process | 7 | Work in occupied buildings could impact mission or delay construction | 2 | Phasing plan is developed to avoid work in occupied spaces. Even if it does happen, this is acceptable. Medical center can work with and around construction. Estimate will be updated to reflect longer durations for activation times. No add'l impact, as long as that is completed. |  |  | 17 | Project Management | PRM | 9032 |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1 | 1 | 1 | Active | 8 | Planning | 29 | 29 | Planning | 2023-05-05 | 0 | 8774 |  |  | 299 | 299 | 1 | 1 | 1
1 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Communicating a prelim alternative that may change | Legal or Regulatory Actions | 10 | Communicating a prelim alternative that may change | 3 | Communicating before TSP Agency workshop after charette |  |  | 16 | Planning - Environmental | PLE | 3454 |  | 5 | Other |  | 10 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:25 | 0 | 7996 |  |  | 306 | 299 | 1 | 1 | 1
2 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Climate change/ sea level rise | Site Conditions | 6 |  | 2 |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 9135 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:29 | 0 | 7996 |  |  | 299 | 299 | 1 | 1 | 1
3 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Sedimentation Rate | Site Conditions | 6 |  | 2 |  |  |  | 4 | Engineering - Hydrology and Hydraulics | EHH | 9135 |  | 5 | Other |  | 10 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:33 | 0 | 7996 |  |  | 299 | 299 | 0 | 1 | 1
4 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Composition of Material at Site | Site Conditions | 6 | Foundation impacts | 3 |  |  |  | 3 | Engineering - Geotechnical | EGT | 9135 |  | 5 | Other |  | 10 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:36 | 0 | 7996 |  |  | 299 | 299 | 0 | 1 | 1
5 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Sources of Rock | Contract Performance | 4 | Sourcing cheaper rock from Canada and policy problems. | 3 | Likely we won't be able to source from Canada. |  |  | 2 | Engineering - Cost | ECS | 9139 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 95 | 95 | Tentatively Selected Plan | 2023-04-27 21:39 | 0 | 7996 |  |  | 299 | 299 | 1 | 1 | 1
6 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Data Gaps | Site Conditions | 6 | Data not available and not recognized as needed until later in planning process | 2 |  |  |  | 13 | Planning - Plan Formulation | PLP | 7996 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 96 | 96 | Decision Document Approval | 2023-04-27 21:47 | 0 | 7996 |  |  | 299 | 299 | 1 | 1 | 1
7 | 3811 | Hyder Harbor Navigational Improvements | 484472 | Weather impacts for cultural Surveys | Site Conditions | 6 |  | 0 | Calculated for when already likely to have good conditions. |  |  | 14 | Planning - Cultural Resources | PLC | 9138 |  | 5 | Other |  | 5 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 1 | 1 | Active | 1 | Feasibility | 96 | 96 | Decision Document Approval | 2023-04-27 21:54 | 0 | 7996 |  |  | 299 | 299 | 1 | 1 | 1

## risk_query
Select r.RISK_ID, r.PROJECT_ID, p.PROJECT_NAME, p.P2_LOOKUP, r.RISK_NAME, c.RISKCATEGORY, r.RISKCATEGORYID, r.RISK_STATEMENT, r.PROB_OCCURRENCE, -- where is this, is there look up value? r.PROB_OCCURRENCE_EVIDENCE, r.OCCURRENCECONFIDENCEID, --o.ID, o.CONFIDENCE, r.RISKOWNERDISCIPLINEID, --d.ID, d.DISCIPLINE, d.ACRONYM as DISCIPLINE_ACRONYM, r.RISKMANAGERID, --m.id, m.RISKMANAGER, r.PERFORMANCEIMPACTTYPEID, --p.ID, p.PERFORMANCEIMPACT, r.PERFORMANCEIMPACT_DESC, r.PERFORMANCEIMPACT_IMPCT, -- WHAT IS THIS? r.PERFORMANCEIMPACT_RISK_RANKING, -- HOW IS THIS CALCULATED r.COST_IMPACT_LOWEST, r.COST_IMPACT_MOSTLIKELY, r.COST_IMPACT_HIGHEST, r.COST_IMPACT_EVIDENCE, r.COST_RISK_RANKING, -- HOW IS THIS CALCULATED r.SCHEDULE_IMPACT_LOWEST, r.SCHEDULE_IMPACT_MOSTLIKELY, r.SCHEDULE_IMPACT_HIGHEST, r.SCHEDULE_IMPACT_EVIDENCE, r.SCHEDULE_RISK_RANKING, r.RISKSTATUSID, S.ID, s.RISKSTATUS, r.PROJECTPHASEID, --h.PHASEID, h.LIFECYCLEPHASENAME, r.PROJECTMILESTONEID, n.ID, n.MILESTONE, r.EDITDATE, r.LOCKSTATUS, r.USER_ID, u.FIRST_NAME, u.LAST_NAME, r.COST_IMPACT_DISTTYPE, r.SCHEDULE_IMPACT_DISTTYPE, r.NO_PERFORMANCE_IMPACT, r.NO_COST_IMPACT, r.NO_SCHEDULE_IMPACT from APP_ERR.RISK r left outer join APP_ERR.PROJECT_VIEW_NEW p on r.PROJECT_ID = p.PROJECT_ID join APP_ERR.RISKCATEGORY c on r.RISKCATEGORYID = c.id left outer join APP_ERR.OCCURRENCECONFIDENCE o on o.ID = r.OCCURRENCECONFIDENCEID left outer join APP_ERR.RISKOWNERDISCIPLINE d on d.id = r.RISKOWNERDISCIPLINEID left outer join APP_ERR.RISKMANAGER m on m.id = r.RISKMANAGERid left outer join APP_ERR.PERFORMANCEIMPACTCATEGORY p on r.PERFORMANCEIMPACTTYPEID = p.ID left outer join APP_ERR.RISKSTATUS s on s.id = r.RISKSTATUSID left outer join app_ERR.PROJECTPHASES h on h.PHASEID = r.PROJECTPHASEID left outer join app_err.PHASEMILESTONE n on n.id = r.PROJECTMILESTONEID left outer join app_err.VTEAM_MEMBERS u on u.ID = r.USER_ID order by r.project_id, r.risk_id